## ControleQualiteProjet
Reference | CodeDocument | CodeDocumentClient | Designation | RQEP | DPCPE | DesignCoord | PC | EL | INS | MEPP | CV | SF | ISPC | ISELPRJS | ISINSPRJS | ISMEPPPRJS | ISCVPRJS | ISSFPRJS | PSLPC | PSLEL | PSLIN | PSLMEPP | PSLCV | PSLSF | CLIENT | Observation | CS | FG | TL | ISCSPRJS | ISFGPRJS | ISTL | PSLPC | PSLFG | PSLCS | PSLTL | ISPRPRJS | PSLPR | PR
AR 11/19 | R1119-RPT-GE-00-001 | 7200039700-JWWF-G06-001 | BDEP endorsement Report | Q | R | I | [7 empty] | C | C | C | C | C |  | I | I | I | I | I | [13 empty] | A | P
AR 11/19 | R1119-RPT-GE-00-005 | 7200039700-JWWF-G06-005 | Technical Study report of odor control system | Q | R | [9 empty] | C | C |  | C |  | I |  |  | I | [14 empty] | A | P
AR 11/19 | R1119-RPT-PR-00-001 | 7200039700-JWWF-P06-001 | Equipment Sizing Report | Q | R | [10 empty] | I | [21 empty] | A | P
AR 11/19 | R1119-RPT-PR-00-002 | 7200039700-JWWF-P06-002 | Hydraulic Study Report | Q | R | [10 empty] | I | [21 empty] | A | P
AR 11/19 | R1119-RPT-PR-00-003 | 7200039700-JWWF-P06-003 | Transient Analyses Report | Q | R | [10 empty] | I | [21 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-001 | 7200039700-JWWF-P01-001 | Piping & Instrumentation Diagram – Force Main Pipeline from JIC boundary to PS-56A | Q | R | C | [7 empty] | I | C | C | I | I | [19 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-012 | 7200039700-JWWF-PE-012 | Piping & Instrumentation Diagram –New Pumping Station PS-56A | Q | R | C | [7 empty] | I | C | C | I | I | [19 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-013 | 7200039700-JWWF-PE-013 | Piping & Instrumentation Diagram - Force Main Pipeline from PS-56A to SWTP-9 | Q | R | C | [7 empty] | I | C | C | I | I | [19 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-014 | 7200039700-JWWF-PE-014 | Piping & Instrumentation Diagram – Typical Details | Q | R | C | [7 empty] | I | C | C | I | I | [19 empty] | A | P
AR 11/19 | R1119-RQ-IN-00-001 | 7200039700-JWWF-I08-001 | Requisition for Control System | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-IN-00-001 | 7200039700-JWWF-I02-001 | Specification for Control System | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-ME-00-001 | 7200039700-JWWF-M02-001 | Force-main Material Specification | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-001 | 7200039700-JWWF-M08-001 | Force-main Material Requisition | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-ME-00-002 | 7200039700-JWWF-M02-002 | Sanitary Wastewater Pump Specification | Q | R | [8 empty] | C | C | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-002 | 7200039700-JWWF-M04-002 | Sanitary Waste water Pump Data Sheet | Q | R | [8 empty] | C | C | V |  | C |  |  |  | A
AR 11/19 | R1119-RQ-ME-00-002 | 7200039700-JWWF-M08-002 | Sanitary Wastewater Pump Material Requisition | Q | R | [8 empty] | C | C | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-003 | 7200039700-JWWF-M04-003 | Electrical Overhead Crane Data Sheet | Q | R | [8 empty] | C |  | V | C |  |  |  |  | A
AR 11/19 | R1119-RQ-ME-00-003 | 7200039700-JWWF-M08-003 | Electrical Overhead Crane Material Requisition | Q | R | [8 empty] | C |  | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-002 | 7200039700-JWWF-E04-002 | Data Sheet for 34,5 KV Switchgear | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-002 | 7200039700-JWWF-EE-002 | Single Line Diagram for 34,5 KV Switchgear sheet 1 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-036 | 7200039700-JWWF-EE-040 | Single Line Diagram for 34,5 KV Switchgear Sheet 2 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-037 | 7200039700-JWWF-EE-041 | Single Line Diagram for 34,5 KV Switchgear Sheet 3 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-035 | 7200039700-JWWF-EE-050 | Electrical Legends and Symbols | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-001 | 7200039700-JWWF-E08-001 | Requisition for 34.5kV RMU and SWITCHGEAR | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-003 | 7200039700-JWWF-E04-003 | Data Sheet for 34,5 KV/4,16 KV Transformer | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-002 | 7200039700-JWWF-E08-002 | Requisition for Transformers | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-004 | 7200039700-JWWF-E02-004 | Data Sheet for MV Emergency Diesel Generator | Q | R | I |  | P | [5 empty] | V |  | C |  |  |  | A
AR 11/19 | R1119-RQ-EL-00-003 | 7200039700-JWWF-E08-003 | Requisition for for MV Emergency Diesel Generator | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-005 | 7200039700-JWWF-E02-005 | Data Sheet for 4,16 KV Switchgear | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-003 | 7200039700-JWWF-EE-003 | Key One Line Diagram & Power Distribution | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-004 | 7200039700-JWWF-EE-004 | Single Line Diagram for 4,16 KV Switchgear Sheet 1 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-033 | 7200039700-JWWF-EE-005 | Single Line Diagram for 4,16 KV Switchgear Sheet 2 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-034 | 7200039700-JWWF-EE-006 | Single Line Diagram for 4,16 KV Switchgear Sheet 3 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-004 | 7200039700-JWWF-E08-004 | Requisition for MV switchgear | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-006 | 7200039700-JWWF-E04-006 | Data Sheet for MV Variable Frequency Drive | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-005 | 7200039700-JWWF-E08-005 | Requisition for MV Varible Frequency Drives Panels | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-CV-00-001 | 7200039700-JWWF-C02-001 | Topographical Survey Specification | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-CV-00-002 | 7200039700-JWWF-C02-002 | Geotechnical Survey Specification | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-CV-00-003 | 7200039700-JWWF-C02-003 | Radar Mapping Specification | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-GE-00-002 | 7200039700-JWWF-G06-002 | Site Visit Report | Q | R | I | [7 empty] | I | C | V | C | I |  | I | I | A | I | I | [13 empty] | I
AR 11/19 | R1119-RPT-GE-00-003 | 7200039700-JWWF-G06-003 | Basis Of Design | Q | R | [8 empty] | C | C | C | C | C | [19 empty] | A | P
AR 11/19 | R1119-SPC-ME-00-004 | 7200039700-JWWF-M02-004 | Piping and Valve Material Specification | Q | R | C | [9 empty] | V |  | I |  |  |  | A
AR 11/19 | R1119-SPC-ME-00-005 | 7200039700-JWWF-M02-005 | Painting and Coating Specification | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-ME-00-006 | 7200039700-JWWF-M02-006 | Hydrotest Specification | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-ME-00-007 | 7200039700-JWWF-M02-007 | Odour System Specification | Q | R | [8 empty] | C | C | V |  | C |  |  |  | A
AR 11/19 | R1119-DSH-ME-00-004 | 7200039700-JWWF-M04-004 | Valves Data Sheet | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-006 | 7200039700-JWWF-M04-006 | Quick Connection Data Sheet | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-013 | 7200039700-JWWF-M04-013 | Odour System Data Sheet | Q | R | I | [7 empty] | C | C | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-014 | 7200039700-JWWF-M04-014 | Penstocks Data Sheet | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-004 | 7200039700-JWWF-M08-004 | Piping Material Requisition | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-005 | 7200039700-JWWF-M08-005 | Valves Material Requisition | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-006 | 7200039700-JWWF-M08-006 | Quick Connection Material Requisition | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-015 | 7200039700-JWWF-M04-015 | Isolation Valve Data Sheet | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-ME-00-009 | 7200039700-JWWF-M04-009 | Air Release / Vacuum Release Valve Data Sheet | Q | R | I | [9 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-014 | 7200039700-JWWF-M08-014 | Isolation Valve Material Requisition | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-010 | 7200039700-JWWF-M08-010 | Air Release / Vacuum Release Valve Material Requisition | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-ME-00-001 | 7200039700-JWWF-M06-001 | Pipeline Stress Analysis report | Q | R | [10 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-CLC-ME-00-001 | 7200039700-JWWF-M05-001 | Force-Main Buoyancy Calculation Note | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-ME-00-002 | 7200039700-JWWF-M03-002 | DN 900 Force-main & fittings detailed MTO | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-LIS-ME-00-010 | 7200039700-JWWF-M03-003 | DN 1200 Force-main & fittings detailed MTO | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-LIS-ME-00-009 | 7200039700-JWWF-M03-009 | Force-main Valves MTO | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-001 | 7200039700-JWWF-ME-001 | Tie-in details drawing (SWTP-9) | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-002 | 7200039700-JWWF-ME-002 | Tie-in details drawing (JUBAIL TOWN) | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-003 | 7200039700-JWWF-ME-005 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-020 | 7200039700-JWWF-ME-004 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-004 | 7200039700-JWWF-ME-013 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2 | Q | R | A | [9 empty] | V | I |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-027 | 7200039700-JWWF-ME-016 | SUPPORT LIST FOR PIPELINE DN900 & DN1200 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-005 | 7200039700-JWWF-MB-005 | Isometric Drawings Tie-in connection Sheet 1 of 5 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-007 | 7200039700-JWWF-ME-006 | Isometric Drawings Tie-in connection Sheet 2 of 5 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-025 | 7200039700-JWWF-MB-007 | Isometric Drawings Tie-in connection Sheet 3 of 5 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-026 | 7200039700-JWWF-MB-008 | Isometric Drawings Tie-in connection Sheet 4 of 5 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-028 | 7200039700-JWWF-MB-009 | Isometric Drawings Tie-in connection Sheet 5 of 5 | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-018 | 7200039700-JWWF-ME-003 | Typical Force-main Crossings Drawings | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-019 | 7200039700-JWWF-ME-012 | Force-main Crossings Schedule | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-029 | 7200039700-JWWF-ME-015 | Tie-in details drawing TIE-IN 003 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DSH-ME-00-010 | 7200039700-JWWF-M04-010 | Sump Pump Data Sheet | Q | R | [8 empty] | C | C | V |  | C |  |  |  | A
AR 11/19 | R1119-DSH-ME-00-011 | 7200039700-JWWF-M04-011 | Electrical Overhead Crane for Diesel Generator Data Sheet | Q | R | [8 empty] | C |  | V | C | C |  |  |  | A
AR 11/19 | R1119-DSH-ME-00-012 | 7200039700-JWWF-M04-012 | Grinder / Macerator Data Sheet | Q | R | [8 empty] | C |  | V |  | C |  |  |  | A
AR 11/19 | R1119-RQ-ME-00-011 | 7200039700-JWWF-M08-011 | Sump Pump Material Requisition | Q | R | [8 empty] | C | C | V | [5 empty] | A
AR 11/19 | R1119-RQ-ME-00-013 | 7200039700-JWWF-M08-013 | Grinder / Macerator Material Requisition | Q | R | [8 empty] | C |  | V | [5 empty] | A
AR 11/19 | R1119-RPT-ME-00-002 | 7200039700-JWWF-M06-002 | Piping Stress Analysis PS 56-A | Q | R | [10 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-LIS-ME-00-006 | 7200039700-JWWF-M03-006 | Valve List | Q | R | [10 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-ME-00-007 | 7200039700-JWWF-M03-007 | General Piping MTO | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-008 | 7200039700-JWWF-LE-001 | General Plot Plan PS -56-A | Q | R | A | [7 empty] | C | I | V | I | C |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-009 | 7200039700-JWWF-LE-002 | 3D Model PS -56-A | Q | R | A | [7 empty] | C | C | V | C | C |  | I | I | I | [15 empty] | I
AR 11/19 | R1119-DWG-ME-00-0010 | 7200039700-JWWF-LE-003 | Piping Layout Drawings PS -56-A | Q | R | A | [7 empty] | C | I | V | I |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-011 | 7200039700-JWWF-LE-004 | Piping support Drawings PS -56-A | Q | R | A | [9 empty] | V | C |  |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-012 | 7200039700-JWWF-LB-001 | Isometric Drawings PS -56-A Sheet 1/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-032 | 7200039700-JWWF-LB-002 | Isometric Drawings PS -56-A Sheet 2/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-033 | 7200039700-JWWF-LB-003 | Isometric Drawings PS -56-A Sheet 3/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-034 | 7200039700-JWWF-LB-004 | Isometric Drawings PS -56-A Sheet 4/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-035 | 7200039700-JWWF-LB-005 | Isometric Drawings PS -56-A Sheet 5/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-036 | 7200039700-JWWF-LB-006 | Isometric Drawings PS -56-A Sheet 6/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-037 | 7200039700-JWWF-LB-007 | Isometric Drawings PS -56-A Sheet 7/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-038 | 7200039700-JWWF-LB-008 | Isometric Drawings PS -56-A Sheet 8/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-039 | 7200039700-JWWF-LB-009 | Isometric Drawings PS -56-A Sheet 9/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-040 | 7200039700-JWWF-LB-010 | Isometric Drawings PS -56-A Sheet 10/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-041 | 7200039700-JWWF-LB-011 | Isometric Drawings PS -56-A Sheet 11/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-042 | 7200039700-JWWF-LB-012 | Isometric Drawings PS -56-A Sheet 12/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-043 | 7200039700-JWWF-LB-013 | Isometric Drawings PS -56-A Sheet 13/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-044 | 7200039700-JWWF-LB-014 | Isometric Drawings PS -56-A Sheet 14/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-045 | 7200039700-JWWF-LB-015 | Isometric Drawings PS -56-A Sheet 15/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-046 | 7200039700-JWWF-LB-016 | Isometric Drawings PS -56-A Sheet 16/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-047 | 7200039700-JWWF-LB-017 | Isometric Drawings PS -56-A Sheet 17/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-048 | 7200039700-JWWF-LB-018 | Isometric Drawings PS -56-A Sheet 18/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-049 | 7200039700-JWWF-LB-019 | Isometric Drawings PS -56-A Sheet 19/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-050 | 7200039700-JWWF-LB-020 | Isometric Drawings PS -56-A Sheet 20/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-051 | 7200039700-JWWF-LB-021 | Isometric Drawings PS -56-A Sheet 21/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-052 | 7200039700-JWWF-LB-022 | Isometric Drawings PS -56-A Sheet 22/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-053 | 7200039700-JWWF-LB-023 | Isometric Drawings PS -56-A Sheet 23/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-054 | 7200039700-JWWF-LB-024 | Isometric Drawings PS -56-A Sheet 24/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-055 | 7200039700-JWWF-LB-025 | Isometric Drawings PS -56-A Sheet 25/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-056 | 7200039700-JWWF-LB-026 | Isometric Drawings PS -56-A Sheet 26/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-057 | 7200039700-JWWF-LB-027 | Isometric Drawings PS -56-A Sheet 27/36 | Q | R | A | [9 empty] | V
AR 11/19 | R1119-DWG-ME-00-058 | 7200039700-JWWF-LB-028 | Isometric Drawings PS -56-A Sheet 28/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-059 | 7200039700-JWWF-LB-029 | Isometric Drawings PS -56-A Sheet 29/36 | Q | R | A | [9 empty] | V
AR 11/19 | R1119-DWG-ME-00-060 | 7200039700-JWWF-LB-030 | Isometric Drawings PS -56-A Sheet 30/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-061 | 7200039700-JWWF-LB-031 | Isometric Drawings PS -56-A Sheet 31/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-062 | 7200039700-JWWF-LB-032 | Isometric Drawings PS -56-A Sheet 32/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-063 | 7200039700-JWWF-LB-033 | Isometric Drawings PS -56-A Sheet 33/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-064 | 7200039700-JWWF-LB-034 | Isometric Drawings PS -56-A Sheet 34/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-065 | 7200039700-JWWF-LB-035 | Isometric Drawings PS -56-A Sheet 35/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-066 | 7200039700-JWWF-LB-036 | Isometric Drawings PS -56-A Sheet 36/36 | Q | R | A | [9 empty] | V | [5 empty] | I
AR 11/19 | R1119-DWG-ME-00-022 | 7200039700-JWWF-LE-005 | Section and Detail Drawing PS-56A Sheet 1/2 | Q | R | A | [7 empty] | I | I | V | I | I |  |  |  | I
AR 11/19 | R1119-DWG-ME-00-023 | 7200039700-JWWF-LE-006 | Section and Detail Drawing PS-56A Sheet 2/2 | Q | R | A | [7 empty] | I | I | V | I | I |  |  |  | I
AR 11/19 | R1119-RPT-PR-00-004 | 7200039700-JWWF-P06-004 | Operating And Control Philosophy | Q | R | [9 empty] | C | [22 empty] | A | P
AR 11/19 | R1119-RPT-PR-00-005 | 7200039700-JWWF-P06-005 | Operating And Maintenance Manual | Q | R | [32 empty] | A | P
AR 11/19 | R1119-LIS-PR-00-001 | 7200039700-JWWF-P03-001 | Symbol And Abbreviations List | Q | R | [9 empty] | I | I | [21 empty] | A | P
AR 11/19 | R1119-LIS-PR-00-002 | 7200039700-JWWF-P03-002 | Equipment List | Q | R | [8 empty] | C |  | C |  | I | [19 empty] | A | P
AR 11/19 | R1119-LIS-PR-00-003 | 7200039700-JWWF-P03-003 | Line List | Q | R | [10 empty] | C |  | I | [19 empty] | A | P
AR 11/19 | R1119-LIS-PR-00-004 | 7200039700-JWWF-P03-004 | Tie-In list | Q | R | [10 empty] | C |  | I | [19 empty] | A | P
AR 11/19 | R1119-LIS-PR-00-005 | 7200039700-JWWF-P03-005 | Cause And Effect Diagram | Q | R | [9 empty] | C | [22 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-002 | 7200039700-JWWF-PE-002 | Block Flow Diagram | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-003 | 7200039700-JWWF-PE-003 | Process Flow Diagram – Force Main Pipeline from JIC boundary to PS-56A | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-010 | 7200039700-JWWF-PE-004 | Process Flow Diagram –New Pumping Station PS-56A | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-011 | 7200039700-JWWF-PE-005 | Process Flow Diagram - Force Main Pipeline from PS-56A to SWTP-9 | Q | R | [32 empty] | A | P
AR 11/19 | R1119-SPC-PR-00-001 | 7200039700-JWWF-P02-001 | Specification for Packaged Air conditioning unit (PACU) | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DSH-PR-00-001 | 7200039700-JWWF-P04-001 | Data Sheet for Packaged Air conditioning unit (PACU) | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DSH-PR-00-002 | 7200039700-JWWF-P04-002 | Data Sheet for Exhaust Fans | Q | R | [32 empty] | A | P
AR 11/19 | R1119-CLC-PR-00-001 | 7200039700-JWWF-P05-001 | HVAC Calculation Note | Q | R | [32 empty] | A | P
AR 11/19 | R1119-RQ-PR-00-001 | 7200039700-JWWF-P08-001 | Requisition for HVAC equipment | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-004 | 7200039700-JWWF-PE-015 | Electrical Building and Sec Room HVAC system Layout1/4 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-015 | 7200039700-JWWF-PE-016 | Electrical Building and Sec Room HVAC system Layout Sheet 2/4 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-016 | 7200039700-JWWF-PE-017 | Electrical Building and Sec Room HVAC system Layout Sheet 3/4 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-017 | 7200039700-JWWF-PE-018 | Electrical Building and Sec Room HVAC system Layout Sheet 4/4 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-006 | 7200039700-JWWF-PE-006 | PLUMBING and HVAC Legend | Q | R | [32 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-007 | 7200039700-JWWF-PE-007 | PLUMBING & Sanitary Layout | Q | R | C | [10 empty] | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-008 | 7200039700-JWWF-PE-008 | Pump Room HVAC system Layout Sheet 1/2 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-019 | 7200039700-JWWF-PE-019 | Pump Room HVAC system Layout Sheet 2/2 | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-DWG-PR-00-009 | 7200039700-JWWF-PE-009 | Generator Building HVAC system Layout | Q | R | C | [7 empty] | I |  |  | C | [20 empty] | A | P
AR 11/19 | R1119-SPC-IN-00-002 | 7200039700-JWWF-I02-002 | General Specification of Instrumentation | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-IN-00-003 | 7200039700-JWWF-I02-003 | Specification for Instrumentation Cables | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-IN-00-004 | 7200039700-JWWF-I02-004 | Specification for Fire and Gas System | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-IN-00-005 | 7200039700-JWWF-I02-005 | Specification for Telephony and LAN | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-001 | 7200039700-JWWF-I03-001 | List of Instruments | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-002 | 7200039700-JWWF-I03-002 | List of Inputs / Outputs | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-003 | 7200039700-JWWF-I03-003 | List of Instrumentation Cables | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-004 | 7200039700-JWWF-I03-004 | Instrumentations accessories BOQ | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-005 | 7200039700-JWWF-I03-005 | MTO for Telephony and LAN | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-IN-00-006 | 7200039700-JWWF-I03-006 | MTO fire and gas | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-001 | 7200039700-JWWF-IE-001 | Control System Architecture | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-002 | 7200039700-JWWF-IE-002 | Instrumentation Block Diagram | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-003 | 7200039700-JWWF-IE-003 | Instrumentation Loop Diagram Sheet 1/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-015 | 7200039700-JWWF-IE-015 | Instrumentation Loop Diagram Sheet 2/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-016 | 7200039700-JWWF-IE-016 | Instrumentation Loop Diagram Sheet 3/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-017 | 7200039700-JWWF-IE-017 | Instrumentation Loop Diagram Sheet 4/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-018 | 7200039700-JWWF-IE-018 | Instrumentation Loop Diagram Sheet 5/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-019 | 7200039700-JWWF-IE-019 | Instrumentation Loop Diagram Sheet 6/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-020 | 7200039700-JWWF-IE-020 | Instrumentation Loop Diagram Sheet 7/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-021 | 7200039700-JWWF-IE-021 | Instrumentation Loop Diagram Sheet 8/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-022 | 7200039700-JWWF-IE-022 | Instrumentation Loop Diagram Sheet 9/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-023 | 7200039700-JWWF-IE-023 | Instrumentation Loop Diagram Sheet 10/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-028 | 7200039700-JWWF-IE-028 | Instrumentation Loop Diagram Sheet 11/11 | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-004 | 7200039700-JWWF-IE-004 | Instrument layout | Q | R | C |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-005 | 7200039700-JWWF-IE-005 | Instrument Cable routing Sheet 1/4 | Q | R | C |  |  | P |  |  |  |  | I | V |  | C |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-006 | 7200039700-JWWF-IE-006 | Instrument Cable routing Sheet 2/4 | Q | R | C |  |  | P |  |  |  |  | I | V |  | C |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-013 | 7200039700-JWWF-IE-007 | Instrument Cable routing Sheet 3/4 | Q | R | C |  |  | P |  |  |  |  | I | V |  | C |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-027 | 7200039700-JWWF-IE-027 | Instrument Cable routing Sheet 4/4 | Q | R | C |  |  | P |  |  |  |  | I | V |  | C |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-007 | 7200039700-JWWF-IE-008 | Junction Box Connection Diagrams | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-008 | 7200039700-JWWF-IE-009 | F&G detectors location Drawing Sheet 1/3 | Q | R | C |  |  | P | [5 empty] | V |  | I | C |  |  | A
AR 11/19 | R1119-DWG-IN-00-014 | 7200039700-JWWF-IE-014 | F&G detectors location Drawing Sheet 2/3 | Q | R | C |  |  | P | [5 empty] | V |  | I | C |  |  | A
AR 11/19 | R1119-DWG-IN-00-024 | 7200039700-JWWF-IE-024 | F&G detectors location Drawing Sheet 3/3 | Q | R | C |  |  | P | [5 empty] | V |  | I | C |  |  | A
AR 11/19 | R1119-DWG-IN-00-011 | 7200039700-JWWF-IE-011 | Instrumentation Hookup Drawing sheet 1/2 | Q | R | C |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-025 | 7200039700-JWWF-IE-025 | Instrumentation Hookup Drawing sheet 2/2 | Q | R | C |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-010 | 7200039700-JWWF-IE-012 | Telephony and LAN Implementation Plan | Q | R | C |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-IN-00-012 | 7200039700-JWWF-IE-013 | Junction Box mounting and installation details | Q | R | C |  |  | P | [5 empty] | V |  | C |  |  |  | A
AR 11/19 | R1119-DWG-IN-00-009 | 7200039700-JWWF-IE-010 | Fire alarm riser diagram: | Q | R | C |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-IN-00-001 | 7200039700-JWWF-I04-001 | Data Sheet for Fire and Gas System Instruments | Q | R |  |  |  | P | [5 empty] | V |  |  | C |  |  | A
AR 11/19 | R1119-DSH-IN-00-002 | 7200039700-JWWF-I04-002 | Data Sheet for Pressure Measuring Instruments | Q | R | I |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-IN-00-003 | 7200039700-JWWF-I04-003 | Data Sheet for Flow Measuring Instruments | Q | R | I |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-DSH-IN-00-004 | 7200039700-JWWF-I04-004 | Data Sheet for Level Measuring Instruments | Q | R | I |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-IN-00-005 | 7200039700-JWWF-I04-005 | Data Sheet for Measuring and Analysis Instruments | Q | R | I |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-DSH-IN-00-006 | 7200039700-JWWF-I04-006 | Data Sheet for MOVs | Q | R | I |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-DSH-IN-00-007 | 7200039700-JWWF-I04-007 | Datasheet of Junction Boxes | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-IN-00-008 | 7200039700-JWWF-I04-008 | Instrumentation cable Data Sheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-002 | 7200039700-JWWF-I08-002 | Requisition for Fire and Gas System | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-003 | 7200039700-JWWF-I08-003 | Requisition for Telephony and LAN | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-004 | 7200039700-JWWF-I08-004 | Requisition for MOVs | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-005 | 7200039700-JWWF-I08-005 | Requisition for Pressure Measuring Instruments | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-006 | 7200039700-JWWF-I08-006 | Requisition for Flow Measuring Instruments | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-007 | 7200039700-JWWF-I08-007 | Requisition for Level Measuring Instruments | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-008 | 7200039700-JWWF-I08-008 | Requisition for Measuring Instruments and Analysis | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-009 | 7200039700-JWWF-I08-009 | Requisition for Junction Boxes | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-010 | 7200039700-JWWF-I08-010 | Requisition for Cables Instrumentation | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-IN-00-011 | 7200039700-JWWF-I08-011 | Requisition for Accessories and Fittings | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-007 | 7200039700-JWWF-E04-007 | Data Sheet for 4,16 KV/0,48 KV Transformer | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-008 | 7200039700-JWWF-E04-008 | Data Sheet for MCC/Switchboard | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-009 | 7200039700-JWWF-E04-009 | Data Sheet for Dry Type Transformer | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-011 | 7200039700-JWWF-E04-011 | Data Sheet for AC UPS | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DSH-EL-00-012 | 7200039700-JWWF-E04-012 | Data Sheet for DC Battery charger and Rectifier | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-EL-00-001 | 7200039700-JWWF-E06-001 | Load Flow Analysis Report | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-EL-00-002 | 7200039700-JWWF-E06-002 | Short circuit Study | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-EL-00-003 | 7200039700-JWWF-E06-003 | Motor Starting Study | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-EL-00-004 | 7200039700-JWWF-E06-004 | Relay Co-ordination and selectivity study | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-001 | 7200039700-JWWF-E05-001 | MV Cable Sizing Calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-002 | 7200039700-JWWF-E05-002 | LV Cable Sizing Calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-003 | 7200039700-JWWF-E05-003 | Indoor Lighting System Calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-004 | 7200039700-JWWF-E05-004 | Outdoor Lighting System Calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-005 | 7200039700-JWWF-E05-005 | Earthing & Lightning calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-006 | 7200039700-JWWF-E05-006 | Detailed Calculation for Electrical Equipments | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-EL-00-007 | 7200039700-JWWF-E05-007 | AC & DC UPS Sizing Calculation | Q | R |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-CLC-EL-00-008 | 7200039700-JWWF-E05-008 | Power Factor Improvement Calculation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-002 | 7200039700-JWWF-E03-002 | Electrical Equipment List | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-003 | 7200039700-JWWF-E03-003 | Calculation Load Normal Operation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-004 | 7200039700-JWWF-E03-004 | Calculation Load Standby Operation | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-005 | 7200039700-JWWF-E03-005 | Electrical MV Cable Schedule | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-006 | 7200039700-JWWF-E03-006 | Electrical LV Cable Schedule | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-007 | 7200039700-JWWF-E03-007 | Electrical Tie-in Schedule | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-008 | 7200039700-JWWF-E03-008 | Lighting Equipments and Fixtures MTO | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-009 | 7200039700-JWWF-E03-009 | Earthing & Lightning Protection Systems Material List | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-EL-00-010 | 7200039700-JWWF-E03-010 | Electrical Bulk material List | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-006 | 7200039700-JWWF-EE-008 | Single Line Diagram for LV MCC/Switchboard | Q | R |  |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-007 | 7200039700-JWWF-EE-009 | Single Line Diagram for AC UPS | Q | R |  |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-008 | 7200039700-JWWF-EE-010 | Single Line Diagram for DC Battery charger and Rectifier | Q | R |  |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-009 | 7200039700-JWWF-EE-011 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules | Q | R |  |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-010 | 7200039700-JWWF-EE-012 | Single Line Diagram for External Lighting Distrubition Panels | Q | R |  |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-011 | 7200039700-JWWF-EE-013 | Typical Schematic and Wiring Diagrams sheet 1 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-038 | 7200039700-JWWF-EE-014 | Typical Schematic and Wiring Diagrams sheet 2 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-039 | 7200039700-JWWF-EE-015 | Typical Schematic and Wiring Diagrams sheet 3 of 3 | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-012 | 7200039700-JWWF-EE-055 | Equipments Arrangement for CUSTOMER and SEC Buildings | Q | R | C |  | P | [5 empty] | V |  |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-013 | 7200039700-JWWF-EE-065 | Cable Routing Layout & Details for CUSTOMER and SEC Buildings | Q | R | C |  | P | [5 empty] | V |  |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-014 | 7200039700-JWWF-EE-016 | Indoor Lighting & Small Power for CUSTOMER and SEC Buildings | Q | R |  |  | P | [5 empty] | V |  |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-015 | 7200039700-JWWF-EE-017 | Earthing Details for CUSTOMER and SEC Buildings | Q | R | C |  | P | [5 empty] | V | I |  |  |  |  | A
AR 11/19 | R1119-DWG-EL-00-016 | 7200039700-JWWF-EE-018 | Lightning protection layout for CUSTOMER and SEC Buildings | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-017 | 7200039700-JWWF-EE-019 | General Cable Routing Layout | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-018 | 7200039700-JWWF-EE-020 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings 1/3 | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-043 | 7200039700-JWWF-EE-018 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings Sheet 2/3 | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-044 | 7200039700-JWWF-EE-035 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings Sheet 3/3 | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-019 | 7200039700-JWWF-EE-021 | Cable Routing Layout & Details for Pump House building Sheet 1/3 | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-020 | 7200039700-JWWF-EE-022 | Cable Routing Layout & Details for Pump House building Sheet 2/3 | Q | R | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-042 | 7200039700-JWWF-EE-042 | Cable Routing Layout & Details for Pump House building Sheet 3/3 | Q |  | C |  | P | [5 empty] | V | I |  | C |  |  | A
AR 11/19 | R1119-DWG-EL-00-021 | 7200039700-JWWF-EE-023 | External Lighting Layout | Q | R | C |  | P | [5 empty] | V |  |  | I |  |  | A
AR 11/19 | R1119-DWG-EL-00-022 | 7200039700-JWWF-EE-024 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-023 | 7200039700-JWWF-EE-025 | Indoor Lighting & Small Power for Pump Station building | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-024 | 7200039700-JWWF-EE-026 | Overall Earthing Layout | Q | R | C |  | P | [5 empty] | V |  |  | I |  |  | A
AR 11/19 | R1119-DWG-EL-00-025 | 7200039700-JWWF-EE-027 | Earthing Details for Electrical/Control/Diesel Generator Buildings | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-026 | 7200039700-JWWF-EE-028 | Earthing Details for Pump Station building | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-027 | 7200039700-JWWF-EE-029 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-032 | 7200039700-JWWF-EE-030 | Electrical Routing Installation Details | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-028 | 7200039700-JWWF-EE-031 | Electrical Lighting Installation Details | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-029 | 7200039700-JWWF-EE-032 | Electrical Earthing & Lightning Installation Details | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-032 | 7200039700-JWWF-EE-034 | Lightning protection layout for Pump House building | Q | R | C |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-EL-00-031 | 7200039700-JWWF-EE-033 | Electrical Interconection Drawing | Q | R |  |  | P | [5 empty] | V | C |  |  |  |  | A
AR 11/19 | R1119-RQ-EL-00-007 | 7200039700-JWWF-E08-007 | Requisition for LV MCC/Switchboard | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-009 | 7200039700-JWWF-E08-009 | Requisition for AC Uninterruptible Power Supply | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-010 | 7200039700-JWWF-E08-010 | Requisition for DC Battery charger and Rectifier | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-011 | 7200039700-JWWF-E08-011 | Requisition for MV/LV Electrical Cables | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-013 | 7200039700-JWWF-E08-013 | Requisition for Lighting Equipments and Fixtures | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-014 | 7200039700-JWWF-E08-014 | Requisition for Earthing & Lightning Protection Systems | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-EL-00-015 | 7200039700-JWWF-E08-015 | Requisition for Electrical Bulk material | Q | R |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RPT-SF-00-001 | 7200039700-JWWF-F06-001 | HSE Philosophy | Q | R | [6 empty] | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-RPT-SF-00-002 | 7200039700-JWWF-F06-002 | Fire Fighting Calculations Report | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-SF-00-002 | 7200039700-JWWF-FE-002 | fire fighting layout Sheet 1 of 2 | Q | R | C | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-SF-00-004 | 7200039700-JWWF-FE-004 | fire fighting layout Sheet 2 of 2 | Q | R | C | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-SF-00-003 | 7200039700-JWWF-FE-003 | Hazardous Area Classification Layout | Q | R | C | [5 empty] | P |  | I | I |  |  | V | [5 empty] | A
AR 11/19 | R1119-LIS-SF-00-001 | 7200039700-JWWF-F03-001 | Safety equipment list | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-LIS-SF-00-002 | 7200039700-JWWF-F03-002 | Hazardous Area Classification Schedule | Q | R | [6 empty] | P |  | I | I |  |  | V | [5 empty] | A
AR 11/19 | R1119-DSH-SF-00-001 | 7200039700-JWWF-F04-001 | Safety Equipment Datasheet | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-SPC-SF-00-001 | 7200039700-JWWF-F02-001 | Safety Equipment Specification | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-RQ-SF-00-001 | 7200039700-JWWF-F08-001 | Safety Equipment Requisition | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-001 | 7200039700-JWWF-AE-001 | Site Development Plan-New Pump Station | Q | R | C |  |  |  |  | P |  |  |  |  | C | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-002 | 7200039700-JWWF-AE-002 | Electrical and Control Building -Ground Floor | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-003 | 7200039700-JWWF-AE-003 | Electrical and Control Building FIRST FLOOR AND CABLE CELLAR PLAN | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-004 | 7200039700-JWWF-AE-004 | Electrical and Control BuildingROOF PLAN | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-005 | 7200039700-JWWF-AE-005 | Electrical and Control Building ELEVATIONS | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-006 | 7200039700-JWWF-AE-006 | Electrical and Control Building SECTIONS | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-007 | 7200039700-JWWF-AE-007 | ELECTRICAL AND CONTROL BUILDING CEILING PLAN | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-008 | 7200039700-JWWF-AE-008 | ELECTRICAL AND CONTROL BUILDING TOILET & KITCHEN | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-009 | 7200039700-JWWF-AE-009 | ELECTRICAL AND CONTROL BUILDING DOORS AND WINDOWS | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-066 | 7200039700-JWWF-AE-0010 | ELECTRICAL AND CONTROL BUILDING MISCELLANEOUS DETAILS | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-010 | 7200039700-JWWF-SE-001 | Structural General Notes Sheet 1/2 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-011 | 7200039700-JWWF-SE-002 | Structural General Notes Sheet 2/2 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-012 | 7200039700-JWWF-SE-003 | Sewer Pump Station Foundation Layout and details sheet 1 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-013 | 7200039700-JWWF-SE-004 | Sewer Pump Station Foundation Layout and details sheet 2 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-014 | 7200039700-JWWF-SE-005 | Sewer Pump Station Steel Structure Layout and details sheet 3 | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-015 | 7200039700-JWWF-SE-006 | Sewer Pump Station Steel Structure Layout and details sheet 4 | Q | R | C |  |  |  |  | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-070 | 7200039700-JWWF-SE-007 | Sewer Pump Station Foundation Layout and details sheet 5 | Q | R | [5 empty] | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-071 | 7200039700-JWWF-SE-008 | Sewer Pump Station Foundation Layout and details sheet 6 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-072 | 7200039700-JWWF-SE-009 | Sewer Pump Station Foundation Layout and details sheet 7 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-016 | 7200039700-JWWF-SE-010 | Electrical and Control Building Foundation, columns slab Layout | Q | R | [5 empty] | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-017 | 7200039700-JWWF-SE-011 | Electrical and Control Building Ground Beam and slab on grade layout sheet 1 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-018 | 7200039700-JWWF-SE-012 | Electrical and Control Building Ground Beam and slab on grade layout sheet 2 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-019 | 7200039700-JWWF-SE-013 | ELECTRICAL AND CONTROL BUILDING BEAMS AND ROOF LAYOUT | Q | R | [5 empty] | P |  |  | C |  |  | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-020 | 7200039700-JWWF-SE-014 | Electrical Building building structural details Sheet 1 | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-021 | 7200039700-JWWF-SE-015 | Sec Interface Building Building Steel Roofing Layout and details | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-025 | 7200039700-JWWF-SE-019 | Flow Meter Chamber -Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-026 | 7200039700-JWWF-SE-020 | Air Release Chamber -Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-027 | 7200039700-JWWF-SE-021 | Isolation Chamber - Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-028 | 7200039700-JWWF-SE-22 | Washout Chamber-Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-081 | 7200039700-JWWF-SE-023 | Air Release Chamber for pipe 1200-Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-082 | 7200039700-JWWF-SE-024 | Isolation Chamber for pipe 1200-- Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-083 | 7200039700-JWWF-SE-025 | Washout Chamber for pipe 1200--Formwork and reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-084 | 7200039700-JWWF-SE-026 | Ladder and covers miscellaneous details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-029 | 7200039700-JWWF-CE-001 | Civil works General arrangement drawing | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-030 | 7200039700-JWWF-CE-002 | Site Grading & Paving Plan-New Pump Station | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-031 | 7200039700-JWWF-CE-003 | Road grading and layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-032 | 7200039700-JWWF-CE-004 | Road Cross Section Drawing | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-033 | 7200039700-JWWF-CE-005 | Strom Water Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-034 | 7200039700-JWWF-CE-006 | PW & Sewer network layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-035 | 7200039700-JWWF-CE-007 | Fence Layout and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-064 | 7200039700-JWWF-CE-008 | Fence and Gates Details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-065 | 7200039700-JWWF-CE-009 | Manholes and connexions drawing | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-036 | 7200039700-JWWF-CE-010 | Miscellaneous Civil Works details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-067 | 7200039700-JWWF-CE-011 | Site Demolition Plan New Pump Station | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-068 | 7200039700-JWWF-CE-031 | PS56 TO SWTP-9 SWW FORCE-MAIN ROUTE MAP Sheet 1/3 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-069 | 7200039700-JWWF-CE-032 | PS56 TO SWTP-9 SWW FORCE-MAIN ROUTE MAP Sheet 2/3 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-073 | 7200039700-JWWF-CE-033 | PS56 TO SWTP-9 SWW FORCE-MAIN ROUTE MAP Sheet 3/3 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-038 | 7200039700-JWWF-CE-021 | Forcemain 1200 Alignement Sheet 1 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-039 | 7200039700-JWWF-CE-022 | Forcemain 1200 Alignement Sheet 2 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-040 | 7200039700-JWWF-CE-023 | Forcemain 1200 Alignement Sheet 3 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-041 | 7200039700-JWWF-CE-024 | Forcemain 1200 Alignement Sheet 4 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-042 | 7200039700-JWWF-CE-025 | Forcemain 1200 Alignement Sheet 5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-043 | 7200039700-JWWF-CE-026 | Forcemain 1200 Alignement Sheet 6 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-044 | 7200039700-JWWF-CE-027 | Forcemain 1200 Alignement Sheet 7 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-045 | 7200039700-JWWF-CE-028 | Forcemain 1200 Alignement Sheet 8 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-053 | 7200039700-JWWF-CE-050 | JUBAIL-TOWN SWW FORCE-MAIN ROUTE MAP (FROM JIC) |  | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-054 | 7200039700-JWWF-CE-051 | Forcemain 900 Alignement Sheet 1/5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-055 | 7200039700-JWWF-CE-052 | Forcemain 900 Alignement Sheet 2/5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-056 | 7200039700-JWWF-CE-053 | Forcemain 900 Alignement Sheet 3/5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-057 | 7200039700-JWWF-CE-054 | Forcemain 900 Alignement Sheet 4/5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-058 | 7200039700-JWWF-CE-055 | Forcemain 900 Alignement Sheet 5/5 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-063 | 7200039700-JWWF-CE-060 | Force-main Trench Details Standard Drawings | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-001 | 7200039700-JWWF-S05-001 | Sewer Pump Sation Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-002 | 7200039700-JWWF-S05-002 | Electrical and Control Building Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-003 | 7200039700-JWWF-S05-003 | Sec Interface Building Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-004 | 7200039700-JWWF-S05-004 | Generator Building Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-005 | 7200039700-JWWF-S05-005 | Flow Meter Chamber Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-006 | 7200039700-JWWF-S05-006 | Air Release Chamber Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-007 | 7200039700-JWWF-S05-007 | Isolation Chamber Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-CLC-CV-00-008 | 7200039700-JWWF-S05-008 | Washout Chamber Calculation Note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-074 | 7200039700-JWWF-SE-027 | Sewer Pump Station Foundation Layout and details sheet 7-steel structure detail | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-075 | 7200039700-JWWF-SE-028 | Operating platform steel structure drawing -PLF1-PLF2 | Q | R | C |  |  |  |  | P |  |  |  |  | I | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-076 | 7200039700-JWWF-SE-029 | Operating platform steel structure drawing -PLF3 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-077 | 7200039700-JWWF-SE-030 | Operating platform steel structure drawing -PLF4 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-078 | 7200039700-JWWF-SE-031 | Operating platform steel structure drawing -PLF5 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-079 | 7200039700-JWWF-SE-032 | Operating platform steel structure drawing -PLF6 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-080 | 7200039700-JWWF-SE-033 | Operating platform steel structure drawing -steel stucture detail | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A
AR 11/19 | R1119-DWG-CV-00-090 | 7200039700-JWWF-SE-034 | Odor control system foundation detail | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A