## ControleQualiteProjet
Reference | CodeDocument | CodeDocumentClient | Designation | RQEP | DP/CPE | PR | EL | IN/TL | CV/ST | ME/PP | PC | SF | IS PR/PRJS | IS EL/PRJS | IS IN/TL/PRJS | IS ME/PP/PRJS | IS CV/ST/PRJS | IS PC | IS SF/PRJS | PSL PR | PSL EL | PSL IN/TL | PSL ME/PP | PSL CV/ST | PSL PC | PSL SF | CPRJ
AR 06/22 | AR0622-RPT-GE-00-001 | ARO1822-RPT-GE-00-001 | Design Basis Report | Q |  | P | [6 empty] | V | I | I | I | I | I | I | A | I | I | I | I |  | I
AR 06/22 | AR0622-RPT-GE-00-002 | ARO1822-RPT-GE-00-002 | Site Visit Report | Q
AR 06/22 | AR0622-DWG-PR-00-001 | ARO1822-DWG-PR-00-001 | Symbols And Abreviations List | Q | R | P | [6 empty] | V | [6 empty] | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-002 | ARO1822-DWG-PR-00-002 | Booster Pumps P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-003 | ARO1822-DWG-PR-00-003 | Booster Pumps P&Id (Demolition) | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-004 | ARO1822-DWG-PR-00-004 | Export Pumps P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-005 | ARO1822-DWG-PR-00-005 | Export Pumps P&Id (Demolition) | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-006 | ARO1822-DWG-PR-00-006 | Hydrocyclones P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-007 | ARO1822-DWG-PR-00-007 | Hydrocyclones P&Id (Demolition) | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-008 | ARO1822-DWG-PR-00-008 | Surge Tank P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-009 | ARO1822-DWG-PR-00-009 | Pipeline P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-DWG-PR-00-010 | ARO1822-DWG-PR-00-010 | Oily Water P&Id | Q | R | P | [6 empty] | V | I | C | I | I |  | I | A | [6 empty] | C
AR 06/22 | AR0622-RPT-PR-00-001 | ARO1822-RPT-PR-00-001 | Line Sizing Report | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RPT-PR-00-002 | ARO1822-RPT-PR-00-002 | Utilities Consumption Report (Update) | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RPT-PR-00-003 | ARO1822-RPT-PR-00-003 | Operation & Control Philosophy (Update) | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RPT-PR-00-004 | ARO1822-RPT-PR-00-004 | Hazop Report | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RPT-PR-00-005 | ARO1822-RPT-PR-00-005 | Hazop Close Out Report | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-PR-00-001 | ARO1822-LIS-PR-00-001 | Process Equipement List | Q | R | P | [6 empty] | V | I | I | I | I | I | I | A
AR 06/22 | AR0622-LIS-PR-00-002 | ARO1822-LIS-PR-00-002 | Process Line List (Update) | Q | R | P | [6 empty] | V | I |  | I | I | I | I | A | [6 empty] | I
AR 06/22 | AR0622-LIS-PR-00-003 | ARO1822-LIS-PR-00-003 | Tie Ins List | Q | R | P | [6 empty] | V | [6 empty] | A | [6 empty] | I
AR 06/22 | AR0622-LIS-PR-00-004 | ARO1822-LIS-PR-00-004 | Utilities Consumption Lists | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-PR-00-005 | ARO1822-LIS-PR-00-005 | Cause & Effect Diagrams (Update) | Q | R | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RPT-PP-00-001 | ARO1822-RPT-PP-00-001 | Piping Stress Analysis Report For Cellar Deck P3 Area | Q | R |  |  |  |  | P | [5 empty] | V | I | [5 empty] | A
AR 06/22 | AR0622-RPT-PP-00-002 | ARO1822-RPT-PP-00-002 | Piping Stress Analysis Report For Cellar Deck P2 Area | Q | R |  |  |  |  | P | [5 empty] | V | I | [5 empty] | A
AR 06/22 | AR0622-LIS-PP-00-001 | ARO1822-LIS-PP-00-001 | Valves List | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | I | A
AR 06/22 | AR0622-LIS-PP-00-002 | ARO1822-LIS-PP-00-002 | Piping & Fittings Mto | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | I |  |  |  | A
AR 06/22 | AR0622-LIS-PP-00-003 | ARO1822-LIS-PP-00-003 | Piping Supports List | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-PP-00-001 | ARO1822-DWG-PP-00-001 | Equipment Arrangment Plan | Q | R |  |  |  |  | P |  |  | I | I | I | V | I | I | I |  |  |  | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-002 | ARO1822-DWG-PP-00-002 | Piping Layout Drawing For Cellar Deck P3 Area | Q | R |  |  |  |  | P |  |  | I | I | I | V | I | I | I |  |  |  | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-003 | ARO1822-DWG-PP-00-003 | Piping Layout Drawing For Cellar Deck P2 Area | Q | R |  |  |  |  | P |  |  | I | I | I | V | I | I | I |  |  |  | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-004 | ARO1822-DWG-PP-00-004 | Piping Layout Drawing For Cellar Deck P3 Area (Demolition) | Q | R |  |  |  |  | P |  |  | I | I | I | V | I | I | I |  |  |  | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-005 | ARO1822-DWG-PP-00-005 | Piping Layout Drawing For Cellar Deck P2 Area (Demolition) | Q | R |  |  |  |  | P |  |  | I | I | I | V | I | I | I |  |  |  | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-006 | ARO1822-DWG-PP-00-006 | Sections And Details For Cellar Deck P3 Area | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-007 | ARO1822-DWG-PP-00-007 | Sections And Details For Cellar Deck P2 Area | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-008 | ARO1822-DWG-PP-00-008 | Piping Tie-In Details Drawings | Q | R |  |  |  |  | P |  |  | I |  |  | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-009 | ARO1822-DWG-PP-00-009 | Piping Isometric For Cellar Deck P3 Area | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-010 | ARO1822-DWG-PP-00-010 | Piping Isometric For Cellar Deck P2 Area | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-011 | ARO1822-DWG-PP-00-011 | Piping Isometric For Cellar Deck P3 Area (Demolition) | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-DWG-PP-00-012 | ARO1822-DWG-PP-00-012 | Piping Isometric For Cellar Deck P2 Area (Demolition) | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-STD-PP-00-001 | ARO1822-STD-PP-00-001 | Pipe Support Details | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | C |  |  |  | A
AR 06/22 | AR0622-RQ-PP-00-001 | ARO1822-RQ-PP-00-001 | Material Requisition For Piping & Fittings Material | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RQ-PP-00-002 | ARO1822-RQ-PP-00-002 | Material Requisition For Valves | Q | R |  |  |  |  | P | [5 empty] | V | [6 empty] | A
AR 06/22 | AR0622-SPC-EL-00-001 | ARO1822-SPC-EL-00-001 | General Specification For Lv Cables | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-EL-00-001 | ARO1822-DWG-EL-00-001 | Cable Routing Layout | Q | R |  | P | [6 empty] | V | C | [5 empty] | A | I |  |  |  |  | C
AR 06/22 | AR0622-DWG-EL-00-002 | ARO1822-DWG-EL-00-002 | Earthing Layout | Q | R |  | P | [6 empty] | V | C | [5 empty] | A | I |  |  |  |  | C
AR 06/22 | AR0622-DWG-EL-00-003 | ARO1822-DWG-EL-00-003 | Lighting Layout | Q | R |  | P | [6 empty] | V | C | [5 empty] | A | I |  |  |  |  | C
AR 06/22 | AR0622-DWG-EL-00-004 | ARO1822-DWG-EL-00-004 | Single Line Diagram_Tie-In For Electrical Motors | Q | R |  | P | [6 empty] | V | I | [5 empty] | A | I |  |  |  |  | C
AR 06/22 | AR0622-DWG-EL-00-005 | ARO1822-DWG-EL-00-005 | Single Line Diagram_Tie-In For Lighting And Sockets | Q | R |  | P | [6 empty] | V | I | [5 empty] | A | I |  |  |  |  | C
AR 06/22 | AR0622-DWG-EL-00-006 | ARO1822-DWG-EL-00-006 | Interconnection Diagram | Q | R |  | P | [6 empty] | V | [6 empty] | A | [5 empty] | C
AR 06/22 | AR0622-DWG-EL-00-007 | ARO1822-DWG-EL-00-007 | Electrical Installation Details | Q | R |  | P | [6 empty] | V | [6 empty] | A | [5 empty] | C
AR 06/22 | AR0622-CLC-EL-00-001 | ARO1822-CLC-EL-00-001 | Lv Cable Sizing Calculation | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-CLC-EL-00-002 | ARO1822-CLC-EL-00-002 | Lighting Calculation | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-EL-00-001 | ARO1822-LIS-EL-00-001 | Electrical Load List | Q | R |  | P | [5 empty] | I | V | [6 empty] | A
AR 06/22 | AR0622-LIS-EL-00-002 | ARO1822-LIS-EL-00-002 | Electrical Cable List | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-EL-00-003 | ARO1822-LIS-EL-00-003 | Electrical Bulk Of Materials | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RQ-EL-00-001 | ARO1822-RQ-EL-00-001 | Material Requisition For Electrical Cables | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RQ-EL-00-002 | ARO1822-RQ-EL-00-002 | Material Requisition For Bulk Materials | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RQ-EL-00-003 | ARO1822-RQ-EL-00-003 | Material Requisition For Mcc Tie-In Upgrade | Q | R |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-SPC-IN-00-001 | ARO1822-SPC-IN-00-001 | Specification For Plc | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-SPC-IN-00-002 | ARO1822-SPC-IN-00-002 | General Instrument Specification | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-SPC-IN-00-003 | ARO1822-SPC-IN-00-003 | Specification For Control And Sdv Valves | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DSH-IN-00-001 | ARO1822-DSH-IN-00-001 | Instruments Cables Datasheets | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DSH-IN-00-002 | ARO1822-DSH-IN-00-002 | F&G Datasheets (To Be Confirmed) | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-001 | ARO1822-DWG-IN-00-001 | Instrument Cable Routing Layouts | Q | R |  |  | P | [6 empty] | V | C | C |  |  |  |  | A |  | I |  | I | C
AR 06/22 | AR0622-RQ-IN-00-001 | ARO1822-RQ-IN-00-001 | Plc Requisition | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-RQ-IN-00-002 | ARO1822-RQ-IN-00-002 | Instruments Cables Requisitions | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DSH-IN-00-003 | ARO1822-DSH-IN-00-003 | Export Pumps Pressure Instruments Datasheets | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DSH-IN-00-004 | ARO1822-DSH-IN-00-004 | Export Pumps Temperature Instruments Datasheet | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DSH-IN-00-005 | ARO1822-DSH-IN-00-005 | Export Pumps Valves Datasheets | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-001 | ARO1822-LIS-IN-00-001 | Booster And Expedition Pumps Instruments Index | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-002 | ARO1822-LIS-IN-00-002 | Booster And Expedition Pumps I/O Lists | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-003 | ARO1822-LIS-IN-00-003 | Booster And Expedition Pumps Instrument Cable Schedule | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-004 | ARO1822-LIS-IN-00-004 | Booster And Expedition Pumps Instrument & F&G Bulk Material | Q | R |  |  | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-002 | ARO1822-DWG-IN-00-002 | Booster And Expedition Pumps Instrument Loop Diagrams | Q | R |  |  | P | [6 empty] | V | [6 empty] | A |  |  |  |  | C
AR 06/22 | AR0622-DWG-IN-00-003 | ARO1822-DWG-IN-00-003 | Booster And Expedition Pumps Instrment Hook-Up And Installation Diagrams | Q | R |  |  | P | [6 empty] | V | [6 empty] | A |  |  |  |  | C
AR 06/22 | AR0622-DWG-IN-00-004 | ARO1822-DWG-IN-00-004 | Booster And Expedition Pumps Instrument Interconnection Diagrams | Q | R |  |  | P | [6 empty] | V | [6 empty] | A |  |  |  |  | C
AR 06/22 | AR0622-LIS-IN-00-005 | ARO1822-LIS-IN-00-005 | Hydrocyclone Instruments Index | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-006 | ARO1822-LIS-IN-00-006 | Hydrocyclone I/O Lists | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-007 | ARO1822-LIS-IN-00-007 | Hydrocyclone Instrument Cable Schedule | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-LIS-IN-00-008 | ARO1822-LIS-IN-00-008 | Hydrocyclone Instrument & F&G Bulk Material | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-005 | ARO1822-DWG-IN-00-005 | Hydrocyclone Instrument Loop Diagrams | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-006 | ARO1822-DWG-IN-00-006 | Hydrocyclone Instrment Hook-Up And Installation Diagrams | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-007 | ARO1822-DWG-IN-00-007 | Hydrocyclone Cable Routing Layouts | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-IN-00-008 | ARO1822-DWG-IN-00-008 | Hydrocyclone Instrument Interconnection Diagrams | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-SF-00-001 | ARO1822-DWG-SF-00-001 | Hazardous Area Classification (Update) | Q | R | [6 empty] | P | I | I | I | I | I | I | V | [6 empty] | A | C
AR 06/22 | AR0622-DWG-SF-00-002 | ARO1822-DWG-SF-00-002 | F&G Detectors Location Plan (To Be Confirmed) | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A | C
AR 06/22 | AR0622-DWG-SF-00-003 | ARO1822-DWG-SF-00-003 | Escape Route And Safety Signs Layout | Q | R | [6 empty] | P | [6 empty] | V | [6 empty] | A | C
AR 06/22 | AR0622-CLC-CV-00-001 | ARO1822-CLC-CV-00-001 | Steel Structues Modification Calculation Note | Q | R |  |  |  | P | [7 empty] | V | [6 empty] | A
AR 06/22 | AR0622-DWG-CV-00-001 | ARO1822-DWG-CV-00-001 | Steel Structues Modification Dwg | Q | R |  |  |  | P | [7 empty] | V | [6 empty] | A |  |  | C