## ControleQualiteProjet
Reference | CodeDocument | CodeDocumentClient | Designation | RQEP | DPCPE | DesignCoord | PC | EL | INS | MEPP | CV | SF | ISPC | ISELPRJS | ISINSPRJS | ISMEPPPRJS | ISCVPRJS | ISSFPRJS | PSLPC | PSLEL | PSLIN | PSLMEPP | PSLCV | PSLSF | CLIENT | Observation | CS | FG | TL | ISCSPRJS | ISFGPRJS | ISTL | PSLPC | PSLFG | PSLCS | PSLTL | ISPRPRJS | PSLPR | PR
AR19/14 | R1914-RPT-GE-00-001 | 123-C01R-G80-22RA-GA-001 | Design Basis Report | Q | R |  |  | C | C | C | C | C | [5 empty] | C | [5 empty] | C | A | [11 empty] | V |  | P
AR19/14 | R1914-CLC-ME-00-001 | 123-C01R-G65-22RA-SE-001 | TIE tanks calculation note | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-ME-00-001 | 123-C01R-G65-22RA-SE-002 | TIE tanks specification | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-003 | 123-350-22RA-SE-001 | TIE tanks arrangement | Q | R | C |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-CV-00-001 | 123-350-22RA-SE-001 | TIE-1 Storage Tank foundation plan, sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-002 | 123-350-22RA-SE-002 | TIE-2 Storage Tank foundation plan, sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-SPC-PC-00-001 | 123-C01R-G65-22RA-EA-001 | Cathodic protection specification | Q | R | [19 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-CLC-PC-00-001 | 123-C01R-G65-22RA-EA-002 | Cathodic Protection Calculation for External Tank Bottom | Q | R | [11 empty] | I | [7 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-CLC-PC-00-002 | 123-C01R-G65-22RA-EA-003 | Cathodic Protection Calculation for Tank Internals | Q | R | [19 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-DWG-PC-00-001 | 123-410-22RA-EE-200 | CATHODIC PROTECTION SYSTEM LAYOUT FOR TANK | Q | R | C | [18 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-DWG-PC-00-002 | 123-410-22RA-EE-201 | Suspended Anodes Installation Details for Tank Internals | Q | R | C | [18 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-DWG-PC-00-003 | 123-410-22RA-EE-202 | Grid Anode Installation Details for External Tank Bottom | Q | R | C | [10 empty] | C | [7 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-DWG-PC-00-004 | 123-410-22RA-EE-203 | Wiring Schematic for Cathodic Protection System for External Tank Bottom | Q | R | C | [10 empty] | C | [7 empty] | A | [7 empty] | A |  |  |  |  | V
AR19/14 | R1914-SPC-ME-00-002 | 123-C01R-G65-22RA-PE-001 | Specification Centrifugal pumps | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-003 | 123-C01R-G65-22RA-PE-002 | Specification Subumersibbe Centrifugal pumps | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-004 | 123-C01R-G65-22RA-PE-003 | Specification Sampling equipment | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-005 | 123-C01R-G65-22RA-PE-005 | Specification isolating gates | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-006 | 123-C01R-G65-22RA-PE-006 | Specification jib cranes and lifting chain | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-007 | 123-C01R-G65-22RA-PE-007 | Specification basket screens | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-008 | 123-C01R-G65-22RA-PE-008 | Specification mechanical screens | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-009 | 123-C01R-G65-22RA-PE-009 | Specification manual bar screens | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-010 | 123-C01R-G65-22RA-PE-010 | Specification odor control system | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-011 | 123-C01R-G65-22RA-PE-011 | Specification grit classifier | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-012 | 123-C01R-G65-22RA-PE-012 | Specification clarifiers | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-013 | 123-C01R-G65-22RA-PE-013 | Specification chemical injection skid systems | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-014 | 123-C01R-G65-22RA-PE-014 | Specification Disc filters | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-015 | 123-C01R-G65-22RA-PE-015 | Specification chlorine desinfection | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-016 | 123-C01R-G65-22RA-PE-016 | Specification polymer preparation skid | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-017 | 123-C01R-G65-22RA-PE-017 | Specification belt press | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-018 | 123-C01R-G65-22RA-PE-018 | Specification polymer metering pumps | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-019 | 123-C01R-G65-22RA-PE-019 | Specification air compressor | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-020 | 123-C01R-G65-22RA-PE-020 | Specification Diesel generator tank | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-021 | 123-C01R-G65-22RA-PE-021 | Specification Mixers | Q | R |  |  |  | I | P |  |  |  | C |  | V | [5 empty] | A |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-ME-00-022 | 123-C01R-G65-22RA-PE-022 | Piping specification | Q | R |  |  |  | I | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-ME-00-023 | 123-C01R-G65-22RA-PE-023 | Pipng class specification | Q | R |  |  |  | I | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-ME-00-024 | 123-C01R-G65-22RA-PE-024 | Valves specification | Q | R |  |  |  | I | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-ME-00-025 | 123-C01R-G65-22RA-PE-025 | Corrosion Protection and material selection Report | Q | R |  |  | I | I | P | I | I |  |  |  | V | [5 empty] | A |  |  | A |  | I | I | I | [9 empty] | I
AR19/14 | R1914-CLC-PR-00-001 | 123-C01R-G65-22RA-PE-035 | Process calculation note | Q | R | [19 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-CLC-PR-00-002 | 123-C01R-G65-22RA-PE-036 | Utilities sizing calculation notes | Q | R |  |  |  | I | [15 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-CLC-PR-00-003 | 123-C01R-G65-22RA-PE-037 | Line Sizing Report | Q | R |  |  |  | I | [15 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-CLC-PR-00-004 | 123-C01R-G65-22RA-PE-038 | Hydraulic Design Calculation Repport | Q | R | [19 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-LIS-PR-00-001 | 123-C01R-G65-22RA-PE-039 | Process and utilities Line List | Q | R |  |  |  | I | I | [14 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-LIS-PR-00-002 | 123-C01R-G65-22RA-PE-040 | Process and utilities Equipement list | Q | R |  |  | I | I | I |  | I | [12 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-LIS-PR-00-003 | 123-C01R-G65-22RA-PE-041 | Utility consumption tables | Q | R |  |  |  |  | I | [14 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-001 | 123-350-22RA-PE-001 | PROCESS LEGENDS 1 | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-002 | 123-350-22RA-PE-002 | PROCESS LEGENDS 2 | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-003 | 123-350-22RA-PE-003 | PROCESS FLOW DIAGRAM + MATIRIAL BALANCE - LIQUID STREAM I | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-004 | 123-350-22RA-PE-004 | PROCESS FLOW DIAGRAM + MATIRIAL BALANCE - LIQUID STREAM II | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-005 | 123-350-22RA-PE-005 | PROCESS FLOW DIAGRAM + MATIRIAL BALANCE- SOLIDS STREAM I | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-006 | 123-350-22RA-PE-006 | PROCESS FLOW DIAGRAM - + MATIRIAL BALANCESOLIDS STREAM II | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-007 | 123-350-22RA-PE-007 | PROCESS FLOW DIAGRAM - SULFIDE PRECIPITANT STORAGE AND FEED SYSTEM + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-008 | 123-350-22RA-PE-008 | PROCESS FLOW DIAGRAM - POLYMER FEED SYSTEM FOR PRIMARY TREATMENT + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-009 | 123-350-22RA-PE-009 | PROCESS FLOW DIAGRAM - POLYMER FEED SYSTEM FOR SECONDARY TREATMENT + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-010 | 123-350-22RA-PE-010 | PROCESS FLOW DIAGRAM - HYDRATED LIME STORAGE AND FEED SYSTEM + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-011 | 123-350-22RA-PE-011 | PROCESS FLOW DIAGRAM - CARBON DIOXIDE STORAGE AND FEED SYSTEM + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-012 | 123-350-22RA-PE-012 | PROCESS FLOW DIAGRAM - ALUM STORAGE AND FEED SYSTEM + MATIRIAL BALANCE | Q | R | C |  | I | I | I | I | [13 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-013 | 123-350-22RA-PE-013 | PROCESS HYDRAULIC GRADE LINE | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-014 | 123-350-22RA-PE-014 | Istrumentation LEGEND, SYMBOLS AND ABREVIATION I | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-015 | 123-350-22RA-PE-015 | Istrumentation LEGEND, SYMBOLS AND ABREVIATION II | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-016 | 123-350-22RA-PE-016 | Istrumentation P&ID - IFLUENT PUMPING | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-017 | 123-350-22RA-PE-017 | Istrumentation P&ID - PRELIMINARY TRETMENT SCREEN & DEGRIT | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-018 | 123-350-22RA-PE-018 | Istrumentation P&ID - PRELIMINARY TRETMENT EQUALIZATION AND INTERMEDIATE PUMPS | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-019 | 123-350-22RA-PE-019 | Istrumentation P&ID - PRIMARY TREATMENT PRIMARY CLARIFIERS 1 AND 2 | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-020 | 123-350-22RA-PE-020 | Istrumentation P&ID - PRIMARY TREATMENT PRIMARY CLARIFIERS 3 AND 4 | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-021 | 123-350-22RA-PE-021 | Istrumentation P&ID - SECONDARY TREATMENT SECONDARY MIXING TANKS | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-022 | 123-350-22RA-PE-022 | Istrumentation P&ID - SECONDARY TREATMENT SECONDARY CLARIFIERS 1 AND 2 | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-023 | 123-350-22RA-PE-023 | Istrumentation P&ID - SECONDARY TREATMENT SECONDARY CLARIFIERS 3 AND 4 | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-024 | 123-350-22RA-PE-024 | Istrumentation P&ID - FILTRATION | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-025 | 123-350-22RA-PE-025 | Istrumentation P&ID - CHLORINE DISINFECTION | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-026 | 123-350-22RA-PE-026 | Istrumentation P&ID - EFFLUENT STORAGE AND PUMPING STATION | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-027 | 123-350-22RA-PE-027 | Istrumentation P&ID - DEWATERING SLUDGE TRANSFER STATION | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-028 | 123-350-22RA-PE-028 | Istrumentation P&ID - DEWATERING | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-029 | 123-350-22RA-PE-029 | Istrumentation P&ID - EMERGENCY STORAGE LAGOON AND DRAINAGE PUMPING STATION | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-030 | 123-350-22RA-PE-030 | Istrumentation P&ID - SULFIDE PRECIPITANT FEED SYSTEM | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-031 | 123-350-22RA-PE-031 | Istrumentation P&ID - PRIMARY TREATMENT POLYMER FEED SYSTEM | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-032 | 123-350-22RA-PE-032 | Istrumentation P&ID - SECONDARY TREATMENT POLYMER FEED SYSTEM | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-033 | 123-350-22RA-PE-033 | Istrumentation P&ID - LIME FEED SYSTEM I | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-034 | 123-350-22RA-PE-034 | Istrumentation P&ID - LIME FEED SYSTEM II | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-035 | 123-350-22RA-PE-035 | Istrumentation P&ID - CARBON DIOXIDE FEED SYSTEM I | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-036 | 123-350-22RA-PE-036 | Istrumentation P&ID - CARBON DIOXIDE FEED SYSTEM II | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-037 | 123-350-22RA-PE-037 | Istrumentation P&ID - CARBON DIOXIDE FEED SYSTEM III | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-038 | 123-350-22RA-PE-038 | Istrumentation P&ID - ALUM FEED SYSTEM | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-039 | 123-350-22RA-PE-039 | Istrumentation P&ID - PRIMARY TREATMENT POLYMER FEED SYSTEM FOR DEWATERING | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-040 | 123-350-22RA-PE-040 | Utilities P&ID | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-041 | 123-350-22RA-PE-041 | Diesel Genrator P&ID | Q | R | C |  | I |  |  | I |  |  |  | C | C | [8 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-PR-00-042 | 123-350-22RA-PE-042 | TYPICAL SEQUENCES | Q | R | C |  | I | [16 empty] | A | [11 empty] | V |  | P
AR19/14 | R1914-DWG-ME-00-004 | 123-530-22RA-PE-050 | CONTRACT AREA LOCATION PLAN | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-005 | 123-530-22RA-PE-051 | GENERAL ARRANGEMENT AND AREA LIMITATIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-006 | 123-530-22RA-PE-052 | Process interconection drawing | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-007 | 123-530-22RA-PE-053 | UTILITY COORDINATION PLAN | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-008 | 123-530-22RA-PE-054 | INFLUENT PUMPING,PRE-TREATMENT GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-009 | 123-530-22RA-PE-055 | INFLUENT PUMPING AND PRELIMINARY TREATMENT SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-010 | 123-530-22RA-PE-056 | PRIMARY CLARIFIERS GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-011 | 123-530-22RA-PE-057 | SECONDARY MIXING TANKS & SECONDARY CLARIFIERS GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-012 | 123-530-22RA-PE-058 | PRIMARY AND SECONDARY CLARIFIERS AND SECONDARY MIXING TANKS SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-013 | 123-530-22RA-PE-059 | SCREENS AND GRIT REMOVAL PLANS AND SECTIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-014 | 123-530-22RA-PE-060 | MIXING TANK, PRIMARY SLUDGE PUMP STATION ,SECONDARY SLUDGE PUMP STATION PLANS & SECTIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-015 | 123-530-22RA-PE-061 | CHEMICAL BUILDING GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-016 | 123-530-22RA-PE-062 | CHEMICAL BUILDING SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-017 | 123-530-22RA-PE-063 | DISK FILTERS & CHLORINE CONTACT TANKS GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-018 | 123-530-22RA-PE-064 | TERTIARY TREATMENT SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-019 | 123-530-22RA-PE-065 | TIE PUMPING AND STORAGE GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-020 | 123-530-22RA-PE-066 | SLUDGE STORAGE AND DEWATERING GENERAL ARRANGEMENT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-021 | 123-530-22RA-PE-067 | SLUDGE MANAGEMENT SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-022 | 123-530-22RA-PE-068 | EQUALIZATION BASIN GENERAL ARRANGEMENT SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-023 | 123-530-22RA-PE-069 | EMERGENCY LAGOON PUMP STATION GENERAL ARRANGEMENT AND SECTIONS AND DETAILS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-024 | 123-530-22RA-PE-070 | CHLORINE CONTACT TANK, TRANSFER PUMP STATION PLANS & SECTIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-025 | 123-530-22RA-PE-071 | FILTERS & BACWASH RETURN PUMP STATION PLANS & SECTIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-026 | 123-530-22RA-PE-072 | EMERGENCY LAGOON PUMP STATION, PRIMARY PLAN ,SCUM PUMP STATION& TIE/TIE PUMP.STAT.PLANS & SECTIONS | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-ME-00-026 | 123-C01R-G65-22RA-MA-001 | HVAC system Specification | Q | R |  |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-CLC-ME-00-002 | 123-C01R-G65-22RA-MA-002 | HVAC calculation note | Q | R |  |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-CLC-ME-00-003 | 123-C01R-G65-22RA-MA-003 | CHEMICAL BUILDING plumbing calculation note | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-CLC-ME-00-004 | 123-C01R-G65-22RA-MA-004 | SUBSTATION BUILDING plumbing calculation note | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-CLC-ME-00-005 | 123-C01R-G65-22RA-MA-005 | PLUMBING CALCULATION NOTES - ANNEXES | Q | R |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-SPC-FG-00-001 | 123-C01R-G65-22RA-MA-006 | FIRE SUPPRESSION SYSTEM SPECIFICATION | Q | R | [19 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-LIS-FG-00-001 | 123-C01R-G65-22RA-MA-007 | Automatic Extinguishing system Cause &Effect Diagram | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DSH-FG-00-001 | 123-C01R-G65-22RA-MA-008 | Automatic Extinguishing Equipment datasheet | Q | R | [19 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-CLC-SF-00-006 | 123-C01R-G65-22RA-MA-009 | FIRE FIGHTING REQUIREMENTS CALCULATION | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-SPC-SF-00-001 | 123-C01R-G65-22RA-MA-010 | FIRE FIGHTING EQUIPMENTS SPECIFICATION | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-SPC-SF-00-002 | 123-C01R-G65-22RA-MA-011 | FIRE FIGHTING SKID SPECIFICATION | Q | R | [6 empty] | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-FG-00-001 | 123-750-22RA-ME-001 | Automatic Extinguishing system Location | Q | R | C |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-FG-00-002 | 123-750-22RA-ME-002 | Automatic Extinguishing system Riser diagram | Q | R | C | [18 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-SF-00-001 | 123-750-22RA-ME-003 | Fire water pumping station - P&ID | Q | R | C |  | I | C | C |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-SF-00-002 | 123-750-22RA-ME-004 | Fire water network - P&ID | Q | R | C |  | I | C | C |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-SF-00-003 | 123-750-22RA-ME-005 | Fire fighting system general arrangement | Q | R | C |  | I |  |  |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-ME-00-033 | 123-750-22RA-ME-006 | PLUMBING AND HVAC LEGEND | Q | R | C |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-027 | 123-750-22RA-ME-007 | CHEMICAL BUILDING HVAC SYSTEM LAYOUT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-028 | 123-750-22RA-ME-008 | CHEMICAL BUILDING PLUMBING AND SANITARY SYSTEM LAYOUT | Q | R | C |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-029 | 123-750-22RA-ME-009 | ELECTRICAL ROOM HVAC SYSTEM LAYOUT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-030 | 123-750-22RA-ME-010 | SUBSTATION BUILDING HVAC SYSTEM LAYOUT | Q | R | C |  | I |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-031 | 123-750-22RA-ME-011 | SUBSTATION BUILDING PLUMBING AND SANITARY SYSTEM LAYOUT | Q | R | C |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-DWG-ME-00-032 | 123-750-22RA-ME-012 | Plumbing standard details | Q | R | C |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  | A
AR19/14 | R1914-RPT-SF-00-001 | 123-C01R-G65-22RA-AE-001 | FIRE & LIFE SAFETY PLAN REPORT | Q | R | C | [5 empty] | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-CV-00-061 | 123-741-22RA-AE-001 | General notes symbols and abbreviations | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-062 | 123-741-22RA-AE-002 | Site Development Plan | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-063 | 123-741-22RA-AE-003 | General Signage and Interior Graphic Types | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | Chemical Building
AR19/14 | R1914-DWG-CV-00-071 | 123-741-22RA-AE-101 | Chemical Building - Ground floor, roof plan & schedules | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-072 | 123-741-22RA-AE-102 | Chemical Building - Elevations, sections and details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-073 | 123-741-22RA-AE-103 | Chemical Building - ABLUTION/TOILET details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-074 | 123-741-22RA-AE-104 | Chemical Building -Sections and miscellaneous details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-075 | 123-741-22RA-AE-105 | Chemical Building - ceiling drawing | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-076 | 123-741-22RA-AE-106 | Chemical Building -Doors & Windows details SHEET 1/2 | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-077 | 123-741-22RA-AE-107 | Chemical Building -Doors & Windows details SHEET 2/2 | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-SF-00-004 | 123-741-22RA-AE-108 | Life and safety plan for chemical building | Q | R | C |  | I |  |  |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-CV-00-090 | 123-741-22RA-AE301 | Electrical Building - Floor plan, elevations, sections and schedules | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-091 | 123-741-22RA-AE302 | Electrical Building -Sections and miscellaneous details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-092 | 123-741-22RA-AE303 | Electrical Building - ceiling drawing | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-093 | 123-741-22RA-AE304 | Electrical Building -Doors & Windows details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-SF-00-005 | 123-741-22RA-AE305 | Life and safety plan for electrical room | Q | R | C |  | I |  |  |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-CV-00-101 | 123-741-22RA-AE-401 | Sub-station building - Floor plan, elevations, sections and schedules | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-102 | 123-741-22RA-AE-402 | Sub-station building -Sections and miscellaneous details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-103 | 123-741-22RA-AE-403 | Sub-station building - ceiling drawing | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-104 | 123-741-22RA-AE-404 | Sub-station building -Doors & Windows details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-SF-00-006 | 123-741-22RA-AE-405 | Life and safety plan for substation and generator | Q | R | C |  | I |  |  |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-DWG-CV-00-111 | 123-741-22RA-AE-501 | SEC building - Floor plan, elevations, sections and schedules | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-112 | 123-741-22RA-AE-502 | SEC building -Sections and miscellaneous details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-113 | 123-741-22RA-AE-503 | SEC building - ceiling drawing | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-114 | 123-741-22RA-AE-504 | SEC building -Doors & Windows details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-SF-00-007 | 123-741-22RA-AE-505 | Life and safety plan for SEC Building | Q | R | C |  | I |  |  |  | P | [5 empty] | V | [5 empty] | A | A
AR19/14 | R1914-CLC-CV-00-001 | 123-C01R-CALC-22RA-CA-001 | Sewage network calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-002 | 123-C01R-CALC-22RA-CA-002 | Runoff calculation report | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-003 | 123-000-22RA-CE-001 | General Notes Civil | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-004 | 123-000-22RA-CE-002 | General Symbols Civils and Structural | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-005 | 123-040-22RA-CE-003 | Civil work (KEY PLAN) | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-006 | 123-040-22RA-CE-004 | Area-1- Civil Work Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-007 | 123-040-22RA-CE-005 | Area-2- Civil Work Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-008 | 123-040-22RA-CE-006 | Area-3- Civil Work Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-009 | 123-040-22RA-CE-007 | Area-4- Civil Work Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-010 | 123-040-22RA-CE-008 | Grading and surface drainage layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-011 | 123-040-22RA-CE-009 | Site Grading Profiles | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-012 | 123-040-22RA-CE-010 | Pavement Site Plan | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-013 | 123-040-22RA-CE-011 | Building Levels | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-014 | 123-040-22RA-CE-012 | Fencing Layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-015 | 123-040-22RA-CE-013 | Fence and Gate Details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-016 | 123-040-22RA-CE-014 | Roads General layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-017 | 123-040-22RA-CE-015 | Road guardrails and delineator details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-018 | 123-040-22RA-CE-016 | Road longitudinal profiles | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-019 | 123-040-22RA-CE-017 | Roads grading plan | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-020 | 123-040-22RA-CE-018 | Roads Cross Sections | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-021 | 123-040-22RA-CE-019 | Roads Marking and signs layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-022 | 123-040-22RA-CE-020 | Road signs details SHEET 1/2 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-023 | 123-040-22RA-CE-021 | Road signs details SHEET 2/2 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-024 | 123-040-22RA-CE-022 | Emergency lagoon Plan Section & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-025 | 123-040-22RA-CE-023 | Equalisation basin Plan sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-026 | 123-040-22RA-CE-024 | Storm Wter Infiltration Basin sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-051 | 123-741-22RA-CE-051 | Sewage network | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-052 | 123-741-22RA-CE-052 | Sewage longitudinal profiles | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-053 | 123-741-22RA-CE-053 | Fire water valve chambers details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-054 | 123-741-22RA-CE-054 | Manholes and connections details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-055 | 123-741-22RA-CE-055 | Telecommunication joint box and manholes details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-056 | 123-741-22RA-CE-056 | Electrical Manholes and channels details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-057 | 123-741-22RA-CE-057 | Pipes installation miscellaneous details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-SPC-CV-00-001 | 123-C01R-G65-22RA-CA-001 | LIGHTWEIGHT CONCRETE SPECIFICATION | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-003 | 123-C01R-CALC-22RA-CA-003 | Influent PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-004 | 123-C01R-CALC-22RA-CA-004 | Ifluent PS Steel Structure- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-005 | 123-C01R-CALC-22RA-CA-005 | Intermediate PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-006 | 123-C01R-CALC-22RA-CA-006 | Diversion Chamber- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-007 | 123-C01R-CALC-22RA-CA-007 | Screen and Grit Removal- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-008 | 123-C01R-CALC-22RA-CA-008 | Primary Clarifier- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-009 | 123-C01R-CALC-22RA-CA-009 | Primary Flow Distribution Chamber- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-010 | 123-C01R-CALC-22RA-CA-010 | Mixing Tank- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-011 | 123-C01R-CALC-22RA-CA-011 | Primary Sludge PS- calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-012 | 123-C01R-CALC-22RA-CA-012 | Primary Sludge Steel Structure- calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-013 | 123-C01R-CALC-22RA-CA-013 | Secondary Sludge PS- calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-014 | 123-C01R-CALC-22RA-CA-014 | Secondary Sludge Steel Structure- calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-015 | 123-C01R-CALC-22RA-CA-015 | Secondary Clarifier- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-016 | 123-C01R-CALC-22RA-CA-016 | Secondary Flow Distribution Chamber- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-017 | 123-C01R-CALC-22RA-CA-017 | Chlorine Contact Tank- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-018 | 123-C01R-CALC-22RA-CA-018 | Filtrate Return PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-019 | 123-C01R-CALC-22RA-CA-019 | Primary Scum PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-020 | 123-C01R-CALC-22RA-CA-020 | TIE/TIE PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-021 | 123-C01R-CALC-22RA-CA-021 | TIE/TIE Steel Structure- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-022 | 123-C01R-CALC-22RA-CA-022 | Backwash Return PS- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-023 | 123-C01R-CALC-22RA-CA-023 | Sludge dewatering Steel Structure- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-024 | 123-C01R-CALC-22RA-CA-024 | Sludge dewatering Tank- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-025 | 123-C01R-CALC-22RA-CA-025 | Concrete Pad for Storage and Feed Facility Tank- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-026 | 123-C01R-CALC-22RA-CA-026 | Chemical building - Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-027 | 123-C01R-CALC-22RA-CA-027 | Chemical building Steel Structure - Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-028 | 123-C01R-CALC-22RA-CA-028 | Substation building - Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-029 | 123-C01R-CALC-22RA-CA-029 | Electrical building - Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-030 | 123-C01R-CALC-22RA-CA-030 | SEC Building- Calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-CLC-CV-00-031 | 123-C01R-CALC-22RA-CA-031 | Parking shade calculation note | Q | R | [5 empty] | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-120 | 123-000-22RA-SE-001 | Structural general notes Sheet 1 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-121 | 123-000-22RA-SE-002 | Structural general notes Sheet 2 | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-125 | 123-760-22RA-SE-005 | Masonry typical details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-126 | 123-760-22RA-SE-006 | External Water proofing - Typical details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-127 | 123-760-22RA-SE-007 | Typical slab on grade details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-128 | 123-760-22RA-SE-008 | Reinforcing bars arrangement details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-129 | 123-760-22RA-SE-009 | FRP ladder and handrail typical details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-131 | 123-760-22RA-SE-021 | Parking shades- framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-132 | 123-760-22RA-SE-022 | Parking shades- foundation drawing | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-136 | 123-760-22RA-SE-023 | Lighting pole foundation | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-151 | 123-760-22RA-SE-051 | Influent pumping station - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-152 | 123-760-22RA-SE-052 | Influent pumping station - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-153 | 123-760-22RA-SE-055 | Inffluent pumping station - Access stairs | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-154 | 123-760-22RA-SE-056 | Influent pumping station - Steel structure layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-155 | 123-760-22RA-SE-057 | Influent pumping station - Steel structure details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-156 | 123-760-22RA-SE-061 | Intermediate Pumping Station - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-157 | 123-760-22RA-SE-062 | Intermediate Pumping Station - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-158 | 123-760-22RA-SE-071 | Diversion Chamber - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-159 | 123-760-22RA-SE-072 | Diversion Chamber - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-160 | 123-760-22RA-SE-081 | Screen and Grit Removal - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-161 | 123-760-22RA-SE-082 | Screen and Grit Removal - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-162 | 123-760-22RA-SE-091 | Primary clarifier - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-163 | 123-760-22RA-SE-092 | Primary clarifier - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-164 | 123-760-22RA-SE-101 | Primary flow distribution chamber and channel - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-165 | 123-760-22RA-SE-102 | Primary flow distribution chamber and channel - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-166 | 123-760-22RA-SE-111 | Mixing tank - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-167 | 123-760-22RA-SE-112 | Mixing tank - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-168 | 123-760-22RA-SE-121 | Primary sludge Pumping Station - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-169 | 123-760-22RA-SE-122 | Primary sludge Pumping Station - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-170 | 123-760-22RA-SE-125 | Primary sludge Pumping Station - Access stairs | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-171 | 123-760-22RA-SE-126 | Primary sludge Pumping Station - Steel structure layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-172 | 123-760-22RA-SE-127 | Primary sludge Pumping Station - Steel structure details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-173 | 123-760-22RA-SE-131 | Secondary sludge Pumping Station - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-174 | 123-760-22RA-SE-132 | Secondary sludge Pumping Station - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-175 | 123-760-22RA-SE-135 | Secondary sludge Pumping Station - Access stairs | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-176 | 123-760-22RA-SE-136 | Secondary sludge Pumping Station - Steel structure layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-177 | 123-760-22RA-SE-137 | Secondary sludge Pumping Station - Steel structure details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-178 | 123-760-22RA-SE-141 | Secondary clarifier - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-179 | 123-760-22RA-SE-142 | Secondary clarifier - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-180 | 123-760-22RA-SE-151 | Secondary flow distribution chamber and channel - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-181 | 123-760-22RA-SE-152 | Secondary flow distribution chamber and channel - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-182 | 123-760-22RA-SE-161 | Chlorine contact tank & transfer PS - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-183 | 123-760-22RA-SE-162 | Chlorine contact tank & transfer PS - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-184 | 123-760-22RA-SE-171 | Emergency Lagoon PS Framing and Details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-185 | 123-760-22RA-SE-172 | Emergency Lagoon PS Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-186 | 123-760-22RA-SE-181 | Filtrate Return PS Framing and Details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-187 | 123-760-22RA-SE-182 | Filtrate Return PS Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-188 | 123-760-22RA-SE-191 | Primary scum PS foundation plan, sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-189 | 123-760-22RA-SE-192 | Primary scum PS reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-190 | 123-760-22RA-SE-201 | TIE/TSE PS foundation plan, sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-191 | 123-760-22RA-SE-202 | TIE/TSE PS Steel Structure Shelter | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-192 | 123-760-22RA-SE-211 | Disk Filters Foundation - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-193 | 123-760-22RA-SE-212 | Disk Filters Foundation - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-194 | 123-760-22RA-SE-221 | Backwash return PS - Framing and details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-195 | 123-760-22RA-SE-222 | Backwash return PS - Reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-196 | 123-760-22RA-SE-231 | Sludge dewatering unit - footing/column/grade beam and framing detail | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-197 | 123-760-22RA-SE-232 | Sludge dewatering unit - framing sections and typical details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-198 | 123-760-22RA-SE-241 | Sludge dewatering unit - Steel structure layout | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-199 | 123-760-22RA-SE-242 | Sludge dewatering unit - Steel structure details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-200 | 123-760-22RA-SE-251 | Sludge Holding tank foundation plan, sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-201 | 123-760-22RA-SE-252 | Sludge Holding tank reinforcement | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-202 | 123-760-22RA-SE-261 | Foundation for Dia 4m Storage and Feed Facility Tank sections & details | Q | R | C |  |  |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-203 | 123-760-22RA-SE-271 | Chemical building - footing/column/grade beam and framing detail | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-204 | 123-760-22RA-SE-272 | Chemical building - roof framing and reinforcement | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-205 | 123-760-22RA-SE-273 | Chemical building - framing sections and typical details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-206 | 123-760-22RA-SE-275 | Chemical Building- Steel Structure Details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-207 | 123-760-22RA-SE-276 | Chemical Building- Steel Structure Details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-208 | 123-760-22RA-SE-281 | Substation building - Foundations ground floor and roof framing and reinforcement | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-209 | 123-760-22RA-SE-282 | Substation building - framing sections and typical details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-210 | 123-760-22RA-SE-291 | Electrical building - Foundations ground floor and roof framing and reinforcement | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-211 | 123-760-22RA-SE-292 | Electrical building - framing sections and typical details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-212 | 123-760-22RA-SE-301 | SEC Building - Framing, reinforcement and details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-DWG-CV-00-213 | 123-760-22RA-SE-311 | Transformer Building - Framing-Reinforcement and Details | Q | R | C |  | I |  |  | P | [5 empty] | V | [5 empty] | A |  | A
AR19/14 | R1914-SPC-TL-00-001 | 123-C01R-G65-22RA-TA-001 | Data Transmission System Specification | Q | R | [19 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-SPC-TL-00-002 | 123-C01R-G65-22RA-TA-002 | Telephone system specification (IP Telephony) | Q | R | [19 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-SPC-TL-00-003 | 123-C01R-G65-22RA-TA-003 | Access Control System Specification | Q | R | [19 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-SPC-TL-00-004 | 123-C01R-G65-22RA-TA-004 | CCTV system specification | Q | R | [19 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-SPC-TL-00-005 | 123-C01R-G65-22RA-TA-005 | Public adress system specification | Q | R | [19 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-001 | 123-211-22RA-TE-001 | Telecom legends and abbreviations | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-002 | 123-211-22RA-TE-002 | Telecommunication site location MAP | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-003 | 123-211-22RA-TE-003 | BUILDING LAYOUT DRAWING | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-004 | 123-211-22RA-TE-004 | Telecom Systems Secondary Duct Bank and Cable Layout | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-005 | 123-211-22RA-TE-005 | Telecommunication hand hole plan | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-006 | 123-211-22RA-TE-006 | Telecommunication hand hole and duct bank sectional details | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-007 | 123-211-22RA-TE-007 | Telecom & fiber optic Intra Building Block Diagram | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-008 | 123-211-22RA-TE-008 | Intra Building Fiber Network Schematic Diagram | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-009 | 123-211-22RA-TE-009 | CCTV BLOCK DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-010 | 123-211-22RA-TE-010 | CCTV SYSTEM SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-011 | 123-211-22RA-TE-011 | CHEMICAL BUILDING CCTV SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-012 | 123-211-22RA-TE-012 | PROCESS AND ELECTRICAL BUILDING CCTV SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-013 | 123-211-22RA-TE-013 | SUBSTATION BUILDING CCTV SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-014 | 123-211-22RA-TE-014 | ACCESS SYSTEM SINGLE LINE RISER LINE DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-015 | 123-211-22RA-TE-015 | CHEMICAL BUILDING ACCESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-016 | 123-211-22RA-TE-016 | PROCESS AND ELECTRICAL BUILDING ACCESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-017 | 123-211-22RA-TE-017 | SUBSTATION BUILDING ACCESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-018 | 123-211-22RA-TE-018 | Telephone, Data SINGLE LINE RISER Diagram | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-019 | 123-211-22RA-TE-019 | CHEMICAL BUILDING TELEPHONE-DATA SYSTEM LAYOUT & SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-020 | 123-211-22RA-TE-020 | PROCESS AND ELECTRICAL BUILDING TELEPHONE-DATA SYSTEM LAYOUT & SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-021 | 123-211-22RA-TE-021 | SUBSTATION BUILDING TELEPHONE-DATA SYSTEM LAYOUT & SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-022 | 123-211-22RA-TE-022 | Public Adress System SINGLE LINE RISER Diagram | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-023 | 123-211-22RA-TE-023 | CHEMICAL BUILDING PUBLIC ADDRESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-024 | 123-211-22RA-TE-024 | PROCESS AND ELECTRICAL BUILDING PUBLIC ADDRESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-025 | 123-211-22RA-TE-025 | SUBSTATION BUILDING PUBLIC ADDRESS SYSTEM LAYOUT AND SINGLE LINE RISER DIAGRAM | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-026 | 123-211-22RA-TE-026 | Telecom Systems Building Layout | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-027 | 123-211-22RA-TE-027 | Telecom equipments room LAYOUT | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-028 | 123-211-22RA-TE-028 | TELECOM ROOM ARRANGEMENT LAYOUT" | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-029 | 123-211-22RA-TE-029 | CAMERAS MOUNTING DETAILS | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-030 | 123-211-22RA-TE-030 | Speaker and microphone outlet mounting details | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-031 | 123-211-22RA-TE-031 | RTU typical fiber optic installation details | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-032 | 123-211-22RA-TE-032 | Telecommunication joint box DETAILS | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-033 | 123-211-22RA-TE-033 | Telecom Cable Schedule | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-TL-00-034 | 123-211-22RA-TE-034 | Typical Duct Bank details | Q | R | C | [18 empty] | A |  |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-CLC-EL-00-001 | 123-C01R-CALC-22RA-EA-001 | CALCULATION LOAD NORMAL OPERATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-002 | 123-C01R-CALC-22RA-EA-002 | CALCULATION LOAD STANDBY OPERATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-005 | 123-C01R-CALC-22RA-EA-003 | 34,5 KV POWER CABLE CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-006 | 123-C01R-CALC-22RA-EA-004 | 13,8 KV POWER CABLE CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-007 | 123-C01R-CALC-22RA-EA-005 | RING POWER CABLE CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-008 | 123-C01R-CALC-22RA-EA-006 | 0,38 KV POWER CABLE CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-012 | 123-C01R-CALC-22RA-EA-007 | DETAILED CALCULATION FOR ELECTRICAL EQUIPEMENT | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-013 | 123-C01R-CALC-22RA-EA-008 | OVERALL CALCULATION OF EARTHING & LIGHTNING PROTECTION SYSTEMS | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-014 | 123-C01R-CALC-22RA-EA-009 | INDOOR LIGHTING SYSTEM CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-015 | 123-C01R-CALC-22RA-EA-010 | OVERALL OUTDOOR LIGHTING SYSTEM CALCULATION | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-017 | 123-C01R-CALC-22RA-EA-011 | POWER FLOW STUDY | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-018 | 123-C01R-CALC-22RA-EA-012 | SHORT CIRCUIT STUDY | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-019 | 123-C01R-CALC-22RA-EA-013 | MOTOR STARTING STUDY | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-020 | 123-C01R-CALC-22RA-EA-014 | COORDINATION STUDY | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-021 | 123-C01R-CALC-22RA-EA-015 | ARC FLASH STUDY | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-022 | 123-C01R-CALC-22RA-EA-016 | RELAY SETTING TABLES | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-CLC-EL-00-023 | 123-C01R-CALC-22RA-EA-017 | Harmonic Analysis | Q | R |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-SPC-FG-00-002 | 123-C01R-G65-22RA-EA-010 | FIRE ALARM SYSTEM REQUIREMENTS | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-SPC-FG-00-003 | 123-C01R-G65-22RA-EA-011 | Fire and Gas Detection System Specification | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-LIS-FG-00-002 | 123-C01R-G65-22RA-EA-012 | F&G Cause & Effect Diagram | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-LIS-FG-00-003 | 123-C01R-G65-22RA-EA-013 | Automatic Extinguishing System cables schedule | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-LIS-FG-00-004 | 123-C01R-G65-22RA-EA-014 | F&G cables schedule | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DSH-FG-00-002 | 123-C01R-G65-22RA-EA-015 | Fire Alarm equipment datasheet | Q | R |  |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-EL-00-032 | 123-410-22RA-EE-001 | ELECTRICAL INDEX OF DRAWING | Q | R | C |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-007 | 123-410-22RA-EE-002 | SYMBOLS & ABBREVIATIONS | Q | R | C |  | P | [5 empty] | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-033 | 123-410-22RA-EE-003 | KEY ONE LINE DIAGRAM & POWER DISTRIBUTION | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-008 | 123-410-22RA-EE-004 | AREA CLASSIFICATION LAYOUT | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-009 | 123-410-22RA-EE-005 | SITE POWER, SIGNAL AND CONTROL DISTRIBUTION | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-010 | 123-410-22RA-EE-006 | EQUIPMENT POWER PLAN I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-011 | 123-410-22RA-EE-007 | EQUIPMENT POWER PLAN II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-012 | 123-410-22RA-EE-008 | OVERALL ELECTRICAL SINGLE LINE DIAGRAM I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-013 | 123-410-22RA-EE-009 | OVERALL ELECTRICAL SINGLE LINE DIAGRAM II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-034 | 123-410-22RA-EE-010 | OVERALL ELECTRICAL SINGLE LINE DIAGRAM III | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-035 | 123-410-22RA-EE-011 | OVERALL ELECTRICAL SINGLE LINE DIAGRAM IV | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-014 | 123-410-22RA-EE-012 | LOW VOLTAGE SINGLE LINE DIAGRAM I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-015 | 123-410-22RA-EE-013 | LOW VOLTAGE SINGLE LINE DIAGRAM II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-016 | 123-410-22RA-EE-014 | LOW VOLTAGE SINGLE LINE DIAGRAM III | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-017 | 123-410-22RA-EE-015 | LOW VOLTAGE SINGLE LINE DIAGRAM IV | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-020 | 123-410-22RA-EE-016 | SINGLE LINE DIAGRAMS OF BUILDING UTILITIES BOARDS (LIGHTING, SOCKETS) | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-021 | 123-410-22RA-EE-017 | SINGLE LINE DIAGRAM OF EXTERNAL LIGHTING SWITSCHBOARDS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-022 | 123-410-22RA-EE-018 | SINGLE LINE DIAGRAM FOR AC/DC UPS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-036 | 123-410-22RA-EE-019 | OVERALL GROUNDING SYSTEMS LAYOUT | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-023 | 123-410-22RA-EE-020 | GROUNDING SYSTEM LAYOUT I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-024 | 123-410-22RA-EE-021 | GROUNDING SYSTEM LAYOUT II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-025 | 123-410-22RA-EE-022 | OVERALL LIGHTNING PROTECTION SYSTEMS LAYOUT | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-037 | 123-410-22RA-EE-023 | LIGHTNING PROTECTION SYSTEMS LAYOUT I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-038 | 123-410-22RA-EE-024 | LIGHTNING PROTECTION SYSTEMS LAYOUT II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-026 | 123-410-22RA-EE-025 | ELECTRICAL LIGHTING LAYOUT I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-027 | 123-410-22RA-EE-026 | ELECTRICAL LIGHTING LAYOUT II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-028 | 123-410-22RA-EE-027 | EXTERNAL LIGHTING LAYOUT | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-039 | 123-410-22RA-EE-028 | SUBSTATION BUILDING LAYOUT & DETAILS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-040 | 123-410-22RA-EE-029 | ELECTRICAL BUILDING LAYOUT & DETAILS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-041 | 123-410-22RA-EE-030 | CHEMICAL BUILDING ELECTRICAL ROOM LAYOUT & DETAILS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-042 | 123-410-22RA-EE-031 | IWTP SWITCHGEAR ROOM LAYOUT & DETAILS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-043 | 123-410-22RA-EE-032 | TYPICAL PADMOUNTED TRANSFORMER INSTALATION LAYOUT & DETAILS I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-044 | 123-410-22RA-EE-033 | TYPICAL PADMOUNTED TRANSFORMER INSTALATION LAYOUT & DETAILS II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-029 | 123-410-22RA-EE-034 | EXTERNAL LIGHTING MISCELLANEOUS DETAILS | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-030 | 123-410-22RA-EE-035 | POWER DISTRIBUTION MISCELLANEOUS DETAILS I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-045 | 123-410-22RA-EE-036 | POWER DISTRIBUTION MISCELLANEOUS DETAILS II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-031 | 123-410-22RA-EE-037 | Cable and conduit shedule | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-046 | 123-410-22RA-EE-038 | MISCELLANEOUS ELECTRICAL DETAILS I | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-047 | 123-410-22RA-EE-039 | MISCELLANEOUS ELECTRICAL DETAILS II | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-048 | 123-410-22RA-EE-040 | MISCELLANEOUS ELECTRICAL DETAILS III | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-EL-00-049 | 123-410-22RA-EE-041 | MISCELLANEOUS ELECTRICAL DETAILS IV | Q | R | C |  | P | I |  |  |  |  | V | [5 empty] | A |  |  |  |  | A
AR19/14 | R1914-DWG-FG-00-003 | 123-410-22RA-EE-100 | F&G system Riser diagram | Q | R | C | [18 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-FG-00-004 | 123-410-22RA-EE-101 | Automatic Extinguishing system cable routing | Q | R | C | [18 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-FG-00-005 | 123-410-22RA-EE-102 | F&G cable routing | Q | R | C | [18 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-FG-00-006 | 123-410-22RA-EE-103 | F&G Location | Q | R | C |  | I | [16 empty] | A |  |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-RPT-IN-00-001 | 123-C01R-G65-22RA-EA-017 | Control philosophy | Q | R |  |  |  | P |  |  |  |  | C | V | [5 empty] | A |  |  |  | A | [11 empty] | C
AR19/14 | R1914-SPC-CS-00-001 | 123-C01R-G65-22RA-EA-018 | SCADA system specification | Q | R |  |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-LIS-IN-00-004 | 123-C01R-G65-22RA-EA-019 | C&E diagram | Q | R |  |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A | [11 empty] | C
AR19/14 | R1914-DSH-IN-00-001 | 123-C01R-G65-22RA-EA-020 | Level Instruments Datasheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-002 | 123-C01R-G65-22RA-EA-021 | Pressure Instruments Datasheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-003 | 123-C01R-G65-22RA-EA-022 | Temperature Instruments Datasheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-004 | 123-C01R-G65-22RA-EA-023 | Flowmeters Datasheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-005 | 123-C01R-G65-22RA-EA-024 | Analyzers Datasheet | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-006 | 123-C01R-G65-22RA-EA-025 | Instrumentation and Fire & Gas cables data sheet" | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DSH-IN-00-007 | 123-C01R-G65-22RA-EA-026 | Technical Data sheet for junction box | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-LIS-IN-00-001 | 123-C01R-G65-22RA-EA-027 | Instrument index | Q | R |  |  |  | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-LIS-CS-00-001 | 123-C01R-G65-22RA-EA-028 | Input/Output List For Control System | Q | R | [8 empty] | C | [10 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-CS-00-001 | 123-410-22RA-EE-038 | swtp and lift station control system architecture diagram | Q | R | C |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-CS-00-002 | 123-410-22RA-EE-051 | office building Control Room Arrangement Layout | Q | R | C |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-CS-00-003 | 123-410-22RA-EE-052 | PLC Room Arrangement Layout | Q | R | C |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-CS-00-004 | 123-410-22RA-EE-053 | SWTP &IWTP SCADA NETWORK | Q | R | C |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-CS-00-005 | 123-410-22RA-EE-054 | Operation1 FIBER OPTIC INTERCONNECTION DIAGRAM | Q | R | C |  | I | [16 empty] | A |  | P |  |  | V |  |  |  | A
AR19/14 | R1914-DWG-IN-00-001 | 123-410-22RA-EE-037 | Instrument cable routing | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-002 | 123-410-22RA-EE-039 | Instrument block diagram | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-003 | 123-410-22RA-EE-040 | Instrument block diagram Load shedding PLC | Q | R | C |  |  | P |  |  |  |  | C | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-004 | 123-410-22RA-EE-041 | INSTRUMENT INTERCONNECTION DIAGRAM | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-005 | 123-410-22RA-EE-042 | Level Instruments mounting and installation details | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-006 | 123-410-22RA-EE-043 | Pressure Instruments mounting and installation details | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-007 | 123-410-22RA-EE-044 | Temperature Instruments mounting and installation details | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-008 | 123-410-22RA-EE-045 | Flowmeters mounting and installation details | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-009 | 123-410-22RA-EE-046 | Analyzers mounting and installation details | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-010 | 123-410-22RA-EE-047 | Junction Box mounting and General Arrangement Drawing | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-011 | 123-410-22RA-EE-048 | Instrument loop diagram | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-012 | 123-410-22RA-EE-049 | PRIMARY TREATMENT JUNCTION BOX WIRING DIAGRAM | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A
AR19/14 | R1914-DWG-IN-00-013 | 123-410-22RA-EE-050 | Instrument cable AND CONDUIT schedule | Q | R | C |  | I | P | [5 empty] | V | [5 empty] | A |  |  |  | A