## DocumentEtude
Reference | CodeDocument | CodeDocumentlient | TitreDocument | Rev | NBHIngenieur | NBHProjeteur | NBHIngenieur | NBHProjeteur | Etat
AR 06/22 | AR0622-RPT-GE-00-001 | ARO1822-RPT-GE-00-001 | Design Basis Memorandum |  | 72 | 0 | 22 | 94
AR 06/22 | AR0622-RPT-GE-00-002 | ARO1822-RPT-GE-00-002 | Site Visit Report |  | 45 | 0 | 7 | 52
AR 06/22 | AR0622-DWG-PR-00-001 | ARO1822-DWG-PR-00-001 | Symbols And Abreviations List |  | 4 | 4 | 1 | 10
AR 06/22 | AR0622-DWG-PR-00-002 | ARO1822-DWG-PR-00-002 | Booster Pumps P&Id |  | 12 | 35 | 5 | 53
AR 06/22 | AR0622-DWG-PR-00-003 | ARO1822-DWG-PR-00-003 | Booster Pumps P&Id (Demolition) |  | 12 | 25 | 5 | 43
AR 06/22 | AR0622-DWG-PR-00-004 | ARO1822-DWG-PR-00-004 | Export Pumps P&Id |  | 12 | 25 | 5 | 43
AR 06/22 | AR0622-DWG-PR-00-005 | ARO1822-DWG-PR-00-005 | Export Pumps P&Id (Demolition) |  | 12 | 25 | 5 | 43
AR 06/22 | AR0622-DWG-PR-00-006 | ARO1822-DWG-PR-00-006 | Hydrocyclones P&Id |  | 12 | 25 | 5 | 43
AR 06/22 | AR0622-DWG-PR-00-007 | ARO1822-DWG-PR-00-007 | Hydrocyclones P&Id (Demolition) |  | 12 | 25 | 5 | 43
AR 06/22 | AR0622-DWG-PR-00-008 | ARO1822-DWG-PR-00-008 | Surge Tank P&Id |  | 8 | 10 | 3 | 23
AR 06/22 | AR0622-DWG-PR-00-009 | ARO1822-DWG-PR-00-009 | Pipeline P&Id |  | 8 | 10 | 3 | 23
AR 06/22 | AR0622-DWG-PR-00-010 | ARO1822-DWG-PR-00-010 | Oily Water P&Id |  | 8 | 10 | 3 | 23
AR 06/22 | AR0622-RPT-PR-00-001 | ARO1822-RPT-PR-00-001 | Line Sizing Report |  | 35 | 0 | 5 | 40
AR 06/22 | AR0622-RPT-PR-00-002 | ARO1822-RPT-PR-00-002 | Utilities Consumption Report (Update) |  | 25 | 0 | 5 | 30
AR 06/22 | AR0622-RPT-PR-00-003 | ARO1822-RPT-PR-00-003 | Operation & Control Philosophy |  | 50 | 0 | 10 | 60
AR 06/22 | AR0622-RPT-PR-00-004 | ARO1822-RPT-PR-00-004 | Hazop Report |  | 8 | 0 | 40 | 48
AR 06/22 | AR0622-RPT-PR-00-005 | ARO1822-RPT-PR-00-005 | Hazop Close Out Report |  | 30 | 0 | 7 | 37
AR 06/22 | AR0622-LIS-PR-00-001 | ARO1822-LIS-PR-00-001 | Process Equipement List |  | 25 | 0 | 4 | 29
AR 06/22 | AR0622-LIS-PR-00-002 | ARO1822-LIS-PR-00-002 | Process Line List (Update) |  | 25 | 0 | 6 | 31
AR 06/22 | AR0622-LIS-PR-00-003 | ARO1822-LIS-PR-00-003 | Tie Ins List |  | 25 | 0 | 6 | 31
AR 06/22 | AR0622-LIS-PR-00-005 | ARO1822-LIS-PR-00-005 | Cause & Effect Diagrams (Update) |  | 34 | 0 | 10 | 44
AR 06/22 | AR0622-RPT-PP-00-001 | ARO1822-RPT-PP-00-001 | Piping Stress Analysis Report For Cellar Deck P3 Area |  | 100 | 0 | 18 | 118
AR 06/22 | AR0622-RPT-PP-00-002 | ARO1822-RPT-PP-00-002 | Piping Stress Analysis Report For Cellar Deck P2 Area |  | 100 | 0 | 18 | 118
AR 06/22 | AR0622-LIS-PP-00-001 | ARO1822-LIS-PP-00-001 | Valves List |  | 25 | 0 | 5 | 30
AR 06/22 | AR0622-LIS-PP-00-002 | ARO1822-LIS-PP-00-002 | Piping & Fittings Mto |  | 0 | 50 | 8 | 68
AR 06/22 | AR0622-LIS-PP-00-003 | ARO1822-LIS-PP-00-003 | Piping Supports List |  | 0 | 30 | 5 | 40
AR 06/22 | AR0622-DWG-PP-00-001 | ARO1822-DWG-PP-00-001 | Equipment Arrangment Plan |  | 20 | 100 | 6 | 156
AR 06/22 | AR0622-DWG-PP-00-002 | ARO1822-DWG-PP-00-002 | Piping Layout Drawing For Cellar Deck P3 Area |  | 20 | 100 | 5 | 155
AR 06/22 | AR0622-DWG-PP-00-003 | ARO1822-DWG-PP-00-003 | Piping Layout Drawing For Cellar Deck P2 Area |  | 20 | 100 | 5 | 155
AR 06/22 | AR0622-DWG-PP-00-004 | ARO1822-DWG-PP-00-004 | Piping Layout Drawing For Cellar Deck P3 Area (Demolition) |  | 10 | 50 | 5 | 75
AR 06/22 | AR0622-DWG-PP-00-005 | ARO1822-DWG-PP-00-005 | Piping Layout Drawing For Cellar Deck P2 Area (Demolition) |  | 10 | 50 | 5 | 75
AR 06/22 | AR0622-DWG-PP-00-006 | ARO1822-DWG-PP-00-006 | Sections And Details For Cellar Deck P3 Area |  | 20 | 100 | 5 | 155
AR 06/22 | AR0622-DWG-PP-00-007 | ARO1822-DWG-PP-00-007 | Sections And Details For Cellar Deck P2 Area |  | 20 | 100 | 5 | 155
AR 06/22 | AR0622-DWG-PP-00-008 | ARO1822-DWG-PP-00-008 | Piping Tie-In Details Drawings |  | 12 | 80 | 4 | 116
AR 06/22 | AR0622-DWG-PP-00-009 | ARO1822-DWG-PP-00-009 | Piping Isometric For Cellar Deck P3 Area |  | 5 | 28 | 2 | 47
AR 06/22 | AR0622-DWG-PP-00-010 | ARO1822-DWG-PP-00-010 | Piping Isometric For Cellar Deck P2 Area |  | 8 | 28 | 3 | 51
AR 06/22 | AR0622-DWG-PP-00-011 | ARO1822-DWG-PP-00-011 | Piping Isometric For Pipeline pumps (Demolition) |  | 2 | 12 | 2 | 19
AR 06/22 | AR0622-DWG-PP-00-012 | ARO1822-DWG-PP-00-012 | Piping Isometric For Booster pumps and lact unit (Demolition) |  | 2 | 12 | 2 | 19
AR 06/22 | AR0622-STD-PP-00-001 | ARO1822-STD-PP-00-001 | Pipe Support Details |  | 4 | 120 | 8 | 172
AR 06/22 | AR0622-RQ-PP-00-001 | ARO1822-RQ-PP-00-001 | Material Requisition For Piping & Fittings Material |  | 12 | 0 | 3 | 15
AR 06/22 | AR0622-RQ-PP-00-002 | ARO1822-RQ-PP-00-002 | Material Requisition For Valves |  | 12 | 0 | 3 | 15
AR 06/22 | AR0622-DWG-EL-00-001 | ARO1822-DWG-EL-00-001 | Cable Routing Layout |  | 8 | 45 | 2 | 57
AR 06/22 | AR0622-DWG-EL-00-002 | ARO1822-DWG-EL-00-002 | Earthing Layout |  | 4 | 24 | 2 | 32
AR 06/22 | AR0622-DWG-EL-00-004 | ARO1822-DWG-EL-00-004 | Single Line Diagram_Tie-In For Electrical Motors |  | 4 | 28 | 2 | 36
AR 06/22 | AR0622-DWG-EL-00-008 | ARO1822-DWG-EL-00-008 | Schematic and Wiring Diagrams |  | 4 | 24 | 2 | 32
AR 06/22 | AR0622-CLC-EL-00-001 | ARO1822-CLC-EL-00-001 | Lv Cable Sizing Calculation |  | 32 | 4 | 4 | 40
AR 06/22 | AR0622-LIS-EL-00-002 | ARO1822-LIS-EL-00-002 | Electrical Cable List |  | 32 | 4 | 8 | 44
AR 06/22 | AR0622-LIS-EL-00-003 | ARO1822-LIS-EL-00-003 | Electrical Bulk Of Materials |  | 12 | 40 | 4 | 60
AR 06/22 | AR0622-RQ-EL-00-001 | ARO1822-RQ-EL-00-001 | Material Requisition For Electrical Cables |  | 24 | 0 | 4 | 28
AR 06/22 | AR0622-RQ-EL-00-002 | ARO1822-RQ-EL-00-002 | Material Requisition For Bulk Materials |  | 16 | 8 | 4 | 30
AR 06/22 | AR0622-SPC-IN-00-001 | ARO1822-SPC-IN-00-001 | Specification For Plc |  | 16 | 0 | 4 | 20
AR 06/22 | AR0622-SPC-IN-00-002 | ARO1822-SPC-IN-00-002 | General Instrument Specification |  | 32 | 0 | 6 | 38
AR 06/22 | AR0622-DSH-IN-00-001 | ARO1822-DSH-IN-00-001 | Instruments Cables Datasheets |  | 8 | 0 | 2 | 10
AR 06/22 | AR0622-DWG-IN-00-001 | ARO1822-DWG-IN-00-001 | Instrument Cable Routing Layouts |  | 4 | 16 | 2 | 26
AR 06/22 | AR0622-RQ-IN-00-001 | ARO1822-RQ-IN-00-001 | Plc Requisition |  | 8 | 0 | 2 | 10
AR 06/22 | AR0622-RQ-IN-00-002 | ARO1822-RQ-IN-00-002 | Instruments Cables Requisitions |  | 8 | 0 | 2 | 10
AR 06/22 | AR0622-DSH-IN-00-003 | ARO1822-DSH-IN-00-003 | Export Pumps Pressure Instruments Datasheets |  | 16 | 0 | 4 | 20
AR 06/22 | AR0622-DSH-IN-00-006 | ARO1822-DSH-IN-00-006 | Junction Box Datasheets |  | 20 | 0 | 4 | 24
AR 06/22 | AR0622-DSH-IN-00-007 | ARO1822-DSH-IN-00-007 | Export Pumps Flow Instruments Datasheets
AR 06/22 | AR0622-DSH-IN-00-008 | ARO1822-DSH-IN-00-008 | Export Pumps Control Valves Datasheets
AR 06/22 | AR0622-LIS-IN-00-001 | ARO1822-LIS-IN-00-001 | Booster And Expedition Pumps Instruments Index |  | 12 | 0 | 4 | 16
AR 06/22 | AR0622-LIS-IN-00-002 | ARO1822-LIS-IN-00-002 | Booster And Expedition Pumps I/O Lists |  | 12 | 0 | 4 | 16
AR 06/22 | AR0622-LIS-IN-00-003 | ARO1822-LIS-IN-00-003 | Booster And Expedition Pumps Instrument Cable Schedule |  | 12 | 0 | 4 | 16
AR 06/22 | AR0622-LIS-IN-00-004 | ARO1822-LIS-IN-00-004 | Booster And Expedition Pumps Instrument Bulk Material |  | 12 | 0 | 4
AR 06/22 | AR0622-DWG-IN-00-002 | ARO1822-DWG-IN-00-002 | Booster And Expedition Pumps Instrument Loop Diagrams |  | 10 | 24 | 3 | 40
AR 06/22 | AR0622-DWG-IN-00-003 | ARO1822-DWG-IN-00-003 | Booster And Expedition Pumps Instrment Hook-Up And Installation Diagrams |  | 10 | 24 | 3 | 40
AR 06/22 | AR0622-RQ-IN-00-003 | ARO1822-RQ-IN-00-003 | Pressure Instruments Requisition |  | 8 | 0 | 4 | 12
AR 06/22 | AR0622-RQ-IN-00-004 | ARO1822-RQ-IN-00-004 | Bulk Requisitions |  | 8 | 0 | 2 | 10
AR 06/22 | AR0622-RQ-IN-00-005 | ARO1822-RQ-IN-00-005 | Junction Box Requisitions |  | 8 | 0 | 2 | 10
AR 06/22 | AR0622-RQ-IN-00-006 | ARO1822-RQ-IN-00-006 | Flow Instruments Requisition
AR 06/22 | AR0622-RQ-IN-00-007 | ARO1822-RQ-IN-00-007 | Control Valves Requisition
AR 06/22 | AR0622-LIS-IN-00-005 | ARO1822-LIS-IN-00-005 | Hydrocyclone Instruments Index |  | 12 | 0 | 4 | 16
AR 06/22 | AR0622-LIS-IN-00-006 | ARO1822-LIS-IN-00-006 | Hydrocyclone I/O Lists |  | 12 | 0 | 4 | 16
AR 06/22 | AR0622-DWG-IN-00-005 | ARO1822-DWG-IN-00-005 | Hydrocyclone Instrument Loop Diagrams |  | 8 | 16 | 1 | 27
AR 06/22 | AR0622-DWG-IN-00-006 | ARO1822-DWG-IN-00-006 | Hydrocyclone Instrment Hook-Up And Installation Diagrams |  | 8 | 24 | 2 | 37
AR 06/22 | AR0622-DWG-IN-00-007 | ARO1822-DWG-IN-00-007 | Hydrocyclone Cable Routing Layouts |  | 8 | 24 | 1 | 36
AR 06/22 | AR0622-DWG-SF-00-001 | ARO1822-DWG-SF-00-001 | Hazardous Area Classification (Update) |  | 16 | 24 | 4 | 50