## DocumentEtude
Reference | CodeDocument | CodeDocumentlient | TitreDocument | Rev | NBHIngenieur | NBHProjeteur | NBHIngenieur | NBHProjeteur | Etat
AR 01/2214 | AR0122-RPT-CV-14-001 | NAWCPF-EPPM-WAZ1-110-CV-SOW-00001 | AZIZA-1 Drilling activities Civil SOW |  | 24 | 0 | 4 | 0
AR 01/2214 | AR0122-DWG-CV-14-001 | NAWCPF-EPPM-WAZ1-110-CV-DAS-00001 | AZIZA-1 Drilling activities civil General arrangement |  | 0 | 32 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-002 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00001 | AZIZA-1 Drilling activities Fencing Details drawing |  | 0 | 24 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-003 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00002 | AZIZA-1 Drilling activities - Formwork drawing |  | 0 | 32 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-004 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00003 | AZIZA-1 Drilling activities - Reinforcement and détails drawing |  | 0 | 40 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-005 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00004 | AZIZA-1 Drilling activities Acces Road Details drawing |  | 0 | 40 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-006 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00005 | AZIZA-1 Drilling activities Acces Road Map details drawing |  | 0 | 24 | 4 | 6
AR 01/2214 | AR0122-DWG-CV-14-007 | NAWCPF-EPPM-WAZ1-110-CV-DRW-00006 | AZIZA-1 Drilling activities Miscellaneous foundation details drawing |  | 0 | 32 | 4 | 6
AR 01/2214 | AR0122-LIS-CV-14-001 | NAWCPF-EPPM-WAZ1-110-CV-MTO-00001 | AZIZA-1 Drilling activities Civil MTO |  | 8 | 32 | 8 | 8
AR 01/2214 | AR0122-CLC-CV-14-001 | NAWCPF-EPPM-WAZ1-110-CV-CLN-00001 | AZIZA-1 Drilling activities Rig foundation calculation Note |  | 32 | 0 | 8 | 0
AR 01/2214 | AR0122-LIS-EL-14-001 | NAWCPF-EPPM-WAZ1-110-EL-LST-00001 | AZIZA-1 Electrical Bulk Material List |  | 8 | 24 | 2 | 2
AR 01/2214 | AR0122-DWG-EL-14-001 | NAWCPF-EPPM-WAZ1-110-EL-LAY-00001 | AZIZA-1 Earthing Layout |  | 8 | 24 | 2 | 2
AR 01/2214 | AR0122-RQ-EL-14-001 | NAWCPF-EPPM-WAZ1-110-EL-REQ-00001 | AZIZA-1 Material Requisition Of The Bulk Material |  | 16 | 0 | 4 | 0