## Instructions for Use (hidden)
Using the 'xVDB Import Forecast List rev0.xlsm' Workbook
Revision Date: 26-Jun-2018
Table of Contents
| 1 | Workbook Presentation & Use Context
| 2 | Building the Forecast List of Documents
| 3 | Importing the list in xVDB Web
| 4 | Customizing the Dictionary
1 Workbook Presentation & Use Context
This workbook is available to all but requires the use of macros to be enabled in the application
In order to interface with the xVDB, the minimum access level required to the xVDB is "Author" with "VDBOperator" role
The file consists of 3 tabs :
- The 'Instructions for Use' Tab (current one) describes the correct procedure for using the workbook and is for consultancy purposes only
- The 'Forecast List' Tab is the working sheet used to define the identification and criterias of forecast documents and is fully editable
- The 'Dictionary' Tab is available to provide details regarding the fields for which data may be imported and should only be modified by trained users
The 'Forecast List' Tab displays 2 types of data fields :
- In Blue : the required document identification (Requisition and Document References, Document Title & Forecast Date)
- In Green : the additional document identification, specificities, characteristics, free criterias …
The 'Dictionary' Tab lists all the additional fields for which data may be imported along with the specificities linked to each
Refer to it for information
2 Building the Forecast List of Documents
Begin by populating the blue cells with applicable data according to VDB Requisition
The Requisition Reference must be consistent with the corresponding reference in xVDB
No special characters are allowed in Requisition & Document References and Title; only letters, numbers and the "-" symbol
As a general rule, the comma (,) is forbidden and avoid special characters
The Document Reference must be unique and not yet recorded in the xVDB. In case of redundancy, the second entry will not be processed by the system
Additional data may be imported in the forecast documents by using the green cells
Select from the drop down list the applicable field(s) for which data will have to be imported
Populate the values as necessary relying on the 'Dictionary' Tab
Warning regarding several data fields :
|  | - Date Fields: |  | Date interpretation can be tricky depending on the local desktop configuration; it is therefore recommended to use the Date Format dd/mm/yyyy
or tryout another excel date format on a few imported documents before applying to a numerous list of documents
|  | - Client Approval Required: |  |  | Indicate 'Yes' if applicable (case sensitive), or leave blank
|  | - Data analysis: |  | Do not skip rows or skip columns (leaving them blank) as all beyond the first encountered blank row or column will be disregarded for the import
3 Importing the list in xVDB Web
In order to interface with xVDB the spreadsheet must first be transformed to a Text File for import in the xVDB
Once all the metadata has been filled in following the requirements and warnings, use the 'Generate Import File' button
Save the Text File in an easy access location and clear name for further browsing
Confirmation of generated Text File is displayed along with complete file path and the number of documents found in the list
The Text File is now to be imported in the corresponding xVDB
In the 'Works' section of the 'Requisitions & Purchase Orders' Menu, use the 'Import Forecast List' action
Browse to select the Text File generated and saved previously
The upload time depends on the number of metadata to process
Upon completion, the following message is displayed and e-mail is received (when no issue is encountered)
In case the Import Process encounters any issue, it will be reported in the received e-mail (example here-after):
In the xVDB, all successfully created Forecast Documents are then available, with all provided metadata, for first record
4 Customizing the Dictionary
Only trained users should customize the 'Dictionary' Tab to fit the project use of characteristics and free criterias
- The 'Field Label' list corresponds to the labels displayed in the xVDB document :
It should NOT be modified as it enables mapping within the document
- The 'Project Specific Label' list corresponds to the actual meaning of the fields on the project if different from standard
This can be modified (especially for the Free Criteria labels) before beginning to fill in the 'Forecast List' table
- Column C is hidden on purpose. It contains the technical field labels used to fill in the correct fields in the xVDB document
IT MUSN'T BE MODIFIED UNDER ANY CIRCUMSTANCE
- The 'Unique or Multiple Value(s)' & 'Format / Separator' lists indicate whether a field can contain several data or not and the format to use for each
It should NOT be modified
- The 'Project Specific Remark' list is dedicated to the project users and in no way used by the system
It could list for example the acceptable project values for various fields

## DocumentEtude
|  | VendorDocRef | VendorDocNm
Reference | CodeDocument | CodeDocumentlient | TitreDocument | REV | NBHIngenieur | NBHProjeteur | NBHIngenieur | NBHProjeteur
AR 05/2202 | AR0522-CLC-ME-05-201 | 3945_18-IN20510A-00285 | PIPING STRESS CALCULATIONS BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 10 | 50 | 8 | 0
AR 05/2202 | AR0522-CLC-CV-05-201 | 3945_18-IN20510A-00263 | STRUCTURAL STEEL CALCULATIONS BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 2 | 26 | 1 | 0
AR 05/2202 | AR0522-DWG-CV-05-201 | 3945_18-IN20510A-00223 | STRUCTURAL STEEL DETAIL DRAWINGS BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 0 | 4 | 25 | 5
AR 05/2202 | AR0522-DWG-CV-05-202 | 3945_18-IN20510A-00575 | FOUNDATION LAYOUT AND LOADING PLAN BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 1 | 1 | 14 | 2
AR 05/2202 | AR0522-DWG-PP-05-201 | 3945_18-IN20510A-00006 | PIPING AND INSTRUMENTATION DIAGRAM (P&ID) BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 1 | 2 | 10 | 2
AR 05/2202 | AR0522-DWG-PP-05-202 | 3945_18-IN20510A-00172 | GENERAL ARRANGEMENT DRAWINGS BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 1 | 5 | 24 | 6
AR 05/2202 | AR0522-DWG-PP-05-203 | 3945_18-IN20510A-00241 | 3D MODEL BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 5 | 5 | 80 | 40
AR 05/2202 | AR0522-DWG-PP-05-204 | 3945_18-IN20510A-00154 | NAMEPLATE SKIDS GAS 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 6 | 2
AR 05/2202 | AR0522-DWG-PP-05-205 | 3945_18-IN20510A-00193 | ISOMETRICS BOOK DRAWINGS BACK-UP SALES GAS METERING SKID 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 18 | 6
AR 05/2202 | AR0522-LIS-PP-05-201 | NA | MTO PIPING - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-LIS-PP-05-202 | NA | MTO STUD-BOLTS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-LIS-PP-05-203 | NA | MTO U-BOLTS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-LIS-PP-05-204 | NA | MTO GASKETS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-CLC-EL-05-201 | 3945_18-IN20510A-00627 | POWER & UTILITY CONSUMPTION CALCULATION SHEET - 60-Y0451 FOR METERING SYSTEMS |  | 2 | 10 | 0 | 0
AR 05/2202 | AR0522-DWG-EL-05-201 | 3945_18-IN20510A-00629 | SINGLE LINE DIAGRAM SKID GAS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 8 | 4
AR 05/2202 | AR0522-DWG-EL-05-202 | 3945_18-IN20510A-00631 | POWER DISTRIBUTION BOARD DIAGRAMS GAS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 10 | 4
AR 05/2202 | AR0522-LIS-IN-05-201 | 3945_18-IN20510A-00302 | HARDWIRED I/O LIST FOR METERING SYSTEMS |  | 0 | 0 | 0 | 0
AR 05/2202 | AR0522-LIS-IN-05-202 | 3945_18-IN20510A-00309 | CABLES LISTS GAS - 60-Y0451 FOR METERING SYSTEMS |  | 2 | 16 | 4 | 0
AR 05/2202 | AR0522-DWG-IN-05-201 | 3945_18-IN20510A-00433 | CABLE BLOCK DIAGRAM GAS SKIDS - 60-Y0451 FOR METERING SYSTEMS |  | 1 | 2 | 6 | 1
AR 05/2202 | AR0522-DWG-IN-05-202 | 3945_18-IN20510A-00547 | JUNCTION BOX DIAGRAM - GAS - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 4 | 22 | 2
AR 05/2202 | AR0522-DWG-IN-05-203 | 3945_18-IN20510A-00633 | INSTRUMENT HOOK UP DRAWINGS AND MOUNTING DETAILS - GAS - 60-Y0451 FOR METERING SYSTEMS |  | 4 | 20 | 18 | 4
AR 05/2202 | AR0522-DWG-IN-05-204 | 3945_18-IN20510A-00396 | FLOW METERING SUPERVISORY COMPUTER CABINET GAS GA DRAWING (ITR-87A) 61-Y3101 - 60-Y0451 - 60-Y0701 |  | 2 | 4 | 34 | 0
AR 05/2202 | AR0522-DWG-IN-05-205 | 3945_18-IN20510A-00635 | FLOW METERING FLOW COMPUTER CABINET GA DRAWING (ITR-87A) 60-Y0451 FOR METERING SYSTEMS |  | 1 | 1 | 10 | 2
AR 05/2202 | AR0522-DWG-IN-05-206 | 3945_18-IN20510A-00416 | LOOP WIRING DRAWINGS SUPERVISORY COMPUTER CABINET GAS (ITR-87A) 61-Y3101 - 60-Y0451 - 60-Y0701 FOR |  | 4 | 7 | 82 | 4
AR 05/2202 | AR0522-DWG-IN-05-207 | 3945_18-IN20510A-00625 | LOOP WIRING DRAWINGS FLOW COMPUTER CABINET GAS (ITR-87A) 60-Y0451 FOR METERING SYSTEMS |  | 2 | 4 | 14 | 2
AR 05/2202 | AR0522-DWG-PP-05-206 | 3945_18-IN20510A-00008 | PIPING AND INSTRUMENTATION DIAGRAM (P&ID) BACK-UP SALES GAS ANALYSER SYSTEM 60-Y0451 |  | 1 | 2 | 10 | 2
AR 05/2202 | AR0522-DWG-PP-05-207 | 3945_18-IN20510A-00174 | GENERAL ARRANGEMENT DRAWINGS BACK-UP SALES GAS ANALYSER SYSTEM 60-Y0451 FOR METERING SYSTEMS |  | 1 | 2 | 24 | 6
AR 05/2202 | AR0522-DWG-PP-05-208 | K-3945_18-IN20510A-00243 | 3D MODEL BACK-UP SALES GAS ANALYSER SYSTEM 60-Y0451 FOR METERING SYSTEMS |  | 1 | 2 | 24 | 6
AR 05/2202 | AR0522-DWG-IN-05-208 | 3945_18-IN20510A-00527 | CABLE BLOCK DIAGRAM ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 1 | 2 | 6 | 1
AR 05/2202 | AR0522-DWG-IN-05-209 | 3945_18-IN20510A-00562 | CABLES LISTS ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 0 | 0 | 0
AR 05/2202 | AR0522-DWG-IN-05-210 | 3945_18-IN20510A-00553 | JUNCTION BOX DIAGRAM - ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 4 | 22 | 2
AR 05/2202 | AR0522-DWG-EL-05-203 | 3945_18-IN20510A-00591 | POWER DISTRIBUTION BOARD DIAGRAMS ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 0 | 0 | 0
AR 05/2202 | AR0522-DWG-EL-05-204 | 3945_18-IN20510A-00586 | SINGLE LINE DIAGRAM ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 8 | 4
AR 05/2202 | AR0522-CLC-ME-06-201 | 3945_18-IN20510A-00285 | PIPING STRESS CALCULATIONS C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 10 | 50 | 8 | 0
AR 05/2202 | AR0522-CLC-CV-06-201 | 3945_18-IN20510A-00263 | STRUCTURAL STEEL CALCULATIONS C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 2 | 26 | 1 | 0
AR 05/2202 | AR0522-DWG-CV-06-201 | 3945_18-IN20510A-00224 | STRUCTURAL STEEL DETAIL DRAWINGS C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 0 | 4 | 25 | 5
AR 05/2202 | AR0522-DWG-CV-06-202 | 3945_18-IN20510A-00576 | FOUNDATION LAYOUT AND LOADING PLAN C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 1 | 1 | 14 | 2
AR 05/2202 | AR0522-DWG-PP-06-201 | 3945_18-IN20510A-00007 | PIPING AND INSTRUMENTATION DIAGRAM (P&ID) C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 10 | 2
AR 05/2202 | AR0522-DWG-PP-06-202 | 3945_18-IN20510A-00173 | GENERAL ARRANGEMENT DRAWINGS C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 1 | 5 | 24 | 6
AR 05/2202 | AR0522-DWG-PP-06-203 | 3945_18-IN20510A-00242 | 3D MODEL C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 5 | 5 | 80 | 40
AR 05/2202 | AR0522-DWG-PP-06-204 | 3945_18-IN20510A-00155 | NAMEPLATE SKIDS GAS 60-Y0701 FOR METERING SYSTEMS |  | 0 | 2 | 6 | 2
AR 05/2202 | AR0522-DWG-PP-06-205 | 3945_18-IN20510A-00194 | ISOMETRICS BOOK DRAWINGS C2 VAPOUR METERING SKID 60-Y0701 FOR METERING SYSTEMS |  | 0 | 2 | 18 | 6
AR 05/2202 | AR0522-LIS-PP-06-201 | NA | MTO PIPING - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-LIS-PP-06-202 | NA | MTO STUD-BOLTS - 60-Y0701 FOR METERING SYSTEMS
AR 05/2202 | AR0522-LIS-PP-06-203 | NA | MTO U-BOLTS - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-LIS-PP-06-204 | NA | MTO GASKETS - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 1 | 7 | 1
AR 05/2202 | AR0522-CLC-EL-06-201 | 3945_18-IN20510A-00628 | POWER & UTILITY CONSUMPTION CALCULATION SHEET - 60-Y0701 FOR METERING SYSTEMS |  | 2 | 10 | 0 | 0
AR 05/2202 | AR0522-DWG-EL-06-201 | 3945_18-IN20510A-00630 | SINGLE LINE DIAGRAM SKID GAS - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 2 | 8 | 4
AR 05/2202 | AR0522-DWG-EL-06-202 | 3945_18-IN20510A-00632 | POWER DISTRIBUTION BOARD DIAGRAMS GAS - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 2 | 10 | 4
AR 05/2202 | AR0522-LIS-IN-06-201 | 3945_18-IN20510A-00302 | HARDWIRED I/O LIST FOR METERING SYSTEMS |  | 0 | 0 | 0 | 0
AR 05/2202 | AR0522-LIS-IN-06-202 | 3945_18-IN20510A-00310 | CABLES LISTS GAS - 60-Y0701 FOR METERING SYSTEMS |  | 2 | 16 | 4 | 0
AR 05/2202 | AR0522-DWG-IN-06-201 | 3945_18-IN20510A-00434 | CABLE BLOCK DIAGRAM GAS SKIDS - 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 6 | 1
AR 05/2202 | AR0522-DWG-IN-06-202 | 3945_18-IN20510A-00548 | JUNCTION BOX DIAGRAM - GAS - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 4 | 22 | 2
AR 05/2202 | AR0522-DWG-IN-06-203 | 3945_18-IN20510A-00634 | INSTRUMENT HOOK UP DRAWINGS AND MOUNTING DETAILS - GAS - 60-Y0701 FOR METERING SYSTEMS |  | 4 | 20 | 18 | 4
AR 05/2202 | AR0522-DWG-IN-06-204 | 3945_18-IN20510A-00396 | FLOW METERING SUPERVISORY COMPUTER CABINET GAS GA DRAWING (ITR-87A) 61-Y3101 - 60-Y0451 - 60-Y0701 |  | 2 | 4 | 34 | 0
AR 05/2202 | AR0522-DWG-IN-06-205 | 3945_18-IN20510A-00636 | FLOW METERING FLOW COMPUTER CABINET GA DRAWING (ITR-87A) 60-Y07011 FOR METERING SYSTEMS |  | 1 | 1 | 10 | 2
AR 05/2202 | AR0522-DWG-IN-06-206 | 3945_18-IN20510A-00416 | LOOP WIRING DRAWINGS SUPERVISORY COMPUTER CABINET GAS (ITR-87A) 61-Y3101 - 60-Y0451 - 60-Y0701 |  | 4 | 7 | 82 | 4
AR 05/2202 | AR0522-DWG-IN-06-207 | 3945_18-IN20510A-00626 | LOOP WIRING DRAWINGS FLOW COMPUTER CABINET GAS (ITR-87A) 60-Y0701 FOR METERING SYSTEMS |  | 2 | 4 | 14 | 2
AR 05/2202 | AR0522-DWG-PP-06-206 | 3945_18-IN20510A-00009 | PIPING AND INSTRUMENTATION DIAGRAM (P&ID) C2 VAPOUR ANALYSER SYSTEM 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 10 | 2
AR 05/2202 | AR0522-DWG-PP-06-207 | 3945_18-IN20510A-00175 | GENERAL ARRANGEMENT DRAWINGS C2 VAPOUR ANALYSER SYSTEM 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 24 | 6
AR 05/2202 | AR0522-DWG-PP-06-208 | K-3945_18-IN20510A-00244 | 3D MODEL C2 VAPOUR ANALYSER SYSTEM 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 24 | 6
AR 05/2202 | AR0522-DWG-IN-06-208 | 3945_18-IN20510A-00528 | CABLE BLOCK DIAGRAM ANALYSER CABINET - 60-Y0701 FOR METERING SYSTEMS |  | 1 | 2 | 6 | 1
AR 05/2202 | AR0522-DWG-IN-06-209 | 3945_18-IN20510A-00563 | CABLES LISTS ANALYSER CABINET - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 0 | 4 | 0
AR 05/2202 | AR0522-DWG-IN-06-210 | 3945_18-IN20510A-00555 | JUNCTION BOX DIAGRAM - ANALYSER CABINET - 60-Y0701 FOR METERING SYSTEMS |  | 0 | 4 | 22 | 2
AR 05/2202 | AR0522-DWG-EL-06-203 | 3945_18-IN20510A-00591 | POWER DISTRIBUTION BOARD DIAGRAMS ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 0 | 0 | 0
AR 05/2202 | AR0522-DWG-EL-06-204 | 3945_18-IN20510A-00592 | SINGLE LINE DIAGRAM ANALYSER CABINET - 60-Y0451 FOR METERING SYSTEMS |  | 0 | 2 | 8 | 4

## Dictionary (hidden)
Field Label | Project Specific Label | NotesItem | Unique or Multiple Value(s) | Format / Separator | Project Specific Remark
Secondary Document Reference | Secondary Document Reference | VendorDocClientRef | Unique |  | référence given by the VENDOR
Other Reference | Return Code to Vendor | VendorDocOtherClientRef | Unique |  | to add in all VDB/SDB
Document Format | Document Format | VendorDocFormat | Multiple | ,
Document Number of Pages | Document Number of Pages | VendorDocNumPages | Unique | Number only
Document Language | Document Language | VendorDocLanguage | Multiple | ,
Ultimate Due Date | Ultimate Due Date | UltimateDt_1 | Unique | Date Format : dd/mm/yyyy
Remarks | Remarks | VendorDocRemark | Unique
Revision Number | Revision Number | VendorDocRevNo | Unique
Revision Date | Revision Date | VendorDocRevDt | Unique | Date Format : dd/mm/yyyy
Revision Object | Revision Object | VendorDocRevObject | Unique
Vendor Transmittal | Vendor Transmittal | VendorTransRef | Unique
Client Approval Required | Client Approval Required | ClientApprovalRequired | Unique | Yes or leave blank
Free Criteria 1 | Document Class | Category_1 | Multiple | , | to add in all VDB/SDB
Free Criteria 2 | ICD | Category_2 | Multiple | , | to add in all VDB/SDB
Free Criteria 3 | Document type-Subtype | Category_3 | Multiple | , | to add in all VDB/SDB
Free Criteria 4 | Discipline-Subdiscipline | Category_4 | Multiple | , | to add in all VDB/SDB
Free Criteria 5 | Doc Items | Category_5 | Multiple | , | to add in all VDB/SDB
Free Criteria 6 | Subcontractor | Category_6 | Multiple | , | to add in all VDB/SDB
Free Criteria 7 | As-Built required | Category_7 | Multiple | , | to add in all VDB/SDB
Free Criteria 8 | Reviewing OC | Category_8 | Multiple | , | to add in all VDB/SDB
Free Criteria 9 | Free Criteria 9 | CategoryDt_9 | Unique | Date Format : dd/mm/yyyy
Free Criteria 10 | Free Criteria 10 | CategoryDt_10 | Unique | Date Format : dd/mm/yyyy
Free Criteria 11 | Free Criteria 11 | CategoryDt_11 | Unique | Date Format : dd/mm/yyyy
Free Criteria 12 | Free Criteria 12 | CategoryDt_12 | Unique | Date Format : dd/mm/yyyy
Free Criteria 13 | System-Unit | Category_13 | Multiple | , | to add in all VDB/SDB
Free Criteria 14 | Native File Required | Category_14 | Multiple | , | to add in all VDB/SDB
Free Criteria 15 | Merger | Category_15 | Unique |  | used in SDB
Free Criteria 16 | CTR Review Code (IFR/IFI) | Category_16 | Unique |  | to add in all VDB/SDB
Note on A1: Do not modify
Note on B1: Can be Customized
Note on C1: Do not modify