## Planning
Référence | Activity ID | Code Document | Activity Name | Original Duration | Predecessors (activity name)
AR 01/2214 | A1030 | AR0122-RPT-CV-14-001 | Drilling activities Civil SOW_IFR | 3
AR 01/2214 | A1040 | AR0122-RPT-CV-14-001 | Drilling activities Civil SOW_IFA | 2
AR 01/2214 | A1050 | AR0122-RPT-CV-14-001 | Drilling activities Civil SOW_IFC | 2
AR 01/2214 | A1060 | AR0122-DWG-CV-14-001 | Drilling activities civil General arrangement_IFR | 3
AR 01/2214 | A1070 | AR0122-DWG-CV-14-001 | Drilling activities civil General arrangement_IFA | 2
AR 01/2214 | A1080 | AR0122-DWG-CV-14-001 | Drilling activities civil General arrangement_IFC | 2
AR 01/2214 | A1090 | AR0122-DWG-CV-14-002 | Drilling activities Fencing Details drawing_IFR | 2
AR 01/2214 | A1100 | AR0122-DWG-CV-14-002 | Drilling activities Fencing Details drawing_IFA | 2
AR 01/2214 | A1110 | AR0122-DWG-CV-14-002 | Drilling activities Fencing Details drawing_IFC | 2
AR 01/2214 | A1120 | AR0122-DWG-CV-14-003 | Drilling activities - Formwork drawing_IFR | 2
AR 01/2214 | A1130 | AR0122-DWG-CV-14-003 | Drilling activities - Formwork drawing_IFA | 2
AR 01/2214 | A1140 | AR0122-DWG-CV-14-003 | Drilling activities - Formwork drawing_IFC | 2
AR 01/2214 | A1150 | AR0122-DWG-CV-14-004 | Drilling activities - Reinforcement and détails drawing_IFR | 2
AR 01/2214 | A1160 | AR0122-DWG-CV-14-004 | Drilling activities - Reinforcement and détails drawing_IFA | 2
AR 01/2214 | A1170 | AR0122-DWG-CV-14-004 | Drilling activities - Reinforcement and détails drawing_IFC | 2
AR 01/2214 | A1180 | AR0122-DWG-CV-14-005 | Drilling activities Acces Road Details drawing_IFR | 3
AR 01/2214 | A1190 | AR0122-DWG-CV-14-005 | Drilling activities Acces Road Details drawing_IFA | 2
AR 01/2214 | A1200 | AR0122-DWG-CV-14-005 | Drilling activities Acces Road Details drawing_IFC | 2
AR 01/2214 | A1210 | AR0122-DWG-CV-14-006 | Drilling activities Acces Road Map details drawing_IFR | 3
AR 01/2214 | A1220 | AR0122-DWG-CV-14-006 | Drilling activities Acces Road Map details drawin_IFA | 2
AR 01/2214 | A1230 | AR0122-DWG-CV-14-006 | Drilling activities Acces Road Map details drawing_IFC | 2
AR 01/2214 | A1240 | AR0122-DWG-CV-14-007 | Drilling activities Miscellaneous foundation details drawing_IFR | 2
AR 01/2214 | A1250 | AR0122-DWG-CV-14-007 | Drilling activities Miscellaneous foundation details drawing_IFA | 2
AR 01/2214 | A1260 | AR0122-DWG-CV-14-007 | Drilling activities Miscellaneous foundation details drawing_IFC | 2
AR 01/2214 | A1270 | AR0122-LIS-CV-14-001 | Drilling activities Civil MTO_IFR | 2
AR 01/2214 | A1280 | AR0122-LIS-CV-14-001 | Drilling activities Civil MTO_IFA | 2
AR 01/2214 | A1290 | AR0122-LIS-CV-14-001 | Drilling activities Civil MTO_IFC | 2
AR 01/2214 | A1300 | AR0122-CLC-CV-14-001 | Drilling activities Rig foundation calculation Note_IFR | 2
AR 01/2214 | A1310 | AR0122-CLC-CV-14-001 | Drilling activities Rig foundation calculation Note_IFA | 2
AR 01/2214 | A1320 | AR0122-CLC-CV-14-001 | Drilling activities Rig foundation calculation Note_IFC | 2
AR 01/2214 | A1330 | AR0122-LIS-EL-14-001 | Electrical Bulk Material List_IFR | 3
AR 01/2214 | A1340 | AR0122-LIS-EL-14-001 | Electrical Bulk Material List_IFA | 2
AR 01/2214 | A1350 | AR0122-LIS-EL-14-001 | Electrical Bulk Material List_IFC | 2
AR 01/2214 | A1360 | AR0122-DWG-EL-14-001 | Earthing Layout_IFR | 3
AR 01/2214 | A1370 | AR0122-DWG-EL-14-001 | Earthing Layout_IFA | 2
AR 01/2214 | A1380 | AR0122-DWG-EL-14-001 | Earthing Layout_IFC | 2
AR 01/2214 | A1390 | AR0122-RQ-EL-14-001 | Material Requisition Of The Bulk Material_IFR | 3
AR 01/2214 | A1400 | AR0122-RQ-EL-14-001 | Material Requisition Of The Bulk Material_IFA | 2
AR 01/2214 | A1410 | AR0122-RQ-EL-14-001 | Material Requisition Of The Bulk Material_IFC | 2