## Planning
Référence | Activity ID | Activity Name | Original Duration | NBHIngenieursenior | NBHIngenieurjunior | NBHProjeteursenior | NBHProjeteurjunior | Predecessors (activity name)
AR 11/19 | A3910 | Project Start | 0
AR 11/19 | A3920 | Kick Off Meeting | 0 |  |  |  |  | A3910
AR 11/19 | A3921 | Site Visit and Data Gathering | 0 |  |  |  |  | A3920
AR 11/19 | A3930 | BDEP Endorsement report approval | 0 |  |  |  |  | A3621
AR 11/19 | A3931 | Collect of All Required Data from Stakeholders | 0 |  |  |  |  | A3930
AR 11/19 | A3932 | Approval of Topographical Survey Specification | 0 |  |  |  |  | A3880, A3930
AR 11/19 | A3933 | Approval of Topo. by Sub-Contractor | 0 |  |  |  |  | A3932
AR 11/19 | A3934 | Approval of Topo. Sub-Contractor(s) by ILF/MARAFIQ | 0 |  |  |  |  | A3933
AR 11/19 | A3935 | Reception of Topographical Report - Forcemain 900 | 0 |  |  |  |  | A3934
AR 11/19 | A3938 | Reception of Topographical Report - Forcemain 1200 | 0 |  |  |  |  | A3934, A3935
AR 11/19 | A3940 | Approval of Radar Mapping Specification | 0 |  |  |  |  | A3900, A3930
AR 11/19 | A3941 | Approval of Radar Mapping by Sub-Contractor | 0 |  |  |  |  | A3940
AR 11/19 | A3942 | Approval of Radar Mapping Sub-Contractor(s) by ILF/MARAFIQ | 0 |  |  |  |  | A3941
AR 11/19 | A3943 | Reception of Radar Report | 0 |  |  |  |  | A3942
AR 11/19 | A5037 | Approval of Geotechnical Survey Specification | 0 |  |  |  |  | A3890, A3930
AR 11/19 | A5038 | Approval of Geo. by Sub-Contractor | 0 |  |  |  |  | A5037
AR 11/19 | A5039 | Approval of Geo. Sub-Contractor(s) by ILF/MARAFIQ | 0 |  |  |  |  | A5038
AR 11/19 | A5040 | Reception of Geotechnical Report | 0 |  |  |  |  | A5039
AR 11/19 | A5042 | Permit Package approval | 0 |  |  |  |  | A4960
AR 11/19 | A5043 | SEC Permit Submission | 0 |  |  |  |  | A2700, A2710, A3840, A3830, A3760, A2760
AR 11/19 | A5044 | Design Review 30% | 0 |  |  |  |  | A3990
AR 11/19 | A5045 | Reception of all LLI Vendor Documents | 0 |  |  |  |  | A3609, A3610, A3634, A3650, A3664, A3674, A3680, A3704, A3710, A3724, A3734, A3770, A3784, A3790, A3804, A3810, A3824, A3850, A3864, A3870
AR 11/19 | A5046 | Design Review 60% | 0 |  |  |  |  | A5044, A3993
AR 11/19 | A5047 | Reception of all Remaining Item Vendor Documents | 0 |  |  |  |  | A1004, A1014, A1024, A1034, A1054, A1080, A1090, A1100, A1184, A1194, A1210, A1220, A1404, A1434, A1450, A1480, A1714, A1744, A1770, A1854, A1874, A1884, A1894, A1904, A1914, A1924, A1934, A1944, A1954, A1964, A1974, A1990, A2000, A2010, A2020, A2030, A2040, A2050, A2060, A2070, A2080, A2394, A2404, A2414, A2464, A2474, A2570, A2590, A2600, A2610, A2620, A2630, A2640, A2650, A2984, A2994, A3000, A1446, A5046
AR 11/19 | A5048 | Design Review 90% | 0 |  |  |  |  | A5046, A3995
AR 11/19 | A5080 | Project Finish | 0 |  |  |  |  | A5042, A5043, A3574, A3584, A3594, A3604, A3609, A3610, A3634, A3650, A3664, A3674, A3680, A3704, A3710, A3724, A3734, A3744, A3754, A3764, A3770, A3784, A3790, A3804, A3810, A3824, A3834, A3844, A3850, A3864, A3870, A3880, A3890, A3900, A3970, A3984, A3995, A1004, A1014, A1024, A1034, A1054, A1080, A1090, A1100, A1184, A1194, A1210, A1220, A1234, A1240, A1274, A1284, A1294, A1304, A1329, A1324, A1334, A1404, A1434, A1450, A1480, A1494, A1504, A1510, A1534, A1554, A1564, A1574, A1624, A1634, A1609, A1644, A1654, A1664, A1674, A1684, A1694, A1714, A1744, A1764, A1770, A1784, A1804, A1814, A1824, A1834, A1854, A1874, A1884, A1894, A1904, A1914, A1924, A1934, A1944, A1954, A1964, A1974, A1990, A2000, A2010, A2020, A2030, A2040, A2050, A2060, A2070, A2080, A2094, A2104, A2114, A2124, A2240, A2134, A2144, A2154, A2164, A2174, A2186, A2194, A2204, A2214, A2224, A2234, A2394, A2404, A2414, A2464, A2474, A2494, A2504, A2514, A2524, A2534, A2544, A2554, A2564, A4014, A4024, A4034, A4044, A2570, A2590, A2600, A2610, A2620, A2630, A2640, A2650, A2694, A2704, A2714, A2724, A2734, A2744, A4050, A4064, A4074, A2754, A2764, A2774, A2784, A2794, A2804, A2814, A2824, A2834, A2844, A2854, A2864, A2874, A2884, A2894, A2904, A2914, A2924, A2934, A2944, A2954, A4084, A4094, A4104, A4114, A4124, A4134, A4144, A2964, A2974, A2984, A2994, A3000, A3014, A3024, A3034, A3044, A3054, A3094, A3104, A3114, A3124, A3134, A3144, A3154, A3164, A3174, A3184, A3194, A3204, A3214, A3224, A3234, A3244, A3254, A3264, A3274, A3284, A3294, A3304, A3314, A3324, A3334, A3344, A3354, A3364, A3374, A3384, A3394, A3404, A3414, A3424, A3434, A3444, A3454, A3464, A3474, A3484, A3494, A3504, A8014, A3524, A3534, A4505, A3554, A4154, A5048, A1086, A1179, A1172, A1352, A1382, A1446, A1756, A4500, A4470, A4440, A4410, A4380, A4350, A4320, A4290, A4530, A4560, A4590, A4620, A4650, A4680, A4710, A4740, A4770, A4800, A4830, A4860, A4890, A4920, A4934, A3189, A3517, A8005, A1317, A5375, A3640, A1540, A2180, A5070, A3559, A8020
AR 11/19 | A3559 | Field & Feed Verification | 19 |  |  |  |  | A3921
AR 11/19 | A3560 | BDEP endorsement Report_IFR | 12 |  |  |  |  | A3559
AR 11/19 | A3561 | BDEP endorsement Report_IFR Client review | 12 |  |  |  |  | A3560
AR 11/19 | A3620 | BDEP endorsement Report_IFA | 12 |  |  |  |  | A3561
AR 11/19 | A3621 | BDEP endorsement Report_IFA Client review | 12 |  |  |  |  | A3620
AR 11/19 | A3640 | BDEP endorsement Report_IFU | 12 |  |  |  |  | A5042, A3930
AR 11/19 | A3970 | Site Visit Report_IFI | 14 |  |  |  |  | A3921, A3621
AR 11/19 | A3980 | Basis Of Design_IFR | 6 |  |  |  |  | A3640, A3970
AR 11/19 | A3981 | Basis Of Design_IFR Client Review | 12 |  |  |  |  | A3980
AR 11/19 | A3982 | Basis Of Design_IFA | 5 |  |  |  |  | A3981
AR 11/19 | A3983 | Basis Of Design_IFA Client Review | 12 |  |  |  |  | A3982
AR 11/19 | A3984 | Basis Of Design_IFC | 2 |  |  |  |  | A3982, A3983
AR 11/19 | A3990 | 3D Model PS -56-A_IFR | 9 |  |  |  |  | A1530, A1550, A1560, A1570, A3600, A5050
AR 11/19 | A3992 | 3D Model PS -56-A_IFR Client Review | 12 |  |  |  |  | A3990
AR 11/19 | A3993 | 3D Model PS -56-A_IFA | 8 |  |  |  |  | A1572, A1562, A1552, A1532, A3602, A5045, A5060, A3992
AR 11/19 | A3994 | 3D Model PS -56-A_IFA Client Review | 12 |  |  |  |  | A3993
AR 11/19 | A3995 | 3D Model PS -56-A_IFC | 8 |  |  |  |  | A1574, A1564, A1554, A1534, A3604, A5047, A5070, A3994
AR 11/19 | A4960 | Engineering support documents for permit package | 70 |  |  |  |  | A3920, A3560
AR 11/19 | A3570 | Equipment Sizing Report (Including Pumps and Wet Well)_IFR | 5 |  |  |  |  | A3600
AR 11/19 | A3571 | Equipment Sizing Report (Including Pumps and Wet Well)_IFR Client Review | 12 |  |  |  |  | A3570
AR 11/19 | A3572 | Equipment Sizing Report (Including Pumps and Wet Well)_IFA | 3 |  |  |  |  | A3602, A3571
AR 11/19 | A3573 | Equipment Sizing Report (Including Pumps and Wet Well)_IFA Client Review | 12 |  |  |  |  | A3572
AR 11/19 | A3574 | Equipment Sizing Report (Including Pumps and Wet Well)_IFC | 2 |  |  |  |  | A3604, A3573
AR 11/19 | A3580 | Hydraulic Study Report_IFR | 6 |  |  |  |  | A3980
AR 11/19 | A3581 | Hydraulic Study Report_IFR Client Review | 12 |  |  |  |  | A3580
AR 11/19 | A3582 | Hydraulic Study Report_IFA | 3 |  |  |  |  | A3935, A3938, A3581
AR 11/19 | A3583 | Hydraulic Study Report_IFA Client Review | 12 |  |  |  |  | A3582
AR 11/19 | A3584 | Hydraulic Study Report_IFC | 2 |  |  |  |  | A5045, A3583
AR 11/19 | A3590 | Transient Analyses Report_IFR | 7 |  |  |  |  | A3570, A3935, A3582, A3938
AR 11/19 | A3591 | Transient Analyses Report_IFR Client Review | 12 |  |  |  |  | A3590
AR 11/19 | A3592 | Transient Analyses Report_IFA | 5 |  |  |  |  | A3591
AR 11/19 | A3593 | Transient Analyses Report_IFA Client Review | 12 |  |  |  |  | A3592
AR 11/19 | A3594 | Transient Analyses Report_IFC | 3 |  |  |  |  | A3593
AR 11/19 | A3600 | Piping & Instrumentation Diagram_IFR | 5 |  |  |  |  | A3580
AR 11/19 | A3601 | Piping & Instrumentation Diagram_IFR Client review | 12 |  |  |  |  | A3600
AR 11/19 | A3602 | Piping & Instrumentation Diagram_IFA | 4 |  |  |  |  | A3601
AR 11/19 | A3603 | Piping & Instrumentation Diagram_IFA Client review | 12 |  |  |  |  | A3602
AR 11/19 | A3604 | Piping & Instrumentation Diagram_IFC | 3 |  |  |  |  | A3603
AR 11/19 | A1620 | Operating And Control Philosophy_IFR | 4 |  |  |  |  | A3600
AR 11/19 | A1621 | Operating And Control Philosophy_IFR Client review | 12 |  |  |  |  | A1620
AR 11/19 | A1622 | Operating And Control Philosophy_IFA | 3 |  |  |  |  | A3602, A1621
AR 11/19 | A1623 | Operating And Control Philosophy_IFA Client review | 12 |  |  |  |  | A1622
AR 11/19 | A1624 | Operating And Control Philosophy_IFC | 2 |  |  |  |  | A3604, A1623
AR 11/19 | A1630 | Operating And Maintenance Manual_IFR | 6 |  |  |  |  | A5045
AR 11/19 | A1631 | Operating And Maintenance Manual_IFR Client review | 12 |  |  |  |  | A1630
AR 11/19 | A1632 | Operating And Maintenance Manual_IFA | 4 |  |  |  |  | A1631, A5047
AR 11/19 | A1633 | Operating And Maintenance Manual_IFA Client review | 12 |  |  |  |  | A1632
AR 11/19 | A1634 | Operating And Maintenance Manual_IFC | 3 |  |  |  |  | A1633
AR 11/19 | A1605 | Symbol And Abbreviations List_IFR | 3 |  |  |  |  | A3930, A3600
AR 11/19 | A1606 | Symbol And Abbreviations List_IFR Client review | 12 |  |  |  |  | A1605
AR 11/19 | A1607 | Symbol And Abbreviations List_IFA | 2 |  |  |  |  | A3602, A1606
AR 11/19 | A1608 | Symbol And Abbreviations List_IFA Client review | 12 |  |  |  |  | A1607
AR 11/19 | A1609 | Symbol And Abbreviations List_IFC | 2 |  |  |  |  | A3604, A1608
AR 11/19 | A1640 | Equipment List_IFR | 3 |  |  |  |  | A3570
AR 11/19 | A1641 | Equipment List_IFR Client review | 12 |  |  |  |  | A1640
AR 11/19 | A1642 | Equipment List_IFA | 2 |  |  |  |  | A1641
AR 11/19 | A1643 | Equipment List_IFA Client review | 12 |  |  |  |  | A1642
AR 11/19 | A1644 | Equipment List_IFC | 2 |  |  |  |  | A1643
AR 11/19 | A1650 | Line List_IFR | 3 |  |  |  |  | A3600
AR 11/19 | A1651 | Line List_IFR Client review | 12 |  |  |  |  | A1650
AR 11/19 | A1652 | Line List_IFA | 2 |  |  |  |  | A1651
AR 11/19 | A1653 | Line List_IFA Client review | 12 |  |  |  |  | A1652
AR 11/19 | A1654 | Line List_IFC | 2 |  |  |  |  | A1653
AR 11/19 | A1660 | Tie-In list_IFR | 4 |  |  |  |  | A3600, A1650
AR 11/19 | A1661 | Tie-In list_IFR Client review | 12 |  |  |  |  | A1660
AR 11/19 | A1662 | Tie-In list_IFA | 3 |  |  |  |  | A1661
AR 11/19 | A1663 | Tie-In list_IFA Client review | 12 |  |  |  |  | A1662
AR 11/19 | A1664 | Tie-In list_IFC | 2 |  |  |  |  | A1663
AR 11/19 | A1670 | Cause And Effect Diagram_IFR | 5 |  |  |  |  | A3600, A1660, A1650, A1620
AR 11/19 | A1671 | Cause And Effect Diagram_IFR Client review | 12 |  |  |  |  | A1670
AR 11/19 | A1672 | Cause And Effect Diagram_IFA | 4 |  |  |  |  | A1671, A3590
AR 11/19 | A1673 | Cause And Effect Diagram_IFA Client review | 12 |  |  |  |  | A1672
AR 11/19 | A1674 | Cause And Effect Diagram_IFC | 3 |  |  |  |  | A1673
AR 11/19 | A1680 | Block Flow Diagram_IFR | 6 |  |  |  |  | A3930, A1605
AR 11/19 | A1681 | Block Flow Diagram_IFR Client review | 12 |  |  |  |  | A1680
AR 11/19 | A1682 | Block Flow Diagram_IFA | 4 |  |  |  |  | A1681
AR 11/19 | A1683 | Block Flow Diagram_IFA Client review | 12 |  |  |  |  | A1682
AR 11/19 | A1684 | Block Flow Diagram_IFC | 2 |  |  |  |  | A3984, A1683
AR 11/19 | A1690 | Process Flow Diagram_IFR | 5 |  |  |  |  | A3930, A1680
AR 11/19 | A1691 | Process Flow Diagram_IFR Client review | 12 |  |  |  |  | A1690
AR 11/19 | A1692 | Process Flow Diagram_IFA | 4 |  |  |  |  | A1691
AR 11/19 | A1693 | Process Flow Diagram_IFA Client review | 12 |  |  |  |  | A1692
AR 11/19 | A1694 | Process Flow Diagram_IFC | 2 |  |  |  |  | A1684, A1693
AR 11/19 | A1710 | Specification for Packaged Air conditioning unit (PACU)_IFR | 4 |  |  |  |  | A3982
AR 11/19 | A1711 | Specification for Packaged Air conditioning unit (PACU)_IFR Client review | 12 |  |  |  |  | A1710
AR 11/19 | A1712 | Specification for Packaged Air conditioning unit (PACU)_IFA | 3 |  |  |  |  | A1711
AR 11/19 | A1713 | Specification for Packaged Air conditioning unit (PACU)_IFA Client review | 12 |  |  |  |  | A1712
AR 11/19 | A1714 | Specification for Packaged Air conditioning unit (PACU)_IFC | 2 |  |  |  |  | A1713
AR 11/19 | A1740 | Data Sheet for Packaged Air conditioning unit (PACU)_IFR | 4 |  |  |  |  | A1760
AR 11/19 | A1741 | Data Sheet for Packaged Air conditioning unit (PACU)_IFR Client review | 12 |  |  |  |  | A1740
AR 11/19 | A1742 | Data Sheet for Packaged Air conditioning unit (PACU)_IFA | 3 |  |  |  |  | A1741
AR 11/19 | A1743 | Data Sheet for Packaged Air conditioning unit (PACU)_IFA Client review | 12 |  |  |  |  | A1742
AR 11/19 | A1744 | Data Sheet for Packaged Air conditioning unit (PACU)_IFC | 2 |  |  |  |  | A1743
AR 11/19 | A1752 | Data Sheet for Exhaust Fans_IFR | 4 |  |  |  |  | A1760, A1740
AR 11/19 | A1753 | Data Sheet for Exhaust Fans_IFR Client review | 12 |  |  |  |  | A1752
AR 11/19 | A1754 | Data Sheet for Exhaust Fans_IFA | 3 |  |  |  |  | A1753
AR 11/19 | A1755 | Data Sheet for Exhaust Fans_IFA Client review | 12 |  |  |  |  | A1754
AR 11/19 | A1756 | Data Sheet for Exhaust Fans_IFC | 2 |  |  |  |  | A1755
AR 11/19 | A1760 | HVAC Calculation Note_IFR | 4 |  |  |  |  | A3980, A3180, A3220, A3240, A3280, A3300, A3185
AR 11/19 | A1761 | HVAC Calculation Note_IFR Client review | 12 |  |  |  |  | A1760
AR 11/19 | A1762 | HVAC Calculation Note_IFA | 3 |  |  |  |  | A1761
AR 11/19 | A1763 | HVAC Calculation Note_IFA Client review | 12 |  |  |  |  | A1762
AR 11/19 | A1764 | HVAC Calculation Note_IFC | 2 |  |  |  |  | A1763
AR 11/19 | A1770 | Requisition for HVAC equipment_IFU | 3 |  |  |  |  | A1762
AR 11/19 | A1780 | Electrical Building and Sec Room HVAC system Layout_IFR | 4 |  |  |  |  | A3180, A3220, A3240, A3280, A3300, A1760, A3185
AR 11/19 | A1781 | Electrical Building and Sec Room HVAC system Layout_IFR Client review | 12 |  |  |  |  | A1780
AR 11/19 | A1782 | Electrical Building and Sec Room HVAC system Layout_IFA | 3 |  |  |  |  | A1781
AR 11/19 | A1783 | Electrical Building and Sec Room HVAC system Layout_IFA Client review | 12 |  |  |  |  | A1782
AR 11/19 | A1784 | Electrical Building and Sec Room HVAC system Layout_IFC | 2 |  |  |  |  | A1783
AR 11/19 | A1800 | PLUMBING and HVAC Legend_IFR | 3 |  |  |  |  | A3930, A1810
AR 11/19 | A1801 | PLUMBING and HVAC Legend_IFR Client review | 12 |  |  |  |  | A1800
AR 11/19 | A1802 | PLUMBING and HVAC Legend_IFA | 2 |  |  |  |  | A1801
AR 11/19 | A1803 | PLUMBING and HVAC Legend_IFA Client review | 12 |  |  |  |  | A1802
AR 11/19 | A1804 | PLUMBING and HVAC Legend_IFC | 2 |  |  |  |  | A1803
AR 11/19 | A1810 | PLUMBING Layout_IFR | 3 |  |  |  |  | A3930, A3180, A3220, A3240, A3280, A3300, A1820, A3185
AR 11/19 | A1811 | PLUMBING Layout_IFR Client review | 12 |  |  |  |  | A1810
AR 11/19 | A1812 | PLUMBING Layout_IFA | 2 |  |  |  |  | A1810, A1811
AR 11/19 | A1813 | PLUMBING Layout_IFA Client review | 12 |  |  |  |  | A1812
AR 11/19 | A1814 | PLUMBING Layout_IFC | 2 |  |  |  |  | A1813
AR 11/19 | A1820 | Pump Room HVAC system Layout_IFR | 3 |  |  |  |  | A1780
AR 11/19 | A1821 | Pump Room HVAC system Layout_IFR Client review | 12 |  |  |  |  | A1820
AR 11/19 | A1822 | Pump Room HVAC system Layout_IFA | 2 |  |  |  |  | A1821
AR 11/19 | A1823 | Pump Room HVAC system Layout_IFA Client review | 12 |  |  |  |  | A1822
AR 11/19 | A1824 | Pump Room HVAC system Layout_IFC | 2 |  |  |  |  | A1823
AR 11/19 | A1830 | Generator Building HVAC system Layout_IFR | 3 |  |  |  |  | A1760
AR 11/19 | A1831 | Generator Building HVAC system Layout_IFR Client review | 12 |  |  |  |  | A1830
AR 11/19 | A1832 | Generator Building HVAC system Layout_IFA | 2 |  |  |  |  | A1831
AR 11/19 | A1833 | Generator Building HVAC system Layout_IFA Client review | 12 |  |  |  |  | A1832
AR 11/19 | A1834 | Generator Building HVAC system Layout_IFC | 2 |  |  |  |  | A1833
AR 11/19 | A3880 | Topographical Survey Specification_IFU | 5 |  |  |  |  | A3920
AR 11/19 | A3890 | Geotechnical Survey Specification_IFU | 3 |  |  |  |  | A3880
AR 11/19 | A3900 | Radar Mapping Specification_IFU | 2 |  |  |  |  | A3890
AR 11/19 | A3090 | Sewer Pump Sation Calculation Note_IFR | 4 |  |  |  |  | A1550, A1560, A5040, A5050
AR 11/19 | A3091 | Sewer Pump Sation Calculation Note_IFR Client review | 12 |  |  |  |  | A3090
AR 11/19 | A3092 | Sewer Pump Sation Calculation Note_IFA | 4 |  |  |  |  | A1562, A3091
AR 11/19 | A3093 | Sewer Pump Sation Calculation Note_IFA Client review | 12 |  |  |  |  | A3092
AR 11/19 | A3094 | Sewer Pump Sation Calculation Note_IFC | 3 |  |  |  |  | A3093
AR 11/19 | A3100 | Electrical and Control Building Calculation Note_IFR | 4 |  |  |  |  | A3180, A3190, A3200, A3210, A5040, A3185
AR 11/19 | A3101 | Electrical and Control Building Calculation Note_IFR Client review | 12 |  |  |  |  | A3100
AR 11/19 | A3102 | Electrical and Control Building Calculation Note_IFA | 3 |  |  |  |  | A3101
AR 11/19 | A3103 | Electrical and Control Building Calculation Note_IFA Client review | 12 |  |  |  |  | A3102
AR 11/19 | A3104 | Electrical and Control Building Calculation Note_IFC | 2 |  |  |  |  | A3103
AR 11/19 | A3110 | Sec Interface Building Calculation Note_IFR | 4 |  |  |  |  | A3220, A3230, A5040
AR 11/19 | A3111 | Sec Interface Building Calculation Note_IFR Client review | 12 |  |  |  |  | A3110
AR 11/19 | A3112 | Sec Interface Building Calculation Note_IFA | 3 |  |  |  |  | A3111
AR 11/19 | A3113 | Sec Interface Building Calculation Note_IFA Client review | 12 |  |  |  |  | A3112
AR 11/19 | A3114 | Sec Interface Building Calculation Note_IFC | 2 |  |  |  |  | A3113
AR 11/19 | A3120 | Generator Building Calculation Note_IFR | 4 |  |  |  |  | A3240, A3250, A5040
AR 11/19 | A3121 | Generator Building Calculation Note_IFR Client review | 12 |  |  |  |  | A3120
AR 11/19 | A3122 | Generator Building Calculation Note_IFA | 3 |  |  |  |  | A3121
AR 11/19 | A3123 | Generator Building Calculation Note_IFA Client review | 12 |  |  |  |  | A3122
AR 11/19 | A3124 | Generator Building Calculation Note_IFC | 2 |  |  |  |  | A3123
AR 11/19 | A3130 | Flow Meter Chamber Calculation Note_IFR | 4 |  |  |  |  | A1325, A1320, A5040, A1313, A5371
AR 11/19 | A3131 | Flow Meter Chamber Calculation Note_IFR Client review | 12 |  |  |  |  | A3130
AR 11/19 | A3132 | Flow Meter Chamber Calculation Note_IFA | 3 |  |  |  |  | A3131
AR 11/19 | A3133 | Flow Meter Chamber Calculation Note_IFA Client review | 12 |  |  |  |  | A3132
AR 11/19 | A3134 | Flow Meter Chamber Calculation Note_IFC | 2 |  |  |  |  | A3133
AR 11/19 | A3140 | Air Release Chamber Calculation Note_IFR | 4 |  |  |  |  | A1325, A1320, A3130, A5040, A1313, A5371
AR 11/19 | A3141 | Air Release Chamber Calculation Note_IFR Client review | 12 |  |  |  |  | A3140
AR 11/19 | A3142 | Air Release Chamber Calculation Note_IFA | 3 |  |  |  |  | A3141
AR 11/19 | A3143 | Air Release Chamber Calculation Note_IFA Client review | 12 |  |  |  |  | A3142
AR 11/19 | A3144 | Air Release Chamber Calculation Note_IFC | 2 |  |  |  |  | A3143
AR 11/19 | A3150 | Isolation Chamber Calculation Note_IFR | 4 |  |  |  |  | A1325, A1320, A3140, A5040, A1313, A5371
AR 11/19 | A3151 | Isolation Chamber Calculation Note_IFR Client review | 12 |  |  |  |  | A3150
AR 11/19 | A3152 | Isolation Chamber Calculation Note_IFA | 3 |  |  |  |  | A3151
AR 11/19 | A3153 | Isolation Chamber Calculation Note_IFA Client review | 12 |  |  |  |  | A3152
AR 11/19 | A3154 | Isolation Chamber Calculation Note_IFC | 2 |  |  |  |  | A3153
AR 11/19 | A3160 | Washout Chamber Calculation Note_IFR | 4 |  |  |  |  | A1325, A1320, A3150, A5040, A1313, A5371
AR 11/19 | A3161 | Washout Chamber Calculation Note_IFR Client review | 12 |  |  |  |  | A3160
AR 11/19 | A3162 | Washout Chamber Calculation Note_IFA | 3 |  |  |  |  | A3161
AR 11/19 | A3163 | Washout Chamber Calculation Note_IFA Client review | 12 |  |  |  |  | A3162
AR 11/19 | A3164 | Washout Chamber Calculation Note_IFC | 2 |  |  |  |  | A3163
AR 11/19 | A3170 | Site Development Plan-New Pump Station_IFR | 4 |  |  |  |  | A1530
AR 11/19 | A3171 | Site Development Plan-New Pump Station_IFR Client review | 12 |  |  |  |  | A3170
AR 11/19 | A3172 | Site Development Plan-New Pump Station_IFA | 3 |  |  |  |  | A3171
AR 11/19 | A3173 | Site Development Plan-New Pump Station_IFA Client review | 12 |  |  |  |  | A3172
AR 11/19 | A3174 | Site Development Plan-New Pump Station_IFC | 2 |  |  |  |  | A3173
AR 11/19 | A3180 | Electrical and Control Building -Ground Floor_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A3181 | Electrical and Control Building -Ground Floor_IFR Client review | 12 |  |  |  |  | A3180
AR 11/19 | A3182 | Electrical and Control Building -Ground Floor_IFA | 2 |  |  |  |  | A3181
AR 11/19 | A3183 | Electrical and Control Building -Ground Floor_IFA Client review | 12 |  |  |  |  | A3182
AR 11/19 | A3184 | Electrical and Control Building -Ground Floor_IFC | 2 |  |  |  |  | A3183
AR 11/19 | A3185 | Electrical and Control Building - Roof Plan & Ceiling plan_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A3186 | Electrical and Control Building - Roof Plan & Ceiling plan_IFR Client review | 12 |  |  |  |  | A3185
AR 11/19 | A3187 | Electrical and Control Building - Roof Plan & Ceiling plan_IFA | 2 |  |  |  |  | A3186
AR 11/19 | A3188 | Electrical and Control Building - Roof Plan & Ceiling plan_IFA Client review | 12 |  |  |  |  | A3187
AR 11/19 | A3189 | Electrical and Control Building - Roof Plan & Ceiling plan_IFC | 2 |  |  |  |  | A3188
AR 11/19 | A3190 | Electrical and Control Building Elevations and Sections_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A3191 | Electrical and Control Building Elevations and Sections_IFR Client review | 12 |  |  |  |  | A3190
AR 11/19 | A3192 | Electrical and Control Building Elevations and Sections_IFA | 2 |  |  |  |  | A3191
AR 11/19 | A3193 | Electrical and Control Building Elevations and Sections_IFA Client review | 12 |  |  |  |  | A3192
AR 11/19 | A3194 | Electrical and Control Building Elevations and Sections_IFC | 2 |  |  |  |  | A3193
AR 11/19 | A3200 | Electrical and Control Building Doors and Windows_IFR | 3 |  |  |  |  | A2880
AR 11/19 | A3201 | Electrical and Control Building Doors and Windows_IFR Client review | 12 |  |  |  |  | A3200
AR 11/19 | A3202 | Electrical and Control Building Doors and Windows_IFA | 2 |  |  |  |  | A3201
AR 11/19 | A3203 | Electrical and Control Building Doors and Windows_IFA Client review | 12 |  |  |  |  | A3202
AR 11/19 | A3204 | Electrical and Control Building Doors and Windows_IFC | 2 |  |  |  |  | A3203
AR 11/19 | A3210 | Electrical and Control Building details and schedules_IFR | 3 |  |  |  |  | A2880
AR 11/19 | A3211 | Electrical and Control Building details and schedules_IFR Client review | 12 |  |  |  |  | A3210
AR 11/19 | A3212 | Electrical and Control Building details and schedules_IFA | 2 |  |  |  |  | A3211
AR 11/19 | A3213 | Electrical and Control Building details and schedules_IFA Client review | 12 |  |  |  |  | A3212
AR 11/19 | A3214 | Electrical and Control Building details and schedules_IFC | 2 |  |  |  |  | A3213
AR 11/19 | A3220 | Sec Interface Building - Ground Floor , Roof Plan Elevations and Sections_IFR | 3 |  |  |  |  | A2830
AR 11/19 | A3221 | Sec Interface Building - Ground Floor , Roof Plan Elevations and Sections_IFR Client review | 12 |  |  |  |  | A3220
AR 11/19 | A3222 | Sec Interface Building - Ground Floor , Roof Plan Elevations and Sections_IFA | 2 |  |  |  |  | A3221
AR 11/19 | A3223 | Sec Interface Building - Ground Floor , Roof Plan Elevations and Sections_IFA Client review | 12 |  |  |  |  | A3222
AR 11/19 | A3224 | Sec Interface Building - Ground Floor , Roof Plan Elevations and Sections_IFC | 2 |  |  |  |  | A3223
AR 11/19 | A3230 | Sec Interface Building - schedule and details_IFR | 3 |  |  |  |  | A2820
AR 11/19 | A3231 | Sec Interface Building - schedule and details_IFR Client review | 12 |  |  |  |  | A3230
AR 11/19 | A3232 | Sec Interface Building - schedule and details_IFA | 2 |  |  |  |  | A3231
AR 11/19 | A3233 | Sec Interface Building - schedule and details_IFA Client review | 12 |  |  |  |  | A3232
AR 11/19 | A3234 | Sec Interface Building - schedule and details_IFC | 2 |  |  |  |  | A3233
AR 11/19 | A3240 | Generator Building -Ground Floor , Roof Plan Elevations and Sections_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A3241 | Generator Building -Ground Floor , Roof Plan Elevations and Sections_IFR Client review | 12 |  |  |  |  | A3240
AR 11/19 | A3242 | Generator Building -Ground Floor , Roof Plan Elevations and Sections_IFA | 2 |  |  |  |  | A3241
AR 11/19 | A3243 | Generator Building -Ground Floor , Roof Plan Elevations and Sections_IFA Client review | 12 |  |  |  |  | A3242
AR 11/19 | A3244 | Generator Building -Ground Floor , Roof Plan Elevations and Sections_IFC | 2 |  |  |  |  | A3243
AR 11/19 | A3250 | Generator Building -schedule and details_IFR | 3 |  |  |  |  | A2880
AR 11/19 | A3251 | Generator Building -schedule and details_IFR Client review | 12 |  |  |  |  | A3250
AR 11/19 | A3252 | Generator Building -schedule and details_IFA | 2 |  |  |  |  | A3251
AR 11/19 | A3253 | Generator Building -schedule and details_IFA Client review | 12 |  |  |  |  | A3252
AR 11/19 | A3254 | Generator Building -schedule and details_IFC | 2 |  |  |  |  | A3253
AR 11/19 | A3260 | Structural General Notes Sheet 1/2_IFR | 4 |  |  |  |  | A3980
AR 11/19 | A3261 | Structural General Notes Sheet 1/2_IFR Client review | 12 |  |  |  |  | A3260
AR 11/19 | A3262 | Structural General Notes Sheet 1/2_IFA | 3 |  |  |  |  | A3261
AR 11/19 | A3263 | Structural General Notes Sheet 1/2_IFA Client review | 12 |  |  |  |  | A3262
AR 11/19 | A3264 | Structural General Notes Sheet 1/2_IFC | 2 |  |  |  |  | A3263
AR 11/19 | A3270 | Structural General Notes Sheet 2/2_IFR | 4 |  |  |  |  | A3260
AR 11/19 | A3271 | Structural General Notes Sheet 2/2_IFR Client review | 12 |  |  |  |  | A3270
AR 11/19 | A3272 | Structural General Notes Sheet 2/2_IFA | 3 |  |  |  |  | A3271
AR 11/19 | A3273 | Structural General Notes Sheet 2/2_IFA Client review | 12 |  |  |  |  | A3272
AR 11/19 | A3274 | Structural General Notes Sheet 2/2_IFC | 2 |  |  |  |  | A3273
AR 11/19 | A3280 | Sewer Pump Station Foundation Layout and details sheet 1_IFR | 3 |  |  |  |  | A3090
AR 11/19 | A3281 | Sewer Pump Station Foundation Layout and details sheet 1_IFR Client review | 12 |  |  |  |  | A3280
AR 11/19 | A3282 | Sewer Pump Station Foundation Layout and details sheet 1_IFA | 3 |  |  |  |  | A3281
AR 11/19 | A3283 | Sewer Pump Station Foundation Layout and details sheet 1_IFA Client review | 12 |  |  |  |  | A3282
AR 11/19 | A3284 | Sewer Pump Station Foundation Layout and details sheet 1_IFC | 3 |  |  |  |  | A3283, A5045
AR 11/19 | A3290 | Sewer Pump Station Foundation Layout and details sheet 2_IFR | 3 |  |  |  |  | A3090, A3280
AR 11/19 | A3291 | Sewer Pump Station Foundation Layout and details sheet 2_IFR Client review | 12 |  |  |  |  | A3290
AR 11/19 | A3292 | Sewer Pump Station Foundation Layout and details sheet 2_IFA | 3 |  |  |  |  | A3291
AR 11/19 | A3293 | Sewer Pump Station Foundation Layout and details sheet 2_IFA Client review | 12 |  |  |  |  | A3292
AR 11/19 | A3294 | Sewer Pump Station Foundation Layout and details sheet 2_IFC | 3 |  |  |  |  | A3293, A5045
AR 11/19 | A3300 | Sewer Pump Station Foundation Layout and details sheet 3_IFR | 3 |  |  |  |  | A3090, A3290
AR 11/19 | A3301 | Sewer Pump Station Foundation Layout and details sheet 3_IFR Client review | 12 |  |  |  |  | A3300
AR 11/19 | A3302 | Sewer Pump Station Foundation Layout and details sheet 3_IFA | 3 |  |  |  |  | A3301
AR 11/19 | A3303 | Sewer Pump Station Foundation Layout and details sheet 3_IFA Client review | 12 |  |  |  |  | A3302
AR 11/19 | A3304 | Sewer Pump Station Foundation Layout and details sheet 3_IFC | 3 |  |  |  |  | A3303, A5045
AR 11/19 | A3310 | Sewer Pump Station Foundation Layout and details sheet 4_IFR | 3 |  |  |  |  | A3090, A3300
AR 11/19 | A3311 | Sewer Pump Station Foundation Layout and details sheet 4_IFR Client review | 12 |  |  |  |  | A3310
AR 11/19 | A3312 | Sewer Pump Station Foundation Layout and details sheet 4_IFA | 3 |  |  |  |  | A3311
AR 11/19 | A3313 | Sewer Pump Station Foundation Layout and details sheet 4_IFA Client review | 12 |  |  |  |  | A3312
AR 11/19 | A3314 | Sewer Pump Station Foundation Layout and details sheet 4_IFC | 3 |  |  |  |  | A3313, A5045
AR 11/19 | A3320 | Electrical and Control Building Foundation, columns slab Layout_IFR | 3 |  |  |  |  | A3100, A3943
AR 11/19 | A3321 | Electrical and Control Building Foundation, columns slab Layout_IFR Client review | 12 |  |  |  |  | A3320
AR 11/19 | A3322 | Electrical and Control Building Foundation, columns slab Layout_IFA | 2 |  |  |  |  | A3321
AR 11/19 | A3323 | Electrical and Control Building Foundation, columns slab Layout_IFA Client review | 12 |  |  |  |  | A3322
AR 11/19 | A3324 | Electrical and Control Building Foundation, columns slab Layout_IFC | 2 |  |  |  |  | A3323
AR 11/19 | A3330 | Electrical and Control Building Structural details_IFR | 3 |  |  |  |  | A3100
AR 11/19 | A3331 | Electrical and Control Building Structural details_IFR Client comment | 12 |  |  |  |  | A3330
AR 11/19 | A3332 | Electrical and Control Building Structural details_IFA | 2 |  |  |  |  | A3331
AR 11/19 | A3333 | Electrical and Control Building Structural details_IFA Client comment | 12 |  |  |  |  | A3332
AR 11/19 | A3334 | Electrical and Control Building Structural details_IFC | 2 |  |  |  |  | A3333
AR 11/19 | A3340 | Electrical and Control Building Steel Roofing Layout and details_IFR | 3 |  |  |  |  | A3100
AR 11/19 | A3341 | Electrical and Control Building Steel Roofing Layout and details_IFR Client review | 12 |  |  |  |  | A3340
AR 11/19 | A3342 | Electrical and Control Building Steel Roofing Layout and details_IFA | 2 |  |  |  |  | A3341
AR 11/19 | A3343 | Electrical and Control Building Steel Roofing Layout and details_IFA Client review | 12 |  |  |  |  | A3342
AR 11/19 | A3344 | Electrical and Control Building Steel Roofing Layout and details_IFC | 2 |  |  |  |  | A3343
AR 11/19 | A3350 | Sec Interface Building Foundation, columns slab Layout_IFR | 3 |  |  |  |  | A3110, A3943
AR 11/19 | A3351 | Sec Interface Building Foundation, columns slab Layout_IFR Client review | 12 |  |  |  |  | A3350
AR 11/19 | A3352 | Sec Interface Building Foundation, columns slab Layout_IFA | 3 |  |  |  |  | A3351
AR 11/19 | A3353 | Sec Interface Building Foundation, columns slab Layout_IFA Client review | 12 |  |  |  |  | A3352
AR 11/19 | A3354 | Sec Interface Building Foundation, columns slab Layout_IFC | 3 |  |  |  |  | A3353
AR 11/19 | A3360 | Sec Interface Building Building Structural details_IFR | 3 |  |  |  |  | A3110, A3350
AR 11/19 | A3361 | Sec Interface Building Building Structural details_IFR Client review | 12 |  |  |  |  | A3360
AR 11/19 | A3362 | Sec Interface Building Building Structural details_IFA | 2 |  |  |  |  | A3361
AR 11/19 | A3363 | Sec Interface Building Building Structural details_IFA Client review | 12 |  |  |  |  | A3362
AR 11/19 | A3364 | Sec Interface Building Building Structural details_IFC | 2 |  |  |  |  | A3363
AR 11/19 | A3370 | Sec Interface Building Building Steel Roofing Layout and details_IFR | 3 |  |  |  |  | A3110
AR 11/19 | A3371 | Sec Interface Building Building Steel Roofing Layout and details_IFR Client erview | 12 |  |  |  |  | A3370
AR 11/19 | A3372 | Sec Interface Building Building Steel Roofing Layout and details_IFA | 3 |  |  |  |  | A3371
AR 11/19 | A3373 | Sec Interface Building Building Steel Roofing Layout and details_IFA Client review | 12 |  |  |  |  | A3372
AR 11/19 | A3374 | Sec Interface Building Building Steel Roofing Layout and details_IFC | 3 |  |  |  |  | A3373
AR 11/19 | A3380 | Generator Building Foundation, columns slab Layout_IFR | 3 |  |  |  |  | A3120
AR 11/19 | A3381 | Generator Building Foundation, columns slab Layout_IFR Client review | 12 |  |  |  |  | A3380
AR 11/19 | A3382 | Generator Building Foundation, columns slab Layout_IFA | 2 |  |  |  |  | A3381
AR 11/19 | A3383 | Generator Building Foundation, columns slab Layout_IFA Client review | 12 |  |  |  |  | A3382
AR 11/19 | A3384 | Generator Building Foundation, columns slab Layout_IFC | 2 |  |  |  |  | A3383, A5045
AR 11/19 | A3390 | Generator Building Structural details_IFR | 3 |  |  |  |  | A3120, A3380
AR 11/19 | A3391 | Generator Building Structural details_IFR Client review | 12 |  |  |  |  | A3390
AR 11/19 | A3392 | Generator Building Structural details_IFA | 2 |  |  |  |  | A3391
AR 11/19 | A3393 | Generator Building Structural details_IFA Client review | 12 |  |  |  |  | A3392
AR 11/19 | A3394 | Generator Building Structural details_IFC | 2 |  |  |  |  | A3393, A5045
AR 11/19 | A3400 | Generator Building Steel Roofing Layout and details_IFR | 3 |  |  |  |  | A3120, A3390
AR 11/19 | A3401 | Generator Building Steel Roofing Layout and details_IFR Client review | 12 |  |  |  |  | A3400
AR 11/19 | A3402 | Generator Building Steel Roofing Layout and details_IFA | 2 |  |  |  |  | A3401
AR 11/19 | A3403 | Generator Building Steel Roofing Layout and details_IFA Client review | 12 |  |  |  |  | A3402
AR 11/19 | A3404 | Generator Building Steel Roofing Layout and details_IFC | 2 |  |  |  |  | A3403, A5045
AR 11/19 | A3410 | Flow Meter Chamber -Formwork and reinforcement_IFR | 3 |  |  |  |  | A3130
AR 11/19 | A3411 | Flow Meter Chamber -Formwork and reinforcement_IFR Client review | 12 |  |  |  |  | A3410
AR 11/19 | A3412 | Flow Meter Chamber -Formwork and reinforcement_IFA | 2 |  |  |  |  | A3411
AR 11/19 | A3413 | Flow Meter Chamber -Formwork and reinforcement_IFA Client review | 12 |  |  |  |  | A3412
AR 11/19 | A3414 | Flow Meter Chamber -Formwork and reinforcement_IFC | 2 |  |  |  |  | A3413
AR 11/19 | A3420 | Air Release Chamber -Formwork and reinforcement_IFR | 4 |  |  |  |  | A3140
AR 11/19 | A3421 | Air Release Chamber -Formwork and reinforcement_IFR Client review | 12 |  |  |  |  | A3420
AR 11/19 | A3422 | Air Release Chamber -Formwork and reinforcement_IFA | 3 |  |  |  |  | A3421
AR 11/19 | A3423 | Air Release Chamber -Formwork and reinforcement_IFA Client review | 12 |  |  |  |  | A3422
AR 11/19 | A3424 | Air Release Chamber -Formwork and reinforcement_IFC | 2 |  |  |  |  | A3423
AR 11/19 | A3430 | Isolation Chamber - Formwork and reinforcement_IFR | 3 |  |  |  |  | A3150
AR 11/19 | A3431 | Isolation Chamber - Formwork and reinforcement_IFR Client review | 12 |  |  |  |  | A3430
AR 11/19 | A3432 | Isolation Chamber - Formwork and reinforcement_IFA | 2 |  |  |  |  | A3431
AR 11/19 | A3433 | Isolation Chamber - Formwork and reinforcement_IFA Client review | 12 |  |  |  |  | A3432
AR 11/19 | A3434 | Isolation Chamber - Formwork and reinforcement_IFC | 2 |  |  |  |  | A3433
AR 11/19 | A3440 | Washout Chamber-Formwork and reinforcement_IFR | 3 |  |  |  |  | A3160
AR 11/19 | A3441 | Washout Chamber-Formwork and reinforcement_IFR Client review | 12 |  |  |  |  | A3440
AR 11/19 | A3442 | Washout Chamber-Formwork and reinforcement_IFA | 2 |  |  |  |  | A3441
AR 11/19 | A3443 | Washout Chamber-Formwork and reinforcement_IFA Client review | 12 |  |  |  |  | A3442
AR 11/19 | A3444 | Washout Chamber-Formwork and reinforcement_IFC | 2 |  |  |  |  | A3443
AR 11/19 | A3450 | Civil works General arrangement drawing_IFR | 4 |  |  |  |  | A1530
AR 11/19 | A3451 | Civil works General arrangement drawing_IFR Client review | 12 |  |  |  |  | A3450
AR 11/19 | A3452 | Civil works General arrangement drawing_IFA | 3 |  |  |  |  | A3451
AR 11/19 | A3453 | Civil works General arrangement drawing_IFA Client review | 12 |  |  |  |  | A3452
AR 11/19 | A3454 | Civil works General arrangement drawing_IFC | 2 |  |  |  |  | A3453
AR 11/19 | A3460 | Site Grading & Paving Plan-New Pump Station_IFR | 3 |  |  |  |  | A1530, A3935, A3450, A3938
AR 11/19 | A3461 | Site Grading & Paving Plan-New Pump Station_IFR Client review | 12 |  |  |  |  | A3460
AR 11/19 | A3462 | Site Grading & Paving Plan-New Pump Station_IFA | 2 |  |  |  |  | A3461
AR 11/19 | A3463 | Site Grading & Paving Plan-New Pump Station_IFA Client review | 12 |  |  |  |  | A3462
AR 11/19 | A3464 | Site Grading & Paving Plan-New Pump Station_IFC | 2 |  |  |  |  | A3463
AR 11/19 | A3470 | Road grading and layout_IFR | 3 |  |  |  |  | A1530, A3460
AR 11/19 | A3471 | Road grading and layout_IFR Client review | 12 |  |  |  |  | A3470
AR 11/19 | A3472 | Road grading and layout_IFA | 2 |  |  |  |  | A3471
AR 11/19 | A3473 | Road grading and layout_IFA Client review | 12 |  |  |  |  | A3472
AR 11/19 | A3474 | Road grading and layout_IFC | 2 |  |  |  |  | A3473
AR 11/19 | A3480 | Road Cross Section Drawing_IFR | 3 |  |  |  |  | A3470
AR 11/19 | A3481 | Road Cross Section Drawing_IFR Client comment | 12 |  |  |  |  | A3480
AR 11/19 | A3482 | Road Cross Section Drawing_IFA | 2 |  |  |  |  | A3481
AR 11/19 | A3483 | Road Cross Section Drawing_IFA Client comment | 12 |  |  |  |  | A3482
AR 11/19 | A3484 | Road Cross Section Drawing_IFC | 2 |  |  |  |  | A3483
AR 11/19 | A3490 | Strom Water Layout_IFR | 3 |  |  |  |  | A3450, A3480
AR 11/19 | A3491 | Strom Water Layout_IFR Client review | 12 |  |  |  |  | A3490
AR 11/19 | A3492 | Strom Water Layout_IFA | 2 |  |  |  |  | A3491
AR 11/19 | A3493 | Strom Water Layout_IFA Client review | 12 |  |  |  |  | A3492
AR 11/19 | A3494 | Strom Water Layout_IFC | 2 |  |  |  |  | A3493
AR 11/19 | A3500 | PW & Sewer network layout_IFR | 3 |  |  |  |  | A3450, A3490
AR 11/19 | A3501 | PW & Sewer network layout_IFR Client review | 12 |  |  |  |  | A3500
AR 11/19 | A3502 | PW & Sewer network layout_IFA | 2 |  |  |  |  | A3501
AR 11/19 | A3503 | PW & Sewer network layout_IFA Client review | 12 |  |  |  |  | A3502
AR 11/19 | A3504 | PW & Sewer network layout_IFC | 2 |  |  |  |  | A3503
AR 11/19 | A3513 | Fence layout and details_IFR | 3 |  |  |  |  | A3450
AR 11/19 | A3514 | Fence layout and details_IFR Client review | 12 |  |  |  |  | A3513
AR 11/19 | A3515 | Fence layout and details_IFA | 2 |  |  |  |  | A3514
AR 11/19 | A3516 | Fence layout and details_IFA Client review | 12 |  |  |  |  | A3515
AR 11/19 | A3517 | Fence layout and details_IFC | 2 |  |  |  |  | A3516
AR 11/19 | A3520 | Miscellaneous Civil Works details_IFR | 3 |  |  |  |  | A3450
AR 11/19 | A3521 | Miscellaneous Civil Works details_IFR Client review | 12 |  |  |  |  | A3520
AR 11/19 | A3522 | Miscellaneous Civil Works details_IFA | 2 |  |  |  |  | A3521
AR 11/19 | A3523 | Miscellaneous Civil Works details_IFA Client review | 12 |  |  |  |  | A3522
AR 11/19 | A3524 | Miscellaneous Civil Works details_IFC | 2 |  |  |  |  | A3523
AR 11/19 | A4930 | Force-main Trench Details Standard Drawings_IFR | 4 |  |  |  |  | A4501, A4150, A3550, A3530
AR 11/19 | A4931 | Force-main Trench Details Standard Drawings_IFR Client review | 12 |  |  |  |  | A4930
AR 11/19 | A4932 | Force-main Trench Details Standard Drawings_IFA | 3 |  |  |  |  | A4931
AR 11/19 | A4933 | Force-main Trench Details Standard Drawings_IFA Client review | 12 |  |  |  |  | A4932
AR 11/19 | A4934 | Force-main Trench Details Standard Drawings_IFC | 2 |  |  |  |  | A4933
AR 11/19 | A8001 | Manholes and connexions drawing_IFR | 3 |  |  |  |  | A3450
AR 11/19 | A8002 | Manholes and connexions drawing_IFR Client review | 12 |  |  |  |  | A8001
AR 11/19 | A8003 | Manholes and connexions drawing_IFA | 2 |  |  |  |  | A8002
AR 11/19 | A8004 | Manholes and connexions drawing_IFA Client review | 12 |  |  |  |  | A8003
AR 11/19 | A8005 | Manholes and connexions drawing_IFC | 2 |  |  |  |  | A8004
AR 11/19 | A8010 | Fence and Gates details_IFR | 3 |  |  |  |  | A3450
AR 11/19 | A8011 | Fence and Gates details_IFR Client review | 12 |  |  |  |  | A8010
AR 11/19 | A8012 | Fence and Gates details_IFA | 2 |  |  |  |  | A8011
AR 11/19 | A8013 | Fence and Gates details_IFA Client review | 12 |  |  |  |  | A8012
AR 11/19 | A8014 | Fence and Gates details_IFC | 2 |  |  |  |  | A8013
AR 11/19 | A3550 | Forcemain 900 Plot plan_IFR | 4 |  |  |  |  | A3935
AR 11/19 | A3551 | Forcemain 900 Plot plan_IFR Client review | 12 |  |  |  |  | A3550
AR 11/19 | A3552 | Forcemain 900 Plot plan_IFA | 3 |  |  |  |  | A3551
AR 11/19 | A3553 | Forcemain 900 Plot plan_IFA Client review | 12 |  |  |  |  | A3552
AR 11/19 | A3554 | Forcemain 900 Plot plan_IFC | 2 |  |  |  |  | A3553
AR 11/19 | A4150 | Forcemain 900 Alignement Sheet 1/9_IFR | 6 |  |  |  |  | A3550
AR 11/19 | A4151 | Forcemain 900 Alignement Sheet 1/9_IFR Client review | 12 |  |  |  |  | A4150
AR 11/19 | A4152 | Forcemain 900 Alignement Sheet 1/9_IFA | 5 |  |  |  |  | A4150, A4151
AR 11/19 | A4153 | Forcemain 900 Alignement Sheet 1/9_IFA Client review | 12 |  |  |  |  | A4152
AR 11/19 | A4154 | Forcemain 900 Alignement Sheet 1/9_IFC | 3 |  |  |  |  | A4152, A4153
AR 11/19 | A4270 | Forcemain 900 Alignement Sheet 2/9_IFR | 6 |  |  |  |  | A4150
AR 11/19 | A4271 | Forcemain 900 Alignement Sheet 2/9_IFR Client review | 12 |  |  |  |  | A4270
AR 11/19 | A4280 | Forcemain 900 Alignement Sheet 2/9_IFA | 5 |  |  |  |  | A4270, A4271
AR 11/19 | A4281 | Forcemain 900 Alignement Sheet 2/9_IFA Client review | 12 |  |  |  |  | A4280
AR 11/19 | A4290 | Forcemain 900 Alignement Sheet 2/9_IFC | 3 |  |  |  |  | A4280, A4281
AR 11/19 | A4300 | Forcemain 900 Alignement Sheet 3/9_IFR | 6 |  |  |  |  | A4270
AR 11/19 | A4301 | Forcemain 900 Alignement Sheet 3/9_IFR Client review | 12 |  |  |  |  | A4300
AR 11/19 | A4310 | Forcemain 900 Alignement Sheet 3/9_IFA | 5 |  |  |  |  | A4300, A4301
AR 11/19 | A4311 | Forcemain 900 Alignement Sheet 3/9_IFA Client review | 12 |  |  |  |  | A4310
AR 11/19 | A4320 | Forcemain 900 Alignement Sheet 3/9_IFC | 3 |  |  |  |  | A4310, A4311
AR 11/19 | A4330 | Forcemain 900 Alignement Sheet 4/9_IFR | 6 |  |  |  |  | A4300
AR 11/19 | A4331 | Forcemain 900 Alignement Sheet 4/9_IFR Client review | 12 |  |  |  |  | A4330
AR 11/19 | A4340 | Forcemain 900 Alignement Sheet 4/9_IFA | 5 |  |  |  |  | A4330, A4331
AR 11/19 | A4341 | Forcemain 900 Alignement Sheet 4/9_IFA Client review | 12 |  |  |  |  | A4340
AR 11/19 | A4350 | Forcemain 900 Alignement Sheet 4/9_IFC | 3 |  |  |  |  | A4340, A4341
AR 11/19 | A4360 | Forcemain 900 Alignement Sheet 5/9_IFR | 6 |  |  |  |  | A4330
AR 11/19 | A4361 | Forcemain 900 Alignement Sheet 5/9_IFR Client review | 12 |  |  |  |  | A4360
AR 11/19 | A4370 | Forcemain 900 Alignement Sheet 5/9_IFA | 5 |  |  |  |  | A4360, A4361
AR 11/19 | A4371 | Forcemain 900 Alignement Sheet 5/9_IFA Client review | 12 |  |  |  |  | A4370
AR 11/19 | A4380 | Forcemain 900 Alignement Sheet 5/9_IFC | 3 |  |  |  |  | A4370, A4371
AR 11/19 | A4390 | Forcemain 900 Alignement Sheet 6/9_IFR | 6 |  |  |  |  | A4360
AR 11/19 | A4391 | Forcemain 900 Alignement Sheet 6/9_IFR Client review | 12 |  |  |  |  | A4390
AR 11/19 | A4400 | Forcemain 900 Alignement Sheet 6/9_IFA | 5 |  |  |  |  | A4390, A4391
AR 11/19 | A4401 | Forcemain 900 Alignement Sheet 6/9_IFA Client review | 12 |  |  |  |  | A4400
AR 11/19 | A4410 | Forcemain 900 Alignement Sheet 6/9_IFC | 3 |  |  |  |  | A4400, A4401
AR 11/19 | A4420 | Forcemain 900 Alignement Sheet 7/9_IFR | 6 |  |  |  |  | A4390
AR 11/19 | A4421 | Forcemain 900 Alignement Sheet 7/9_IFR Client review | 12 |  |  |  |  | A4420
AR 11/19 | A4430 | Forcemain 900 Alignement Sheet 7/9_IFA | 5 |  |  |  |  | A4420, A4421
AR 11/19 | A4431 | Forcemain 900 Alignement Sheet 7/9_IFA Client review | 12 |  |  |  |  | A4430
AR 11/19 | A4440 | Forcemain 900 Alignement Sheet 7/9_IFC | 3 |  |  |  |  | A4430, A4431
AR 11/19 | A4450 | Forcemain 900 Alignement Sheet 8/9_IFR | 6 |  |  |  |  | A4420
AR 11/19 | A4451 | Forcemain 900 Alignement Sheet 8/9_IFR Client review | 12 |  |  |  |  | A4450
AR 11/19 | A4460 | Forcemain 900 Alignement Sheet 8/9_IFA | 5 |  |  |  |  | A4450, A4451
AR 11/19 | A4461 | Forcemain 900 Alignement Sheet 8/9_IFA Client review | 12 |  |  |  |  | A4460
AR 11/19 | A4470 | Forcemain 900 Alignement Sheet 8/9_IFC | 3 |  |  |  |  | A4460, A4461
AR 11/19 | A4480 | Forcemain 900 Alignement Sheet 9/9_IFR | 6 |  |  |  |  | A4450
AR 11/19 | A4481 | Forcemain 900 Alignement Sheet 9/9_IFR Client review | 12 |  |  |  |  | A4480
AR 11/19 | A4490 | Forcemain 900 Alignement Sheet 9/9_IFA | 5 |  |  |  |  | A4480, A4481
AR 11/19 | A4491 | Forcemain 900 Alignement Sheet 9/9_IFA Client review | 12 |  |  |  |  | A4490
AR 11/19 | A4500 | Forcemain 900 Alignement Sheet 9/9_IFC | 3 |  |  |  |  | A4490, A4491
AR 11/19 | A3530 | Forcemain 1200 Plot plan_IFR | 4 |  |  |  |  | A3938
AR 11/19 | A3531 | Forcemain 1200 Plot plan_IFR Client review | 12 |  |  |  |  | A3530
AR 11/19 | A3532 | Forcemain 1200 Plot plan_IFA | 3 |  |  |  |  | A3531
AR 11/19 | A3533 | Forcemain 1200 Plot plan_IFA Client review | 12 |  |  |  |  | A3532
AR 11/19 | A3534 | Forcemain 1200 Plot plan_IFC | 2 |  |  |  |  | A3533
AR 11/19 | A4501 | Forcemain 1200 Alignement Sheet 1/15_IFR | 6 |  |  |  |  | A3530
AR 11/19 | A4502 | Forcemain 1200 Alignement Sheet 1/15_IFR Client review | 12 |  |  |  |  | A4501
AR 11/19 | A4503 | Forcemain 1200 Alignement Sheet 1/15_IFA | 5 |  |  |  |  | A4502
AR 11/19 | A4504 | Forcemain 1200 Alignement Sheet 1/15_IFA Client review | 12 |  |  |  |  | A4503
AR 11/19 | A4505 | Forcemain 1200 Alignement Sheet 1/15_IFC | 3 |  |  |  |  | A4504
AR 11/19 | A4510 | Forcemain 1200 Alignement Sheet 2/15_IFR | 6 |  |  |  |  | A4501
AR 11/19 | A4511 | Forcemain 1200 Alignement Sheet 2/15_IFR Client review | 12 |  |  |  |  | A4510
AR 11/19 | A4520 | Forcemain 1200 Alignement Sheet 2/15_IFA | 5 |  |  |  |  | A4511
AR 11/19 | A4521 | Forcemain 1200 Alignement Sheet 2/15_IFA Client review | 12 |  |  |  |  | A4520
AR 11/19 | A4530 | Forcemain 1200 Alignement Sheet 2/15_IFC | 3 |  |  |  |  | A4521
AR 11/19 | A4540 | Forcemain 1200 Alignement Sheet 3/15_IFR | 6 |  |  |  |  | A4510
AR 11/19 | A4541 | Forcemain 1200 Alignement Sheet 3/15_IFR Client review | 12 |  |  |  |  | A4540
AR 11/19 | A4550 | Forcemain 1200 Alignement Sheet 3/15_IFA | 5 |  |  |  |  | A4541
AR 11/19 | A4551 | Forcemain 1200 Alignement Sheet 3/15_IFA Client review | 12 |  |  |  |  | A4550
AR 11/19 | A4560 | Forcemain 1200 Alignement Sheet 3/15_IFC | 3 |  |  |  |  | A4551
AR 11/19 | A4570 | Forcemain 1200 Alignement Sheet 4/15_IFR | 6 |  |  |  |  | A4540
AR 11/19 | A4571 | Forcemain 1200 Alignement Sheet 4/15_IFR Client review | 12 |  |  |  |  | A4570
AR 11/19 | A4580 | Forcemain 1200 Alignement Sheet 4/15_IFA | 5 |  |  |  |  | A4571
AR 11/19 | A4581 | Forcemain 1200 Alignement Sheet 4/15_IFA Client review | 12 |  |  |  |  | A4580
AR 11/19 | A4590 | Forcemain 1200 Alignement Sheet 4/15_IFC | 3 |  |  |  |  | A4581
AR 11/19 | A4600 | Forcemain 1200 Alignement Sheet 5/15_IFR | 6 |  |  |  |  | A4570
AR 11/19 | A4601 | Forcemain 1200 Alignement Sheet 5/15_IFR Client review | 12 |  |  |  |  | A4600
AR 11/19 | A4610 | Forcemain 1200 Alignement Sheet 5/15_IFA | 5 |  |  |  |  | A4601
AR 11/19 | A4611 | Forcemain 1200 Alignement Sheet 5/15_IFA Client review | 12 |  |  |  |  | A4610
AR 11/19 | A4620 | Forcemain 1200 Alignement Sheet 5/15_IFC | 3 |  |  |  |  | A4611
AR 11/19 | A4630 | Forcemain 1200 Alignement Sheet 6/15_IFR | 6 |  |  |  |  | A4600
AR 11/19 | A4631 | Forcemain 1200 Alignement Sheet 6/15_IFR Client review | 12 |  |  |  |  | A4630
AR 11/19 | A4640 | Forcemain 1200 Alignement Sheet 6/15_IFA | 5 |  |  |  |  | A4631
AR 11/19 | A4641 | Forcemain 1200 Alignement Sheet 6/15_IFA Client review | 12 |  |  |  |  | A4640
AR 11/19 | A4650 | Forcemain 1200 Alignement Sheet 6/15_IFC | 3 |  |  |  |  | A4641
AR 11/19 | A4660 | Forcemain 1200 Alignement Sheet 7/15_IFR | 6 |  |  |  |  | A4630
AR 11/19 | A4661 | Forcemain 1200 Alignement Sheet 7/15_IFR Client review | 12 |  |  |  |  | A4660
AR 11/19 | A4670 | Forcemain 1200 Alignement Sheet 7/15_IFA | 5 |  |  |  |  | A4661
AR 11/19 | A4671 | Forcemain 1200 Alignement Sheet 7/15_IFA Client review | 12 |  |  |  |  | A4670
AR 11/19 | A4680 | Forcemain 1200 Alignement Sheet 7/15_IFC | 3 |  |  |  |  | A4671
AR 11/19 | A4690 | Forcemain 1200 Alignement Sheet 8/15_IFR | 6 |  |  |  |  | A4660
AR 11/19 | A4691 | Forcemain 1200 Alignement Sheet 8/15_IFR Client review | 12 |  |  |  |  | A4690
AR 11/19 | A4700 | Forcemain 1200 Alignement Sheet 8/15_IFA | 5 |  |  |  |  | A4691
AR 11/19 | A4701 | Forcemain 1200 Alignement Sheet 8/15_IFA Client review | 12 |  |  |  |  | A4700
AR 11/19 | A4710 | Forcemain 1200 Alignement Sheet 8/15_IFC | 3 |  |  |  |  | A4701
AR 11/19 | A4720 | Forcemain 1200 Alignement Sheet 9/15_IFR | 6 |  |  |  |  | A4690
AR 11/19 | A4721 | Forcemain 1200 Alignement Sheet 9/15_IFR Client review | 12 |  |  |  |  | A4720
AR 11/19 | A4730 | Forcemain 1200 Alignement Sheet 9/15_IFA | 5 |  |  |  |  | A4721
AR 11/19 | A4731 | Forcemain 1200 Alignement Sheet 9/15_IFA Client review | 12 |  |  |  |  | A4730
AR 11/19 | A4740 | Forcemain 1200 Alignement Sheet 9/15_IFC | 3 |  |  |  |  | A4731
AR 11/19 | A4750 | Forcemain 1200 Alignement Sheet 10/15_IFR | 6 |  |  |  |  | A4720
AR 11/19 | A4751 | Forcemain 1200 Alignement Sheet 10/15_IFR Client review | 12 |  |  |  |  | A4750
AR 11/19 | A4760 | Forcemain 1200 Alignement Sheet 10/15_IFA | 5 |  |  |  |  | A4751
AR 11/19 | A4761 | Forcemain 1200 Alignement Sheet 10/15_IFA Client review | 12 |  |  |  |  | A4760
AR 11/19 | A4770 | Forcemain 1200 Alignement Sheet 10/15_IFC | 3 |  |  |  |  | A4761
AR 11/19 | A4780 | Forcemain 1200 Alignement Sheet 11/15_IFR | 6 |  |  |  |  | A4750
AR 11/19 | A4781 | Forcemain 1200 Alignement Sheet 11/15_IFR Client review | 12 |  |  |  |  | A4780
AR 11/19 | A4790 | Forcemain 1200 Alignement Sheet 11/15_IFA | 5 |  |  |  |  | A4781
AR 11/19 | A4791 | Forcemain 1200 Alignement Sheet 11/15_IFA Client review | 12 |  |  |  |  | A4790
AR 11/19 | A4800 | Forcemain 1200 Alignement Sheet 11/15_IFC | 3 |  |  |  |  | A4791
AR 11/19 | A4810 | Forcemain 1200 Alignement Sheet 12/15_IFR | 6 |  |  |  |  | A4780
AR 11/19 | A4811 | Forcemain 1200 Alignement Sheet 12/15_IFR Client review | 12 |  |  |  |  | A4810
AR 11/19 | A4820 | Forcemain 1200 Alignement Sheet 12/15_IFA | 5 |  |  |  |  | A4811
AR 11/19 | A4821 | Forcemain 1200 Alignement Sheet 12/15_IFA Client review | 12 |  |  |  |  | A4820
AR 11/19 | A4830 | Forcemain 1200 Alignement Sheet 12/15_IFC | 3 |  |  |  |  | A4821
AR 11/19 | A4840 | Forcemain 1200 Alignement Sheet 13/15_IFR | 6 |  |  |  |  | A4810
AR 11/19 | A4841 | Forcemain 1200 Alignement Sheet 13/15_IFR Client review | 12 |  |  |  |  | A4840
AR 11/19 | A4850 | Forcemain 1200 Alignement Sheet 13/15_IFA | 5 |  |  |  |  | A4841
AR 11/19 | A4851 | Forcemain 1200 Alignement Sheet 13/15_IFA Client review | 12 |  |  |  |  | A4850
AR 11/19 | A4860 | Forcemain 1200 Alignement Sheet 13/15_IFC | 3 |  |  |  |  | A4851
AR 11/19 | A4870 | Forcemain 1200 Alignement Sheet 14/15_IFR | 6 |  |  |  |  | A4840
AR 11/19 | A4871 | Forcemain 1200 Alignement Sheet 14/15_IFR Client review | 12 |  |  |  |  | A4870
AR 11/19 | A4880 | Forcemain 1200 Alignement Sheet 14/15_IFA | 5 |  |  |  |  | A4871
AR 11/19 | A4881 | Forcemain 1200 Alignement Sheet 14/15_IFA Client review | 12 |  |  |  |  | A4880
AR 11/19 | A4890 | Forcemain 1200 Alignement Sheet 14/15_IFC | 3 |  |  |  |  | A4881
AR 11/19 | A4900 | Forcemain 1200 Alignement Sheet 15/15_IFR | 6 |  |  |  |  | A4870
AR 11/19 | A4901 | Forcemain 1200 Alignement Sheet 15/15_IFR Client review | 12 |  |  |  |  | A4900
AR 11/19 | A4910 | Forcemain 1200 Alignement Sheet 15/15_IFA | 5 |  |  |  |  | A4901
AR 11/19 | A4911 | Forcemain 1200 Alignement Sheet 15/15_IFA Client review | 12 |  |  |  |  | A4910
AR 11/19 | A4920 | Forcemain 1200 Alignement Sheet 15/15_IFC | 3 |  |  |  |  | A4911
AR 11/19 | A3630 | Force-main Material Specification_IFR | 3 |  |  |  |  | A3580
AR 11/19 | A3631 | Force-main Material Specification_IFR Client review | 12 |  |  |  |  | A3630
AR 11/19 | A3632 | Force-main Material Specification_IFA | 2 |  |  |  |  | A3631
AR 11/19 | A3633 | Force-main Material Specification_IFA Client review | 12 |  |  |  |  | A3632
AR 11/19 | A3634 | Force-main Material Specification_IFC | 2 |  |  |  |  | A3633
AR 11/19 | A3650 | Force-main Material Requisition_IFU | 3 |  |  |  |  | A3580, A3632
AR 11/19 | A3660 | Sanitary Wastewater Pump Specification_IFR | 4 |  |  |  |  | A3620
AR 11/19 | A3661 | Sanitary Wastewater Pump Specification_IFR Client review | 12 |  |  |  |  | A3660
AR 11/19 | A3662 | Sanitary Wastewater Pump Specification_IFA | 3 |  |  |  |  | A3661, A3980
AR 11/19 | A3663 | Sanitary Wastewater Pump Specification_IFA Client review | 12 |  |  |  |  | A3662
AR 11/19 | A3664 | Sanitary Wastewater Pump Specification_IFC | 2 |  |  |  |  | A3663
AR 11/19 | A3670 | Sanitary Wastewater Pump Data Sheet_IFR | 4 |  |  |  |  | A3660
AR 11/19 | A3671 | Sanitary Wastewater Pump Data Sheet_IFR Client review | 12 |  |  |  |  | A3670
AR 11/19 | A3672 | Sanitary Wastewater Pump Data Sheet_IFA | 3 |  |  |  |  | A3671, A3662
AR 11/19 | A3673 | Sanitary Wastewater Pump Data Sheet_IFA Client review | 12 |  |  |  |  | A3672
AR 11/19 | A3674 | Sanitary Wastewater Pump Data Sheet_IFC | 2 |  |  |  |  | A3673
AR 11/19 | A3680 | Sanitary Wastewater Pump Material Requisition_IFU | 4 |  |  |  |  | A3670
AR 11/19 | A3700 | Electrical Overhead Crane Data Sheet_IFR | 4 |  |  |  |  | A3670
AR 11/19 | A3701 | Electrical Overhead Crane Data Sheet_IFR Client review | 12 |  |  |  |  | A3700
AR 11/19 | A3702 | Electrical Overhead Crane Data Sheet_IFA | 3 |  |  |  |  | A3701
AR 11/19 | A3703 | Electrical Overhead Crane Data Sheet_IFA Client review | 12 |  |  |  |  | A3702
AR 11/19 | A3704 | Electrical Overhead Crane Data Sheet_IFC | 2 |  |  |  |  | A3703
AR 11/19 | A3710 | Electrical Overhead Crane Material Requisition_IFU | 3 |  |  |  |  | A3702
AR 11/19 | A1000 | Piping and Valve Material Specification_IFR | 4 |  |  |  |  | A3980
AR 11/19 | A1001 | Piping and Valve Material Specification_IFR Client review | 12 |  |  |  |  | A1000
AR 11/19 | A1002 | Piping and Valve Material Specification_IFA | 3 |  |  |  |  | A1001
AR 11/19 | A1003 | Piping and Valve Material Specification_IFA Client review | 12 |  |  |  |  | A1002
AR 11/19 | A1004 | Piping and Valve Material Specification_IFC | 2 |  |  |  |  | A1003
AR 11/19 | A1010 | Painting and Coating Specification_IFR | 3 |  |  |  |  | A1002
AR 11/19 | A1011 | Painting and Coating Specification_IFR Client review | 12 |  |  |  |  | A1010
AR 11/19 | A1012 | Painting and Coating Specification_IFA | 2 |  |  |  |  | A1011
AR 11/19 | A1013 | Painting and Coating Specification_IFA Client review | 12 |  |  |  |  | A1012
AR 11/19 | A1014 | Painting and Coating Specification_IFC | 2 |  |  |  |  | A1013
AR 11/19 | A1020 | Hydrotest Specification_IFR | 3 |  |  |  |  | A3600
AR 11/19 | A1021 | Hydrotest Specification_IFR Client review | 12 |  |  |  |  | A1020
AR 11/19 | A1022 | Hydrotest Specification_IFA | 2 |  |  |  |  | A1021
AR 11/19 | A1023 | Hydrotest Specification_IFA Client review | 12 |  |  |  |  | A1022
AR 11/19 | A1024 | Hydrotest Specification_IFC | 2 |  |  |  |  | A1023
AR 11/19 | A1030 | Valves Data Sheet_IFR | 3 |  |  |  |  | A3600, A1000
AR 11/19 | A1031 | Valves Data Sheet_IFR Client review | 12 |  |  |  |  | A1030
AR 11/19 | A1032 | Valves Data Sheet_IFA | 2 |  |  |  |  | A1031
AR 11/19 | A1033 | Valves Data Sheet_IFA Client review | 12 |  |  |  |  | A1032
AR 11/19 | A1034 | Valves Data Sheet_IFC | 2 |  |  |  |  | A1033
AR 11/19 | A1050 | Quick Connection Data Sheet_IFR | 3 |  |  |  |  | A3600
AR 11/19 | A1051 | Quick Connection Data Sheet_IFR Client review | 12 |  |  |  |  | A1050
AR 11/19 | A1052 | Quick Connection Data Sheet_IFA | 2 |  |  |  |  | A1051
AR 11/19 | A1053 | Quick Connection Data Sheet_IFA Client review | 12 |  |  |  |  | A1052
AR 11/19 | A1054 | Quick Connection Data Sheet_IFC | 2 |  |  |  |  | A1053
AR 11/19 | A1080 | Piping Material Requisition_IFU | 2 |  |  |  |  | A3600, A1650, A1510
AR 11/19 | A1082 | Odor System Specification_IFR | 2 |  |  |  |  | A1020
AR 11/19 | A1083 | Odor System Specification_IFR Client review | 12 |  |  |  |  | A1082
AR 11/19 | A1084 | Odor System Specification_IFA | 2 |  |  |  |  | A1083
AR 11/19 | A1085 | Odor System Specification_IFA Client review | 12 |  |  |  |  | A1084
AR 11/19 | A1086 | Odor System Specification_IFC | 2 |  |  |  |  | A1085
AR 11/19 | A1090 | Valves Material Requisition_IFU | 2 |  |  |  |  | A3600, A1650, A1032, A1500
AR 11/19 | A1100 | Quick Connection Material Requisition_IFU | 2 |  |  |  |  | A3600, A1052
AR 11/19 | A1152 | Penstocks Data Sheet_IFR | 3 |  |  |  |  | A3600, A1175
AR 11/19 | A1153 | Penstocks Data Sheet_IFR Client review | 12 |  |  |  |  | A1152
AR 11/19 | A1162 | Penstocks Data Sheet_IFA | 2 |  |  |  |  | A1153
AR 11/19 | A1163 | Penstocks Data Sheet_IFA Client review | 12 |  |  |  |  | A1162
AR 11/19 | A1172 | Penstocks Data Sheet_IFC | 2 |  |  |  |  | A1163
AR 11/19 | A1175 | Odor System Data Sheet_IFR | 2 |  |  |  |  | A3600
AR 11/19 | A1176 | Odor System Data Sheet_IFR Client review | 12 |  |  |  |  | A1175
AR 11/19 | A1177 | Odor System Data Sheet_IFA | 2 |  |  |  |  | A1176
AR 11/19 | A1178 | Odor System Data Sheet_IFA Client review | 12 |  |  |  |  | A1177
AR 11/19 | A1179 | Odor System Data Sheet_IFC | 2 |  |  |  |  | A1178
AR 11/19 | A1180 | Isolation Valve Data Sheet_IFR | 2 |  |  |  |  | A3600, A3580
AR 11/19 | A1181 | Isolation Valve Data Sheet_IFR Client review | 12 |  |  |  |  | A1180
AR 11/19 | A1182 | Isolation Valve Data Sheet_IFA | 2 |  |  |  |  | A1181
AR 11/19 | A1183 | Isolation Valve Data Sheet_IFA Client review | 12 |  |  |  |  | A1182
AR 11/19 | A1184 | Isolation Valve Data Sheet_IFC | 2 |  |  |  |  | A1183
AR 11/19 | A1190 | Air Release / Vacuum Release Valve Data Sheet_IFR | 3 |  |  |  |  | A3600, A3590
AR 11/19 | A1191 | Air Release / Vacuum Release Valve Data Sheet_IFR Client review | 12 |  |  |  |  | A1190
AR 11/19 | A1192 | Air Release / Vacuum Release Valve Data Sheet_IFA | 2 |  |  |  |  | A1191
AR 11/19 | A1193 | Air Release / Vacuum Release Valve Data Sheet_IFA Client review | 12 |  |  |  |  | A1192
AR 11/19 | A1194 | Air Release / Vacuum Release Valve Data Sheet_IFC | 2 |  |  |  |  | A1193
AR 11/19 | A1210 | Isolation Valve Material Requisition_IFU | 3 |  |  |  |  | A3600, A3580, A1182
AR 11/19 | A1220 | Air Release / Vacuum Release Valve Material Requisition_IFU | 3 |  |  |  |  | A3580, A3600, A1192
AR 11/19 | A1400 | Sump Pump Data Sheet_IFR | 3 |  |  |  |  | A3580, A1050
AR 11/19 | A1401 | Sump Pump Data Sheet_IFR Client review | 12 |  |  |  |  | A1400
AR 11/19 | A1402 | Sump Pump Data Sheet_IFA | 2 |  |  |  |  | A1401
AR 11/19 | A1403 | Sump Pump Data Sheet_IFA Client review | 12 |  |  |  |  | A1402
AR 11/19 | A1404 | Sump Pump Data Sheet_IFC | 2 |  |  |  |  | A1403
AR 11/19 | A1430 | Grinder / Macerator Data Sheet_IFR | 3 |  |  |  |  | A1030, A3980
AR 11/19 | A1431 | Grinder / Macerator Data Sheet_IFR client review | 12 |  |  |  |  | A1430
AR 11/19 | A1432 | Grinder / Macerator Data Sheet_IFA | 2 |  |  |  |  | A1431
AR 11/19 | A1433 | Grinder / Macerator Data Sheet_IFA Client review | 12 |  |  |  |  | A1432
AR 11/19 | A1434 | Grinder / Macerator Data Sheet_IFC | 2 |  |  |  |  | A1433
AR 11/19 | A1442 | Electrical Overhead Crane for Diesel Generator Data Sheet_IFR | 2 |  |  |  |  | A1430, A3980
AR 11/19 | A1443 | Electrical Overhead Crane for Diesel Generator Data Sheet_IFR Client review | 12 |  |  |  |  | A1442
AR 11/19 | A1444 | Electrical Overhead Crane for Diesel Generator Data Sheet_IFA | 2 |  |  |  |  | A1443
AR 11/19 | A1445 | Electrical Overhead Crane for Diesel Generator Data Sheet_IFA Client review | 12 |  |  |  |  | A1444
AR 11/19 | A1446 | Electrical Overhead Crane for Diesel Generator Data Sheet_IFC | 2 |  |  |  |  | A1445
AR 11/19 | A1450 | Sump Pump Material Requisition_IFU | 2 |  |  |  |  | A1402
AR 11/19 | A1480 | Grinder / Macerator Material Requisition_IFU | 2 |  |  |  |  | A1432
AR 11/19 | A1500 | Valve List_IFR | 5 |  |  |  |  | A3600
AR 11/19 | A1501 | Valve List_IFR Client review | 12 |  |  |  |  | A1500
AR 11/19 | A1502 | Valve List_IFA | 4 |  |  |  |  | A1501
AR 11/19 | A1503 | Valve List_IFA Client review | 12 |  |  |  |  | A1502
AR 11/19 | A1504 | Valve List_IFC | 3 |  |  |  |  | A1503
AR 11/19 | A1230 | Force-Main Buoyancy Calculation Note_IFR | 5 |  |  |  |  | A3630, A3600, A4501, A3530, A3550, A4150
AR 11/19 | A1231 | Force-Main Buoyancy Calculation Note_IFR Client review | 12 |  |  |  |  | A1230
AR 11/19 | A1232 | Force-Main Buoyancy Calculation Note_IFA | 4 |  |  |  |  | A1231
AR 11/19 | A1233 | Force-Main Buoyancy Calculation Note_IFA Client review | 12 |  |  |  |  | A1232
AR 11/19 | A1234 | Force-Main Buoyancy Calculation Note_IFC | 3 |  |  |  |  | A1233
AR 11/19 | A1242 | Pipeline Stress Analysis report_IFR | 8 |  |  |  |  | A4501, A3600, A4150
AR 11/19 | A1243 | Pipeline Stress Analysis report_IFR Client review | 12 |  |  |  |  | A1242
AR 11/19 | A1342 | Pipeline Stress Analysis report_IFA | 6 |  |  |  |  | A5045, A1243
AR 11/19 | A1343 | Pipeline Stress Analysis report_IFA Client review | 12 |  |  |  |  | A1342
AR 11/19 | A1352 | Pipeline Stress Analysis report_IFC | 4 |  |  |  |  | A1343
AR 11/19 | A1490 | Piping Stress Analysis PS 56-A_IFR | 8 |  |  |  |  | A3600, A1000, A4150, A4501, A3990
AR 11/19 | A1491 | Piping Stress Analysis PS 56-A_IFR Client review | 12 |  |  |  |  | A1490
AR 11/19 | A1492 | Piping Stress Analysis PS 56-A_IFA | 4 |  |  |  |  | A5045, A1491
AR 11/19 | A1493 | Piping Stress Analysis PS 56-A_IFA Client review | 12 |  |  |  |  | A1492
AR 11/19 | A1494 | Piping Stress Analysis PS 56-A_IFC | 3 |  |  |  |  | A1493
AR 11/19 | A1240 | DN 900 Force-main & fittings detailed MTO_IFU | 5 |  |  |  |  | A3550, A4150, A3630, A3600, A1270
AR 11/19 | A8020 | DN 1200 Force-main & fittings detailed MTO_IFU | 5 |  |  |  |  | A1270, A3530, A3600, A3630, A4501, A1240
AR 11/19 | A1510 | General Piping MTO_IFU | 4 |  |  |  |  | A1570
AR 11/19 | A1540 | Force-main Valves MTO_IFU | 3 |  |  |  |  | A3602, A3632
AR 11/19 | A1270 | Typical Force-main Crossings Drawings_IFR | 3 |  |  |  |  | A3530, A4501, A4150, A3550
AR 11/19 | A1271 | Typical Force-main Crossings Drawings_IFR Client review | 12 |  |  |  |  | A1270
AR 11/19 | A1272 | Typical Force-main Crossings Drawings_IFA | 2 |  |  |  |  | A1271
AR 11/19 | A1273 | Typical Force-main Crossings Drawings_IFA Client review | 12 |  |  |  |  | A1272
AR 11/19 | A1274 | Typical Force-main Crossings Drawings_IFC | 2 |  |  |  |  | A1273
AR 11/19 | A1280 | Force-main Crossings Schedule_IFR | 5 |  |  |  |  | A1270, A4501, A4150
AR 11/19 | A1281 | Force-main Crossings Schedule_IFR Client review | 12 |  |  |  |  | A1280
AR 11/19 | A1282 | Force-main Crossings Schedule_IFA | 4 |  |  |  |  | A1281
AR 11/19 | A1283 | Force-main Crossings Schedule_IFA Client review | 12 |  |  |  |  | A1282
AR 11/19 | A1284 | Force-main Crossings Schedule_IFC | 3 |  |  |  |  | A1283
AR 11/19 | A1290 | Tie-in details drawing (SWTP-9)_IFR | 3 |  |  |  |  | A3600, A1650, A1660
AR 11/19 | A1291 | Tie-in details drawing (SWTP-9)_IFR Client review | 12 |  |  |  |  | A1290
AR 11/19 | A1292 | Tie-in details drawing (SWTP-9)_IFA | 2 |  |  |  |  | A1291
AR 11/19 | A1293 | Tie-in details drawing (SWTP-9)_IFA Client review | 12 |  |  |  |  | A1292
AR 11/19 | A1294 | Tie-in details drawing (SWTP-9)_IFC | 2 |  |  |  |  | A1293
AR 11/19 | A1300 | Tie-in details drawing (JUBAIL TOWN)_IFR | 3 |  |  |  |  | A1650, A1660, A3600, A1290
AR 11/19 | A1301 | Tie-in details drawing (JUBAIL TOWN)_IFR Client review | 12 |  |  |  |  | A1300
AR 11/19 | A1302 | Tie-in details drawing (JUBAIL TOWN)_IFA | 2 |  |  |  |  | A1301
AR 11/19 | A1303 | Tie-in details drawing (JUBAIL TOWN)_IFA Client review | 12 |  |  |  |  | A1302
AR 11/19 | A1304 | Tie-in details drawing (JUBAIL TOWN)_IFC | 2 |  |  |  |  | A1303
AR 11/19 | A1313 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900_IFR | 3 |  |  |  |  | A1180, A1190, A3550, A3590, A1530
AR 11/19 | A1314 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900_IFR Client review | 12 |  |  |  |  | A1313
AR 11/19 | A1315 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900_IFA | 2 |  |  |  |  | A1314
AR 11/19 | A1316 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900_IFA Client review | 12 |  |  |  |  | A1315
AR 11/19 | A1317 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 900_IFC | 2 |  |  |  |  | A1316
AR 11/19 | A1320 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2_IFR | 4 |  |  |  |  | A1325, A1313
AR 11/19 | A1321 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2_IFR CR | 12 |  |  |  |  | A1320
AR 11/19 | A1322 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2_IFA | 3 |  |  |  |  | A1321
AR 11/19 | A1323 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2_IFA CR | 12 |  |  |  |  | A1322
AR 11/19 | A1324 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 1 of 2_IFC | 2 |  |  |  |  | A1323
AR 11/19 | A1325 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200_IFR | 3 |  |  |  |  | A3590, A1180, A1190, A3530, A1530
AR 11/19 | A1326 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200_IFR Client review | 12 |  |  |  |  | A1325
AR 11/19 | A1327 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200_IFA | 2 |  |  |  |  | A1326
AR 11/19 | A1328 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200_IFA Client review | 12 |  |  |  |  | A1327
AR 11/19 | A1329 | Typical Drawings for washout chambers/air valve chambers / isolation valves Chamber DN 1200_IFC | 2 |  |  |  |  | A1328
AR 11/19 | A1330 | Isometric Drawings Tie-in connection_IFR | 4 |  |  |  |  | A1290, A1300, A1325, A1313
AR 11/19 | A1331 | Isometric Drawings Tie-in connection_IFR Client review | 12 |  |  |  |  | A1330
AR 11/19 | A1332 | Isometric Drawings Tie-in connection_IFA | 3 |  |  |  |  | A1331
AR 11/19 | A1333 | Isometric Drawings Tie-in connection_IFA Client review | 12 |  |  |  |  | A1332
AR 11/19 | A1334 | Isometric Drawings Tie-in connection_IFC | 2 |  |  |  |  | A1333
AR 11/19 | A1362 | Force-main special crossings Details_IFR | 4 |  |  |  |  | A4501, A4150, A1330
AR 11/19 | A1363 | Force-main special crossings Details_IFR Client review | 12 |  |  |  |  | A1362
AR 11/19 | A1372 | Force-main special crossings Details_IFA | 3 |  |  |  |  | A1363
AR 11/19 | A1373 | Force-main special crossings Details_IFA Client review | 12 |  |  |  |  | A1372
AR 11/19 | A1382 | Force-main special crossings Details_IFC | 2 |  |  |  |  | A1373
AR 11/19 | A1530 | General Plot Plan PS -56-A_IFR | 5 |  |  |  |  | A3970
AR 11/19 | A1531 | General Plot Plan PS -56-A_IFR Client review | 12 |  |  |  |  | A1530
AR 11/19 | A1532 | General Plot Plan PS -56-A_IFA | 4 |  |  |  |  | A1531
AR 11/19 | A1533 | General Plot Plan PS -56-A_IFA Client review | 12 |  |  |  |  | A1532
AR 11/19 | A1534 | General Plot Plan PS -56-A_IFC | 3 |  |  |  |  | A3935, A5040, A3943, A3938, A1533
AR 11/19 | A1550 | Piping Layout Drawings PS -56-A_IFR | 5 |  |  |  |  | A1530
AR 11/19 | A1551 | Piping Layout Drawings PS -56-A_IFR Client review | 12 |  |  |  |  | A1550
AR 11/19 | A1552 | Piping Layout Drawings PS -56-A_IFA | 4 |  |  |  |  | A1551
AR 11/19 | A1553 | Piping Layout Drawings PS -56-A_IFA Client review | 12 |  |  |  |  | A1552
AR 11/19 | A1554 | Piping Layout Drawings PS -56-A_IFC | 3 |  |  |  |  | A1534, A1553
AR 11/19 | A1560 | Piping support Drawings PS -56-A_IFR | 5 |  |  |  |  | A1570
AR 11/19 | A1561 | Piping support Drawings PS -56-A_IFR Client review | 12 |  |  |  |  | A1560
AR 11/19 | A1562 | Piping support Drawings PS -56-A_IFA | 4 |  |  |  |  | A1561
AR 11/19 | A1563 | Piping support Drawings PS -56-A_IFA Client review | 12 |  |  |  |  | A1562
AR 11/19 | A1564 | Piping support Drawings PS -56-A_IFC | 3 |  |  |  |  | A1563
AR 11/19 | A1570 | Isometric Drawings PS -56-A_IFR | 4 |  |  |  |  | A1532, A1550, A5050
AR 11/19 | A1571 | Isometric Drawings PS -56-A_IFR Client review | 12 |  |  |  |  | A1570
AR 11/19 | A1572 | Isometric Drawings PS -56-A_IFA | 3 |  |  |  |  | A1571
AR 11/19 | A1573 | Isometric Drawings PS -56-A_IFA Client review | 12 |  |  |  |  | A1572
AR 11/19 | A1574 | Isometric Drawings PS -56-A_IFC | 2 |  |  |  |  | A1573
AR 11/19 | A5050 | Section and Detail Drawing PS-56A_IFR | 5 |  |  |  |  | A1530
AR 11/19 | A5051 | Section and Detail Drawing PS-56A_IFR Client review | 12 |  |  |  |  | A5050
AR 11/19 | A5060 | Section and Detail Drawing PS-56A_IFA | 4 |  |  |  |  | A5051
AR 11/19 | A5061 | Section and Detail Drawing PS-56A_IFA Client review | 12 |  |  |  |  | A5060
AR 11/19 | A5070 | Section and Detail Drawing PS-56A_IFC | 3 |  |  |  |  | A1534, A5061
AR 11/19 | A5371 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 2 of 2_IFR | 4 |  |  |  |  | A1325, A1313
AR 11/19 | A5372 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 2 of 2_IFR CR | 12 |  |  |  |  | A5371
AR 11/19 | A5373 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 2 of 2_IFA | 3 |  |  |  |  | A5372
AR 11/19 | A5374 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 2 of 2_IFA CR | 12 |  |  |  |  | A5373
AR 11/19 | A5375 | Pipe and valves supports details for washout chambers/air valve chambers / isolation valves Chamber Sheet 2 of 2_IFC | 2 |  |  |  |  | A5374
AR 11/19 | A3720 | Data Sheet for 34.5kV Ring Main Unit_IFR | 3 |  |  |  |  | A3750
AR 11/19 | A3721 | Data Sheet for 34.5kV Ring Main Unit_IFR Client review | 12 |  |  |  |  | A3720
AR 11/19 | A3722 | Data Sheet for 34.5kV Ring Main Unit_IFA | 2 |  |  |  |  | A3721
AR 11/19 | A3723 | Data Sheet for 34.5kV Ring Main Unit_IFA Client review | 12 |  |  |  |  | A3722
AR 11/19 | A3724 | Data Sheet for 34.5kV Ring Main Unit_IFC | 2 |  |  |  |  | A3723
AR 11/19 | A3730 | Data Sheet for 34,5 KV Switchgear_IFR | 3 |  |  |  |  | A3760
AR 11/19 | A3731 | Data Sheet for 34,5 KV Switchgear_IFR Client review | 12 |  |  |  |  | A3730
AR 11/19 | A3732 | Data Sheet for 34,5 KV Switchgear_IFA | 2 |  |  |  |  | A3731
AR 11/19 | A3733 | Data Sheet for 34,5 KV Switchgear_IFA Client review | 12 |  |  |  |  | A3732
AR 11/19 | A3734 | Data Sheet for 34,5 KV Switchgear_IFC | 2 |  |  |  |  | A3733
AR 11/19 | A3740 | Electical Legends and Symbols_IFR | 3 |  |  |  |  | A3750, A3760, A3840
AR 11/19 | A3741 | Electical Legends and Symbols_IFR Client review | 12 |  |  |  |  | A3740
AR 11/19 | A3742 | Electical Legends and Symbols_IFA | 2 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800, A3741
AR 11/19 | A3743 | Electical Legends and Symbols_IFA Client review | 12 |  |  |  |  | A3742
AR 11/19 | A3744 | Electical Legends and Symbols_IFC | 2 |  |  |  |  | A3742, A3743
AR 11/19 | A3750 | Single Line Diagram for RMU_IFR | 3 |  |  |  |  | A3830
AR 11/19 | A3751 | Single Line Diagram for RMU_IFR Client review | 12 |  |  |  |  | A3750
AR 11/19 | A3752 | Single Line Diagram for RMU_IFA | 2 |  |  |  |  | A3751
AR 11/19 | A3753 | Single Line Diagram for RMU_IFA Client review | 12 |  |  |  |  | A3752
AR 11/19 | A3754 | Single Line Diagram for RMU_IFC | 2 |  |  |  |  | A3753
AR 11/19 | A3760 | Single Line Diagram for 34,5 KV Switchgear_IFR | 4 |  |  |  |  | A3750
AR 11/19 | A3761 | Single Line Diagram for 34,5 KV Switchgear_IFR Client review | 12 |  |  |  |  | A3760
AR 11/19 | A3762 | Single Line Diagram for 34,5 KV Switchgear_IFA | 3 |  |  |  |  | A3761
AR 11/19 | A3763 | Single Line Diagram for 34,5 KV Switchgear_IFA Client review | 12 |  |  |  |  | A3762
AR 11/19 | A3764 | Single Line Diagram for 34,5 KV Switchgear_IFC | 2 |  |  |  |  | A3763
AR 11/19 | A3770 | Requisition for 34.5kV RMU and SWITCHGEAR_IFU | 3 |  |  |  |  | A3722, A3732
AR 11/19 | A3780 | Data Sheet for 34,5 KV/4,16 KV Transformer_IFR | 3 |  |  |  |  | A3830
AR 11/19 | A3781 | Data Sheet for 34,5 KV/4,16 KV Transformer_IFR Client review | 12 |  |  |  |  | A3780
AR 11/19 | A3782 | Data Sheet for 34,5 KV/4,16 KV Transformer_IFA | 2 |  |  |  |  | A3781
AR 11/19 | A3783 | Data Sheet for 34,5 KV/4,16 KV Transformer_IFA Client review | 12 |  |  |  |  | A3782
AR 11/19 | A3784 | Data Sheet for 34,5 KV/4,16 KV Transformer_IFC | 2 |  |  |  |  | A3783
AR 11/19 | A3790 | Requisition for Transformers_IFU | 3 |  |  |  |  | A3782
AR 11/19 | A3800 | Data Sheet for MV Emergency Diesel Generator_IFR | 3 |  |  |  |  | A3620
AR 11/19 | A3801 | Data Sheet for MV Emergency Diesel Generator_IFR Client review | 12 |  |  |  |  | A3800
AR 11/19 | A3802 | Data Sheet for MV Emergency Diesel Generator_IFA | 2 |  |  |  |  | A3801
AR 11/19 | A3803 | Data Sheet for MV Emergency Diesel Generator_IFA Client review | 12 |  |  |  |  | A3802
AR 11/19 | A3804 | Data Sheet for MV Emergency Diesel Generator_IFC | 2 |  |  |  |  | A3803
AR 11/19 | A3810 | Requisition for for MV Emergency Diesel Generator_IFU | 3 |  |  |  |  | A3800
AR 11/19 | A3820 | Data Sheet for 4,16 KV Switchgear_IFR | 2 |  |  |  |  | A3840
AR 11/19 | A3821 | Data Sheet for 4,16 KV Switchgear_IFR Client review | 12 |  |  |  |  | A3820
AR 11/19 | A3822 | Data Sheet for 4,16 KV Switchgear_IFA | 2 |  |  |  |  | A3821
AR 11/19 | A3823 | Data Sheet for 4,16 KV Switchgear_IFA Client review | 12 |  |  |  |  | A3822
AR 11/19 | A3824 | Data Sheet for 4,16 KV Switchgear_IFC | 2 |  |  |  |  | A3823
AR 11/19 | A3830 | Key One Line Diagram & Power Distribution_IFR | 3 |  |  |  |  | A4020, A4040
AR 11/19 | A3831 | Key One Line Diagram & Power Distribution_IFR Client review | 12 |  |  |  |  | A3830
AR 11/19 | A3832 | Key One Line Diagram & Power Distribution_IFA | 2 |  |  |  |  | A3831
AR 11/19 | A3833 | Key One Line Diagram & Power Distribution_IFA Client review | 12 |  |  |  |  | A3832
AR 11/19 | A3834 | Key One Line Diagram & Power Distribution_IFC | 2 |  |  |  |  | A3833
AR 11/19 | A3840 | Single Line Diagram for 4,16 KV Switchgear_IFR | 4 |  |  |  |  | A3760
AR 11/19 | A3841 | Single Line Diagram for 4,16 KV Switchgear_IFR Client review | 12 |  |  |  |  | A3840
AR 11/19 | A3842 | Single Line Diagram for 4,16 KV Switchgear_IFA | 3 |  |  |  |  | A3841
AR 11/19 | A3843 | Single Line Diagram for 4,16 KV Switchgear_IFA Client review | 12 |  |  |  |  | A3842
AR 11/19 | A3844 | Single Line Diagram for 4,16 KV Switchgear_IFC | 2 |  |  |  |  | A3843
AR 11/19 | A3850 | Requisition for MV switchgear_IFU | 3 |  |  |  |  | A3822
AR 11/19 | A3860 | Data Sheet for MV Variable Frequency Drive_IFR | 3 |  |  |  |  | A3730
AR 11/19 | A3861 | Data Sheet for MV Variable Frequency Drive_IFR Client review | 12 |  |  |  |  | A3860
AR 11/19 | A3862 | Data Sheet for MV Variable Frequency Drive_IFA | 2 |  |  |  |  | A3861
AR 11/19 | A3863 | Data Sheet for MV Variable Frequency Drive_IFA Client review | 12 |  |  |  |  | A3862
AR 11/19 | A3864 | Data Sheet for MV Variable Frequency Drive_IFC | 2 |  |  |  |  | A3863
AR 11/19 | A3870 | Requisition for MV Varible Frequency Drives Panels_IFU | 3 |  |  |  |  | A3862
AR 11/19 | A2390 | Data Sheet for 4,16 KV/0,48 KV Transformer_IFR | 3 |  |  |  |  | A2760, A3840
AR 11/19 | A2391 | Data Sheet for 4,16 KV/0,48 KV Transformer_IFR Client review | 12 |  |  |  |  | A2390
AR 11/19 | A2392 | Data Sheet for 4,16 KV/0,48 KV Transformer_IFA | 2 |  |  |  |  | A2391
AR 11/19 | A2393 | Data Sheet for 4,16 KV/0,48 KV Transformer_IFA Client review | 12 |  |  |  |  | A2392
AR 11/19 | A2394 | Data Sheet for 4,16 KV/0,48 KV Transformer_IFC | 2 |  |  |  |  | A2393
AR 11/19 | A2400 | Data Sheet for LV MCC/Switchboard_IFR | 3 |  |  |  |  | A2760
AR 11/19 | A2401 | Data Sheet for LV MCC/Switchboard_IFR Client review | 12 |  |  |  |  | A2400
AR 11/19 | A2402 | Data Sheet for LV MCC/Switchboard_IFA | 2 |  |  |  |  | A2401
AR 11/19 | A2403 | Data Sheet for LV MCC/Switchboard_IFA Client review | 12 |  |  |  |  | A2402
AR 11/19 | A2404 | Data Sheet for LV MCC/Switchboard_IFC | 2 |  |  |  |  | A2403
AR 11/19 | A2410 | Data Sheet for Dry Type Transformer_IFR | 3 |  |  |  |  | A2760, A2800
AR 11/19 | A2411 | Data Sheet for Dry Type Transformer_IFR Client review | 12 |  |  |  |  | A2410
AR 11/19 | A2412 | Data Sheet for Dry Type Transformer_IFA | 2 |  |  |  |  | A2411
AR 11/19 | A2413 | Data Sheet for Dry Type Transformer_IFA Client review | 12 |  |  |  |  | A2412
AR 11/19 | A2414 | Data Sheet for Dry Type Transformer_IFC | 2 |  |  |  |  | A2413
AR 11/19 | A2460 | Data Sheet for 10 KVA AC UPS_IFR | 3 |  |  |  |  | A2770
AR 11/19 | A2461 | Data Sheet for 10 KVA AC UPS_IFR Client review | 12 |  |  |  |  | A2460
AR 11/19 | A2462 | Data Sheet for 10 KVA AC UPS_IFA | 2 |  |  |  |  | A2461
AR 11/19 | A2463 | Data Sheet for 10 KVA AC UPS_IFA Client review | 12 |  |  |  |  | A2462
AR 11/19 | A2464 | Data Sheet for 10 KVA AC UPS_IFC | 2 |  |  |  |  | A2463
AR 11/19 | A2470 | Data Sheet for Battery charger and Rectifier_IFR | 3 |  |  |  |  | A2780, A2460
AR 11/19 | A2471 | Data Sheet for Battery charger and Rectifier_IFR Client review | 12 |  |  |  |  | A2470
AR 11/19 | A2472 | Data Sheet for Battery charger and Rectifier_IFA | 2 |  |  |  |  | A2471
AR 11/19 | A2473 | Data Sheet for Battery charger and Rectifier_IFA Client review | 12 |  |  |  |  | A2472
AR 11/19 | A2474 | Data Sheet for Battery charger and Rectifier_IFC | 2 |  |  |  |  | A2473
AR 11/19 | A2570 | Requisition for LV MCC/Switchboard_IFU | 3 |  |  |  |  | A2402
AR 11/19 | A2590 | Requisition for AC Uninterruptible Power Supply_IFU | 3 |  |  |  |  | A2462
AR 11/19 | A2600 | Requisition for DC Battery charger and Rectifier _IFU | 3 |  |  |  |  | A2462
AR 11/19 | A2610 | Requisition for MV/LV Electrical Cables_IFU | 3 |  |  |  |  | A2720, A2730
AR 11/19 | A2620 | Requisition for Local Control Panels_IFU | 3 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2630 | Requisition for Lighting Equipments and Fixtures_IFU | 3 |  |  |  |  | A4050
AR 11/19 | A2640 | Requisition for Earthing & Lightning Protection Systems_IFU | 3 |  |  |  |  | A4060
AR 11/19 | A2650 | Requisition for Electrical Bulk material_IFU | 3 |  |  |  |  | A4070
AR 11/19 | A2490 | Load Flow Analysis Report_IFR | 3 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2491 | Load Flow Analysis Report_IFR Client review | 12 |  |  |  |  | A2490
AR 11/19 | A2492 | Load Flow Analysis Report_IFA | 3 |  |  |  |  | A2491
AR 11/19 | A2493 | Load Flow Analysis Report_IFA Client review | 12 |  |  |  |  | A2492
AR 11/19 | A2494 | Load Flow Analysis Report_IFC | 2 |  |  |  |  | A2493
AR 11/19 | A2500 | Short circuit Study_IFR | 5 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2501 | Short circuit Study_IFR Client review | 12 |  |  |  |  | A2500
AR 11/19 | A2502 | Short circuit Study_IFA | 4 |  |  |  |  | A2501
AR 11/19 | A2503 | Short circuit Study_IFA Client review | 12 |  |  |  |  | A2502
AR 11/19 | A2504 | Short circuit Study_IFC | 2 |  |  |  |  | A2503
AR 11/19 | A2510 | Motor Starting Study_IFR | 3 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2511 | Motor Starting Study_IFR Client review | 12 |  |  |  |  | A2510
AR 11/19 | A2512 | Motor Starting Study_IFA | 2 |  |  |  |  | A2511
AR 11/19 | A2513 | Motor Starting Study_IFA Client review | 12 |  |  |  |  | A2512
AR 11/19 | A2514 | Motor Starting Study_IFC | 2 |  |  |  |  | A2513
AR 11/19 | A2520 | Relay Co-ordination and selectivity study_IFR | 9 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2521 | Relay Co-ordination and selectivity study_IFR Client review | 12 |  |  |  |  | A2520
AR 11/19 | A2522 | Relay Co-ordination and selectivity study_IFA | 5 |  |  |  |  | A2521, A5045
AR 11/19 | A2523 | Relay Co-ordination and selectivity study_IFA Client review | 12 |  |  |  |  | A2522
AR 11/19 | A2524 | Relay Co-ordination and selectivity study_IFC | 2 |  |  |  |  | A2523, A5047
AR 11/19 | A2530 | MV Cable Sizing Calculation_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A2531 | MV Cable Sizing Calculation_IFR Client review | 12 |  |  |  |  | A2530
AR 11/19 | A2532 | MV Cable Sizing Calculation_IFA | 2 |  |  |  |  | A2531
AR 11/19 | A2533 | MV Cable Sizing Calculation_IFA Client review | 12 |  |  |  |  | A2532
AR 11/19 | A2534 | MV Cable Sizing Calculation_IFC | 2 |  |  |  |  | A2533
AR 11/19 | A2540 | LV Cable Sizing Calculation_IFR | 4 |  |  |  |  | A2870
AR 11/19 | A2541 | LV Cable Sizing Calculation_IFR Client review | 12 |  |  |  |  | A2540
AR 11/19 | A2542 | LV Cable Sizing Calculation_IFA | 3 |  |  |  |  | A2541
AR 11/19 | A2543 | LV Cable Sizing Calculation_IFA Client review | 12 |  |  |  |  | A2542
AR 11/19 | A2544 | LV Cable Sizing Calculation_IFC | 2 |  |  |  |  | A2543
AR 11/19 | A2550 | Indoor Lighting System Calculation_IFR | 3 |  |  |  |  | A4020, A3190, A3220, A3240, A3300, A3310, A3320, A3350, A3380, A1780, A1820, A1830
AR 11/19 | A2551 | Indoor Lighting System Calculation_IFR Client review | 12 |  |  |  |  | A2550
AR 11/19 | A2552 | Indoor Lighting System Calculation_IFA | 3 |  |  |  |  | A2551
AR 11/19 | A2553 | Indoor Lighting System Calculation_IFA Client review | 12 |  |  |  |  | A2552
AR 11/19 | A2554 | Indoor Lighting System Calculation_IFC | 2 |  |  |  |  | A2553
AR 11/19 | A2560 | Outdoor Lighting System Calculation_IFR | 3 |  |  |  |  | A2870
AR 11/19 | A2561 | Outdoor Lighting System Calculation_IFR Client review | 12 |  |  |  |  | A2560
AR 11/19 | A2562 | Outdoor Lighting System Calculation_IFA | 2 |  |  |  |  | A2561
AR 11/19 | A2563 | Outdoor Lighting System Calculation_IFA Client review | 12 |  |  |  |  | A2562
AR 11/19 | A2564 | Outdoor Lighting System Calculation_IFC | 2 |  |  |  |  | A2563
AR 11/19 | A4010 | Earthing & Lightning calculation_IFR | 3 |  |  |  |  | A1530, A1550, A3880, A5050
AR 11/19 | A4011 | Earthing & Lightning calculation_IFR Client review | 12 |  |  |  |  | A4010
AR 11/19 | A4012 | Earthing & Lightning calculation_IFA | 2 |  |  |  |  | A4011
AR 11/19 | A4013 | Earthing & Lightning calculation_IFA Client review | 12 |  |  |  |  | A4012
AR 11/19 | A4014 | Earthing & Lightning calculation_IFC | 2 |  |  |  |  | A4013
AR 11/19 | A4020 | Detailed Calculation for Electrical Equipments_IFR | 3 |  |  |  |  | A2700, A2710
AR 11/19 | A4021 | Detailed Calculation for Electrical Equipments_IFR Client review | 12 |  |  |  |  | A4020
AR 11/19 | A4022 | Detailed Calculation for Electrical Equipments_IFA | 2 |  |  |  |  | A4021
AR 11/19 | A4023 | Detailed Calculation for Electrical Equipments_IFA Client review | 12 |  |  |  |  | A4022
AR 11/19 | A4024 | Detailed Calculation for Electrical Equipments_IFC | 2 |  |  |  |  | A4023
AR 11/19 | A4030 | AC & DC UPS Sizing Calculation_IFR | 3 |  |  |  |  | A3750, A3760, A3840
AR 11/19 | A4031 | AC & DC UPS Sizing Calculation_IFR Client review | 12 |  |  |  |  | A4030
AR 11/19 | A4032 | AC & DC UPS Sizing Calculation_IFA | 2 |  |  |  |  | A4031
AR 11/19 | A4033 | AC & DC UPS Sizing Calculation_IFA Client review | 12 |  |  |  |  | A4032
AR 11/19 | A4034 | AC & DC UPS Sizing Calculation_IFC | 2 |  |  |  |  | A4033
AR 11/19 | A4040 | Power Factor Improvement Calculation_IFR | 3 |  |  |  |  | A4020
AR 11/19 | A4041 | Power Factor Improvement Calculation_IFR Client review | 12 |  |  |  |  | A4040
AR 11/19 | A4042 | Power Factor Improvement Calculation_IFA | 2 |  |  |  |  | A4041
AR 11/19 | A4043 | Power Factor Improvement Calculation_IFA Client review | 12 |  |  |  |  | A4042
AR 11/19 | A4044 | Power Factor Improvement Calculation_IFC | 2 |  |  |  |  | A4043
AR 11/19 | A2690 | Electrical Equipment List_IFR | 3 |  |  |  |  | A3750, A3760, A3830, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2691 | Electrical Equipment List_IFR Client review | 12 |  |  |  |  | A2690
AR 11/19 | A2692 | Electrical Equipment List_IFA | 2 |  |  |  |  | A2691
AR 11/19 | A2693 | Electrical Equipment List_IFA Client review | 12 |  |  |  |  | A2692
AR 11/19 | A2694 | Electrical Equipment List_IFC | 2 |  |  |  |  | A2693
AR 11/19 | A2700 | Calculation Load Normal Operation_IFR | 3 |  |  |  |  | A1640
AR 11/19 | A2701 | Calculation Load Normal Operation_IFR Client review | 12 |  |  |  |  | A2700
AR 11/19 | A2702 | Calculation Load Normal Operation_IFA | 2 |  |  |  |  | A2701
AR 11/19 | A2703 | Calculation Load Normal Operation_IFA Client review | 12 |  |  |  |  | A2702
AR 11/19 | A2704 | Calculation Load Normal Operation_IFC | 2 |  |  |  |  | A2703
AR 11/19 | A2710 | Calculation Load Standby Operation_IFR | 3 |  |  |  |  | A1640
AR 11/19 | A2711 | Calculation Load Standby Operation_IFR Client review | 12 |  |  |  |  | A2710
AR 11/19 | A2712 | Calculation Load Standby Operation_IFA | 2 |  |  |  |  | A2711
AR 11/19 | A2713 | Calculation Load Standby Operation_IFA Client review | 12 |  |  |  |  | A2712
AR 11/19 | A2714 | Calculation Load Standby Operation_IFC | 2 |  |  |  |  | A2713
AR 11/19 | A2720 | Electrical MV Cable Schedule_IFR | 3 |  |  |  |  | A2530
AR 11/19 | A2721 | Electrical MV Cable Schedule_IFR Client review | 12 |  |  |  |  | A2720
AR 11/19 | A2722 | Electrical MV Cable Schedule_IFA | 2 |  |  |  |  | A2721
AR 11/19 | A2723 | Electrical MV Cable Schedule_IFA Client review | 12 |  |  |  |  | A2722
AR 11/19 | A2724 | Electrical MV Cable Schedule_IFC | 2 |  |  |  |  | A2723
AR 11/19 | A2730 | Electrical LV Cable Schedule_IFR | 5 |  |  |  |  | A2540, A3931
AR 11/19 | A2731 | Electrical LV Cable Schedule_IFR Client review | 12 |  |  |  |  | A2730
AR 11/19 | A2732 | Electrical LV Cable Schedule_IFA | 4 |  |  |  |  | A2731
AR 11/19 | A2733 | Electrical LV Cable Schedule_IFA Client review | 12 |  |  |  |  | A2732
AR 11/19 | A2734 | Electrical LV Cable Schedule_IFC | 2 |  |  |  |  | A2733
AR 11/19 | A2740 | Electrical Tie-in Schedule_IFR | 3 |  |  |  |  | A3750, A3760, A3830, A2870, A2930
AR 11/19 | A2741 | Electrical Tie-in Schedule_IFR Client review | 12 |  |  |  |  | A2740
AR 11/19 | A2742 | Electrical Tie-in Schedule_IFA | 2 |  |  |  |  | A2741
AR 11/19 | A2743 | Electrical Tie-in Schedule_IFA Client review | 12 |  |  |  |  | A2742
AR 11/19 | A2744 | Electrical Tie-in Schedule_IFC | 2 |  |  |  |  | A2743
AR 11/19 | A4050 | Lighting Equipments and Fixtures MTO_IFU | 3 |  |  |  |  | A4110
AR 11/19 | A4060 | Earthing & Lightning Protection Systems Material List_IFR | 3 |  |  |  |  | A4120
AR 11/19 | A4061 | Earthing & Lightning Protection Systems Material List_IFR Client review | 12 |  |  |  |  | A4060
AR 11/19 | A4062 | Earthing & Lightning Protection Systems Material List_IFA | 2 |  |  |  |  | A4061
AR 11/19 | A4063 | Earthing & Lightning Protection Systems Material List_IFA Client review | 12 |  |  |  |  | A4062
AR 11/19 | A4064 | Earthing & Lightning Protection Systems Material List_IFC | 2 |  |  |  |  | A4063
AR 11/19 | A4070 | Electrical Bulk material List_IFR | 3 |  |  |  |  | A4100, A2832, A2872, A2882, A2892
AR 11/19 | A4071 | Electrical Bulk material List_IFR Client review | 12 |  |  |  |  | A4070
AR 11/19 | A4072 | Electrical Bulk material List_IFA | 2 |  |  |  |  | A4071
AR 11/19 | A4073 | Electrical Bulk material List_IFA Client review | 12 |  |  |  |  | A4072
AR 11/19 | A4074 | Electrical Bulk material List_IFC | 2 |  |  |  |  | A4073
AR 11/19 | A2750 | Electrical Index of Drawing_IFR | 3 |  |  |  |  | A3980
AR 11/19 | A2751 | Electrical Index of Drawing_IFR Client review | 12 |  |  |  |  | A2750
AR 11/19 | A2752 | Electrical Index of Drawing_IFA | 2 |  |  |  |  | A2751
AR 11/19 | A2753 | Electrical Index of Drawing_IFA Client review | 12 |  |  |  |  | A2752
AR 11/19 | A2754 | Electrical Index of Drawing_IFC | 2 |  |  |  |  | A3984, A2753
AR 11/19 | A2760 | Single Line Diagram for LV MCC/Switchboard_IFR | 4 |  |  |  |  | A3830
AR 11/19 | A2761 | Single Line Diagram for LV MCC/Switchboard_IFR Client review | 12 |  |  |  |  | A2760
AR 11/19 | A2762 | Single Line Diagram for LV MCC/Switchboard_IFA | 3 |  |  |  |  | A2761
AR 11/19 | A2763 | Single Line Diagram for LV MCC/Switchboard_IFA Client review | 12 |  |  |  |  | A2762
AR 11/19 | A2764 | Single Line Diagram for LV MCC/Switchboard_IFC | 2 |  |  |  |  | A2763
AR 11/19 | A2770 | Single Line Diagram for AC UPS_IFR | 3 |  |  |  |  | A4030
AR 11/19 | A2771 | Single Line Diagram for AC UPS_IFR Client review | 12 |  |  |  |  | A2770
AR 11/19 | A2772 | Single Line Diagram for AC UPS_IFA | 2 |  |  |  |  | A2771
AR 11/19 | A2773 | Single Line Diagram for AC UPS_IFA Client review | 12 |  |  |  |  | A2772
AR 11/19 | A2774 | Single Line Diagram for AC UPS_IFC | 2 |  |  |  |  | A2773
AR 11/19 | A2780 | Single Line Diagram for DC Battery charger and Rectifier_IFR | 3 |  |  |  |  | A4030
AR 11/19 | A2781 | Single Line Diagram for DC Battery charger and Rectifier_IFR Client review | 12 |  |  |  |  | A2780
AR 11/19 | A2782 | Single Line Diagram for DC Battery charger and Rectifier_IFA | 2 |  |  |  |  | A2781
AR 11/19 | A2783 | Single Line Diagram for DC Battery charger and Rectifier_IFA Client review | 12 |  |  |  |  | A2782
AR 11/19 | A2784 | Single Line Diagram for DC Battery charger and Rectifier_IFC | 2 |  |  |  |  | A2783
AR 11/19 | A2790 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules_IFR | 3 |  |  |  |  | A2840, A2910, A2920
AR 11/19 | A2791 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules_IFR Client review | 12 |  |  |  |  | A2790
AR 11/19 | A2792 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules_IFA | 2 |  |  |  |  | A2791
AR 11/19 | A2793 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules_IFA Client review | 12 |  |  |  |  | A2792
AR 11/19 | A2794 | Single Line Diagram for Lighting & Utilities Distrubition Panels Schedules_IFC | 2 |  |  |  |  | A2793
AR 11/19 | A2800 | Single Line Diagram for External Lighting Distrubition Panels_IFR | 3 |  |  |  |  | A4140
AR 11/19 | A2801 | Single Line Diagram for External Lighting Distrubition Panels_IFR Client review | 12 |  |  |  |  | A2800
AR 11/19 | A2802 | Single Line Diagram for External Lighting Distrubition Panels_IFA | 2 |  |  |  |  | A2801
AR 11/19 | A2803 | Single Line Diagram for External Lighting Distrubition Panels_IFA Client review | 12 |  |  |  |  | A2802
AR 11/19 | A2804 | Single Line Diagram for External Lighting Distrubition Panels_IFC | 2 |  |  |  |  | A2803
AR 11/19 | A2810 | Typical Schematic and Wiring Diagrams_IFR | 3 |  |  |  |  | A3750, A3760, A3840, A2760, A2770, A2780, A2790, A2800
AR 11/19 | A2811 | Typical Schematic and Wiring Diagrams_IFR Client review | 12 |  |  |  |  | A2810
AR 11/19 | A2812 | Typical Schematic and Wiring Diagrams_IFA | 2 |  |  |  |  | A2811
AR 11/19 | A2813 | Typical Schematic and Wiring Diagrams_IFA Client review | 12 |  |  |  |  | A2812
AR 11/19 | A2814 | Typical Schematic and Wiring Diagrams_IFC | 2 |  |  |  |  | A2813
AR 11/19 | A2820 | Equipments Arrangement for SEC Interface Building_IFR | 3 |  |  |  |  | A3760, A1780, A3220
AR 11/19 | A2821 | Equipments Arrangement for SEC Interface Building_IFR Client review | 12 |  |  |  |  | A2820
AR 11/19 | A2822 | Equipments Arrangement for SEC Interface Building_IFA | 2 |  |  |  |  | A2821
AR 11/19 | A2823 | Equipments Arrangement for SEC Interface Building_IFA Client review | 12 |  |  |  |  | A2822
AR 11/19 | A2824 | Equipments Arrangement for SEC Interface Building_IFC | 2 |  |  |  |  | A2823
AR 11/19 | A2830 | Cable Routing Layout & Details for SEC Interface Building_IFR | 3 |  |  |  |  | A2720, A2730
AR 11/19 | A2831 | Cable Routing Layout & Details for SEC Interface Building_IFR Client review | 12 |  |  |  |  | A2830
AR 11/19 | A2832 | Cable Routing Layout & Details for SEC Interface Building_IFA | 2 |  |  |  |  | A2831
AR 11/19 | A2833 | Cable Routing Layout & Details for SEC Interface Building_IFA Client review | 12 |  |  |  |  | A2832
AR 11/19 | A2834 | Cable Routing Layout & Details for SEC Interface Building_IFC | 2 |  |  |  |  | A2833
AR 11/19 | A2840 | Indoor Lighting & Small Power for SEC Interface Building_IFR | 3 |  |  |  |  | A2550
AR 11/19 | A2841 | Indoor Lighting & Small Power for SEC Interface Building_IFR Client review | 12 |  |  |  |  | A2840
AR 11/19 | A2842 | Indoor Lighting & Small Power for SEC Interface Building_IFA | 2 |  |  |  |  | A2841
AR 11/19 | A2843 | Indoor Lighting & Small Power for SEC Interface Building_IFA Client review | 12 |  |  |  |  | A2842
AR 11/19 | A2844 | Indoor Lighting & Small Power for SEC Interface Building_IFC | 2 |  |  |  |  | A2843
AR 11/19 | A2850 | Earthing Details for SEC Interface Building_IFR | 3 |  |  |  |  | A2820, A2930
AR 11/19 | A2851 | Earthing Details for SEC Interface Building_IFR Client review | 12 |  |  |  |  | A2850
AR 11/19 | A2852 | Earthing Details for SEC Interface Building_IFA | 2 |  |  |  |  | A2851
AR 11/19 | A2853 | Earthing Details for SEC Interface Building_IFA Client review | 12 |  |  |  |  | A2852
AR 11/19 | A2854 | Earthing Details for SEC Interface Building_IFC | 2 |  |  |  |  | A2853
AR 11/19 | A2860 | Lightning protection layout for SEC Interface Building_IFR | 3 |  |  |  |  | A2850
AR 11/19 | A2861 | Lightning protection layout for SEC Interface Building_IFR Client review | 12 |  |  |  |  | A2860
AR 11/19 | A2862 | Lightning protection layout for SEC Interface Building_IFA | 2 |  |  |  |  | A2861
AR 11/19 | A2863 | Lightning protection layout for SEC Interface Building_IFA Client review | 12 |  |  |  |  | A2862
AR 11/19 | A2864 | Lightning protection layout for SEC Interface Building_IFC | 2 |  |  |  |  | A2863
AR 11/19 | A2870 | General Cable Routing Layout_IFR | 3 |  |  |  |  | A1530, A1550, A3750, A3760, A3840, A2760, A2770, A2780, A5050
AR 11/19 | A2871 | General Cable Routing Layout_IFR Client review | 12 |  |  |  |  | A2870
AR 11/19 | A2872 | General Cable Routing Layout_IFA | 3 |  |  |  |  | A2871
AR 11/19 | A2873 | General Cable Routing Layout_IFA Client review | 12 |  |  |  |  | A2872
AR 11/19 | A2874 | General Cable Routing Layout_IFC | 2 |  |  |  |  | A2873
AR 11/19 | A2880 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings_IFR | 3 |  |  |  |  | A2720, A2730, A1780, A1830, A3180, A3190, A3240, A2870, A3185
AR 11/19 | A2881 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings_IFR Client review | 12 |  |  |  |  | A2880
AR 11/19 | A2882 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings_IFA | 3 |  |  |  |  | A2881
AR 11/19 | A2883 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings_IFA Client review | 12 |  |  |  |  | A2882
AR 11/19 | A2884 | Cable Routing Layout & Details for Electrical/Control/Diesel Generator Buildings_IFC | 2 |  |  |  |  | A2883
AR 11/19 | A2890 | Cable Routing Layout & Details for Pump Station building_IFR | 3 |  |  |  |  | A2720, A2730, A3300, A3310, A2870
AR 11/19 | A2891 | Cable Routing Layout & Details for Pump Station building_IFR Client review | 12 |  |  |  |  | A2890
AR 11/19 | A2892 | Cable Routing Layout & Details for Pump Station building_IFA | 3 |  |  |  |  | A2891
AR 11/19 | A2893 | Cable Routing Layout & Details for Pump Station building_IFA Client review | 12 |  |  |  |  | A2892
AR 11/19 | A2894 | Cable Routing Layout & Details for Pump Station building_IFC | 2 |  |  |  |  | A2893
AR 11/19 | A2900 | Cable and Conduit Schedule_IFR | 3 |  |  |  |  | A2870, A2830, A2880, A2890
AR 11/19 | A2901 | Cable and Conduit Schedule_IFR Client review | 12 |  |  |  |  | A2900
AR 11/19 | A2902 | Cable and Conduit Schedule_IFA | 2 |  |  |  |  | A2901
AR 11/19 | A2903 | Cable and Conduit Schedule_IFA Client review | 12 |  |  |  |  | A2902
AR 11/19 | A2904 | Cable and Conduit Schedule_IFC | 2 |  |  |  |  | A2903
AR 11/19 | A2910 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings_IFR | 3 |  |  |  |  | A2550
AR 11/19 | A2911 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings_IFR Client review | 12 |  |  |  |  | A2910
AR 11/19 | A2912 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings_IFA | 3 |  |  |  |  | A2911
AR 11/19 | A2913 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings_IFA Client review | 12 |  |  |  |  | A2912
AR 11/19 | A2914 | Indoor Lighting & Small Power for Electrical/Control/Diesel Generator Buildings_IFC | 2 |  |  |  |  | A2913
AR 11/19 | A2920 | Indoor Lighting & Small Power for Pump Station building_IFR | 3 |  |  |  |  | A2550
AR 11/19 | A2921 | Indoor Lighting & Small Power for Pump Station building_IFR Client review | 12 |  |  |  |  | A2920
AR 11/19 | A2922 | Indoor Lighting & Small Power for Pump Station building_IFA | 2 |  |  |  |  | A2921
AR 11/19 | A2923 | Indoor Lighting & Small Power for Pump Station building_IFA Client review | 12 |  |  |  |  | A2922
AR 11/19 | A2924 | Indoor Lighting & Small Power for Pump Station building_IFC | 2 |  |  |  |  | A2923
AR 11/19 | A2930 | Overall Earthing Layout_IFR | 3 |  |  |  |  | A1530, A1550, A4010, A5050
AR 11/19 | A2931 | Overall Earthing Layout_IFR Client review | 12 |  |  |  |  | A2930
AR 11/19 | A2932 | Overall Earthing Layout_IFA | 2 |  |  |  |  | A2931
AR 11/19 | A2933 | Overall Earthing Layout_IFA Client review | 12 |  |  |  |  | A2932
AR 11/19 | A2934 | Overall Earthing Layout_IFC | 2 |  |  |  |  | A1534, A2933
AR 11/19 | A2940 | Earthing Details for Electrical/Control/Diesel Generator Buildings_IFR | 3 |  |  |  |  | A4010, A1780, A1830, A3180, A3190, A3240, A3320, A3380, A2870, A3185
AR 11/19 | A2941 | Earthing Details for Electrical/Control/Diesel Generator Buildings_IFR Client review | 12 |  |  |  |  | A2940
AR 11/19 | A2942 | Earthing Details for Electrical/Control/Diesel Generator Buildings_IFA | 2 |  |  |  |  | A2941
AR 11/19 | A2943 | Earthing Details for Electrical/Control/Diesel Generator Buildings_IFA Client review | 12 |  |  |  |  | A2942
AR 11/19 | A2944 | Earthing Details for Electrical/Control/Diesel Generator Buildings_IFC | 2 |  |  |  |  | A2943
AR 11/19 | A2950 | Earthing Details for Pump Station building_IFR | 3 |  |  |  |  | A4010, A3300, A3310, A2870
AR 11/19 | A2951 | Earthing Details for Pump Station building_IFR Client review | 12 |  |  |  |  | A2950
AR 11/19 | A2952 | Earthing Details for Pump Station building_IFA | 2 |  |  |  |  | A2951
AR 11/19 | A2953 | Earthing Details for Pump Station building_IFA Client review | 12 |  |  |  |  | A2952
AR 11/19 | A2954 | Earthing Details for Pump Station building_IFC | 2 |  |  |  |  | A2953
AR 11/19 | A4080 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings_IFR | 3 |  |  |  |  | A2940
AR 11/19 | A4081 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings_IFR Client review | 12 |  |  |  |  | A4080
AR 11/19 | A4082 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings_IFA | 2 |  |  |  |  | A4081
AR 11/19 | A4083 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings_IFA Client review | 12 |  |  |  |  | A4082
AR 11/19 | A4084 | Lightning protection layout for Electrical/Control/Diesel Generator Buildings_IFC | 2 |  |  |  |  | A4083
AR 11/19 | A4090 | Lightning protection layout for Pump Station building_IFR | 3 |  |  |  |  | A2950
AR 11/19 | A4091 | Lightning protection layout for Pump Station building_IFR Client review | 12 |  |  |  |  | A4090
AR 11/19 | A4092 | Lightning protection layout for Pump Station building_IFA | 2 |  |  |  |  | A4091
AR 11/19 | A4093 | Lightning protection layout for Pump Station building_IFA Client review | 12 |  |  |  |  | A4092
AR 11/19 | A4094 | Lightning protection layout for Pump Station building_IFC | 2 |  |  |  |  | A4093
AR 11/19 | A4100 | Electrical Routing Installation Details_IFR | 3 |  |  |  |  | A2830, A2880, A2890
AR 11/19 | A4101 | Electrical Routing Installation Details_IFR Client review | 12 |  |  |  |  | A4100
AR 11/19 | A4102 | Electrical Routing Installation Details_IFA | 2 |  |  |  |  | A4101
AR 11/19 | A4103 | Electrical Routing Installation Details_IFA Client review | 12 |  |  |  |  | A4102
AR 11/19 | A4104 | Electrical Routing Installation Details_IFC | 2 |  |  |  |  | A4103
AR 11/19 | A4110 | Electrical Lighting Installation Details_IFR | 3 |  |  |  |  | A2840, A4140, A2910, A2920
AR 11/19 | A4111 | Electrical Lighting Installation Details_IFR Client review | 12 |  |  |  |  | A4110
AR 11/19 | A4112 | Electrical Lighting Installation Details_IFA | 2 |  |  |  |  | A4111
AR 11/19 | A4113 | Electrical Lighting Installation Details_IFA Client review | 12 |  |  |  |  | A4112
AR 11/19 | A4114 | Electrical Lighting Installation Details_IFC | 2 |  |  |  |  | A4113
AR 11/19 | A4120 | Electrical Earthing & Lightning Installation Details_IFR | 2 |  |  |  |  | A2930, A2850, A2940, A2950, A2860, A4080, A4090
AR 11/19 | A4121 | Electrical Earthing & Lightning Installation Details_IFR Client review | 12 |  |  |  |  | A4120
AR 11/19 | A4122 | Electrical Earthing & Lightning Installation Details_IFA | 2 |  |  |  |  | A4121
AR 11/19 | A4123 | Electrical Earthing & Lightning Installation Details_IFA Client review | 12 |  |  |  |  | A4122
AR 11/19 | A4124 | Electrical Earthing & Lightning Installation Details_IFC | 2 |  |  |  |  | A4123
AR 11/19 | A4130 | Electrical Interconection Drawing_IFR | 6 |  |  |  |  | A5045
AR 11/19 | A4131 | Electrical Interconection Drawing_IFR Client review | 12 |  |  |  |  | A4130
AR 11/19 | A4132 | Electrical Interconection Drawing_IFA | 4 |  |  |  |  | A4131, A5047
AR 11/19 | A4133 | Electrical Interconection Drawing_IFA Client review | 12 |  |  |  |  | A4132
AR 11/19 | A4134 | Electrical Interconection Drawing_IFC | 2 |  |  |  |  | A4133
AR 11/19 | A4140 | External Lighting Layout_IFR | 3 |  |  |  |  | A2560
AR 11/19 | A4141 | External Lighting Layout_IFR Client review | 12 |  |  |  |  | A4140
AR 11/19 | A4142 | External Lighting Layout_IFA | 2 |  |  |  |  | A4141
AR 11/19 | A4143 | External Lighting Layout_IFA Client review | 12 |  |  |  |  | A4142
AR 11/19 | A4144 | External Lighting Layout_IFC | 2 |  |  |  |  | A4143
AR 11/19 | A3605 | Specification for Control System_IFR | 3 |  |  |  |  | A3600
AR 11/19 | A3606 | Specification for Control System_IFR Client review | 12 |  |  |  |  | A3605
AR 11/19 | A3607 | Specification for Control System_IFA | 2 |  |  |  |  | A3606
AR 11/19 | A3608 | Specification for Control System_IFA Client review | 12 |  |  |  |  | A3607
AR 11/19 | A3609 | Specification for Control System_IFC | 2 |  |  |  |  | A3984, A3608
AR 11/19 | A3610 | Requisition for Control System_IFU | 3 |  |  |  |  | A3607, A2100
AR 11/19 | A1850 | General Specification of Instrumentation_IFR | 3 |  |  |  |  | A3600
AR 11/19 | A1851 | General Specification of Instrumentation_IFR Client review | 12 |  |  |  |  | A1850
AR 11/19 | A1852 | General Specification of Instrumentation_IFA | 2 |  |  |  |  | A1851
AR 11/19 | A1853 | General Specification of Instrumentation_IFA Client review | 12 |  |  |  |  | A1852
AR 11/19 | A1854 | General Specification of Instrumentation_IFC | 2 |  |  |  |  | A1853
AR 11/19 | A1870 | Specification for Instrumentation Cables_IFR | 3 |  |  |  |  | A3980, A3930
AR 11/19 | A1871 | Specification for Instrumentation Cables_IFR Client review | 12 |  |  |  |  | A1870
AR 11/19 | A1872 | Specification for Instrumentation Cables_IFA | 3 |  |  |  |  | A1871
AR 11/19 | A1873 | Specification for Instrumentation Cables_IFA Client review | 12 |  |  |  |  | A1872
AR 11/19 | A1874 | Specification for Instrumentation Cables_IFC | 2 |  |  |  |  | A3984, A1873
AR 11/19 | A1880 | Specification for Fire and Gas System_IFR | 3 |  |  |  |  | A3980, A3930, A1870
AR 11/19 | A1881 | Specification for Fire and Gas System_IFR Client review | 12 |  |  |  |  | A1880
AR 11/19 | A1882 | Specification for Fire and Gas System_IFA | 2 |  |  |  |  | A1881
AR 11/19 | A1883 | Specification for Fire and Gas System_IFA Client review | 12 |  |  |  |  | A1882
AR 11/19 | A1884 | Specification for Fire and Gas System_IFC | 2 |  |  |  |  | A3984, A1883
AR 11/19 | A1890 | Specification for Telephony and LAN_IFR | 3 |  |  |  |  | A3980, A3930, A1880
AR 11/19 | A1891 | Specification for Telephony and LAN_IFR Client review | 12 |  |  |  |  | A1890
AR 11/19 | A1892 | Specification for Telephony and LAN_IFA | 2 |  |  |  |  | A1891
AR 11/19 | A1893 | Specification for Telephony and LAN_IFA Client review | 12 |  |  |  |  | A1892
AR 11/19 | A1894 | Specification for Telephony and LAN_IFC | 2 |  |  |  |  | A1893
AR 11/19 | A1900 | Data Sheet for Fire and Gas System Instruments_IFR | 3 |  |  |  |  | A2200
AR 11/19 | A1901 | Data Sheet for Fire and Gas System Instruments_IFR Client review | 12 |  |  |  |  | A1900
AR 11/19 | A1902 | Data Sheet for Fire and Gas System Instruments_IFA | 2 |  |  |  |  | A1901
AR 11/19 | A1903 | Data Sheet for Fire and Gas System Instruments_IFA Client review | 12 |  |  |  |  | A1902
AR 11/19 | A1904 | Data Sheet for Fire and Gas System Instruments_IFC | 2 |  |  |  |  | A1903
AR 11/19 | A1910 | Data Sheet for Pressure Measuring Instruments_IFR | 3 |  |  |  |  | A2090
AR 11/19 | A1911 | Data Sheet for Pressure Measuring Instruments_IFR Client review | 12 |  |  |  |  | A1910
AR 11/19 | A1912 | Data Sheet for Pressure Measuring Instruments_IFA | 2 |  |  |  |  | A1911
AR 11/19 | A1913 | Data Sheet for Pressure Measuring Instruments_IFA Client review | 12 |  |  |  |  | A1912
AR 11/19 | A1914 | Data Sheet for Pressure Measuring Instruments_IFC | 2 |  |  |  |  | A1913
AR 11/19 | A1920 | Data Sheet for Flow Measuring Instruments_IFR | 3 |  |  |  |  | A2090, A1910
AR 11/19 | A1921 | Data Sheet for Flow Measuring Instruments_IFR Client review | 12 |  |  |  |  | A1920
AR 11/19 | A1922 | Data Sheet for Flow Measuring Instruments_IFA | 2 |  |  |  |  | A1921
AR 11/19 | A1923 | Data Sheet for Flow Measuring Instruments_IFA Client review | 12 |  |  |  |  | A1922
AR 11/19 | A1924 | Data Sheet for Flow Measuring Instruments_IFC | 2 |  |  |  |  | A1923
AR 11/19 | A1930 | Data Sheet for Level Measuring Instruments_IFR | 3 |  |  |  |  | A2090, A1920
AR 11/19 | A1931 | Data Sheet for Level Measuring Instruments_IFR Client review | 12 |  |  |  |  | A1930
AR 11/19 | A1932 | Data Sheet for Level Measuring Instruments_IFA | 2 |  |  |  |  | A1931
AR 11/19 | A1933 | Data Sheet for Level Measuring Instruments_IFA Client review | 12 |  |  |  |  | A1932
AR 11/19 | A1934 | Data Sheet for Level Measuring Instruments_IFC | 2 |  |  |  |  | A1933
AR 11/19 | A1940 | Data Sheet for Measuring and Analysis Instruments_IFR | 3 |  |  |  |  | A2090, A1930
AR 11/19 | A1941 | Data Sheet for Measuring and Analysis Instruments_IFR Client review | 12 |  |  |  |  | A1940
AR 11/19 | A1942 | Data Sheet for Measuring and Analysis Instruments_IFA | 2 |  |  |  |  | A1941
AR 11/19 | A1943 | Data Sheet for Measuring and Analysis Instruments_IFA Client review | 12 |  |  |  |  | A1942
AR 11/19 | A1944 | Data Sheet for Measuring and Analysis Instruments_IFC | 2 |  |  |  |  | A1943
AR 11/19 | A1950 | Data Sheet for MOVs_IFR | 3 |  |  |  |  | A2090, A1920
AR 11/19 | A1951 | Data Sheet for MOVs_IFR Client review | 12 |  |  |  |  | A1950
AR 11/19 | A1952 | Data Sheet for MOVs_IFA | 2 |  |  |  |  | A1951
AR 11/19 | A1953 | Data Sheet for MOVs_IFA Client review | 12 |  |  |  |  | A1952
AR 11/19 | A1954 | Data Sheet for MOVs_IFC | 2 |  |  |  |  | A1953
AR 11/19 | A1960 | Datasheet of Junction Boxes_IFR | 2 |  |  |  |  | A2182, A1940
AR 11/19 | A1961 | Datasheet of Junction Boxes_IFR Client review | 12 |  |  |  |  | A1960
AR 11/19 | A1962 | Datasheet of Junction Boxes_IFA | 2 |  |  |  |  | A1961
AR 11/19 | A1963 | Datasheet of Junction Boxes_IFA Client review | 12 |  |  |  |  | A1962
AR 11/19 | A1964 | Datasheet of Junction Boxes_IFC | 2 |  |  |  |  | A1963
AR 11/19 | A1970 | Instrument cable datasheets_IFR | 2 |  |  |  |  | A2110, A1960
AR 11/19 | A1971 | Instrument cable datasheets_IFR Client review | 12 |  |  |  |  | A1970
AR 11/19 | A1972 | Instrument cable datasheets_IFA | 2 |  |  |  |  | A1971
AR 11/19 | A1973 | Instrument cable datasheets_IFA Client review | 12 |  |  |  |  | A1972
AR 11/19 | A1974 | Instrument cable datasheets_IFC | 2 |  |  |  |  | A1973
AR 11/19 | A1990 | Requisition for Fire and Gas System_IFU | 2 |  |  |  |  | A1902
AR 11/19 | A2000 | Requisition for Telephony and LAN_IFU | 2 |  |  |  |  | A2240
AR 11/19 | A2010 | Requisition for MOVs_IFU | 2 |  |  |  |  | A1952
AR 11/19 | A2020 | Requisition for Pressure Measuring Instruments_IFU | 2 |  |  |  |  | A1912
AR 11/19 | A2030 | Requisition for Flow Measuring Instruments_IFU | 2 |  |  |  |  | A1922
AR 11/19 | A2040 | Requisition for Level Measuring Instruments_IFU | 2 |  |  |  |  | A1932
AR 11/19 | A2050 | Requisition for Measuring Instruments and Analysis_IFU | 2 |  |  |  |  | A1942
AR 11/19 | A2060 | Requisition for Junction Boxes_IFU | 2 |  |  |  |  | A1962
AR 11/19 | A2070 | Requisition for Cables Instrumentation_IFU | 2 |  |  |  |  | A1972
AR 11/19 | A2080 | Requisition for Accessories and Fittings_IFU | 2 |  |  |  |  | A3830, A2070
AR 11/19 | A2090 | List of Instruments_IFR | 4 |  |  |  |  | A3600
AR 11/19 | A2091 | List of Instruments_IFR Client review | 12 |  |  |  |  | A2090
AR 11/19 | A2092 | List of Instruments_IFA | 3 |  |  |  |  | A2091
AR 11/19 | A2093 | List of Instruments_IFA Client review | 12 |  |  |  |  | A2092
AR 11/19 | A2094 | List of Instruments_IFC | 2 |  |  |  |  | A2093
AR 11/19 | A2100 | List of Inputs / Outputs_IFR | 3 |  |  |  |  | A2090
AR 11/19 | A2101 | List of Inputs / Outputs_IFR Client review | 12 |  |  |  |  | A2100
AR 11/19 | A2102 | List of Inputs / Outputs_IFA | 2 |  |  |  |  | A2101
AR 11/19 | A2103 | List of Inputs / Outputs_IFA Client review | 12 |  |  |  |  | A2102
AR 11/19 | A2104 | List of Inputs / Outputs_IFC | 2 |  |  |  |  | A2103
AR 11/19 | A2110 | List of Instrumentation Cables_IFR | 3 |  |  |  |  | A2140, A2100
AR 11/19 | A2111 | List of Instrumentation Cables_IFR Client review | 12 |  |  |  |  | A2110
AR 11/19 | A2112 | List of Instrumentation Cables_IFA | 2 |  |  |  |  | A2111
AR 11/19 | A2113 | List of Instrumentation Cables_IFA Client review | 12 |  |  |  |  | A2112
AR 11/19 | A2114 | List of Instrumentation Cables_IFC | 2 |  |  |  |  | A2113
AR 11/19 | A2120 | Instrumentations accessories BOQ_IFR | 3 |  |  |  |  | A2110
AR 11/19 | A2121 | Instrumentations accessories BOQ_IFR Client review | 12 |  |  |  |  | A2120
AR 11/19 | A2122 | Instrumentations accessories BOQ_IFA | 2 |  |  |  |  | A2121
AR 11/19 | A2123 | Instrumentations accessories BOQ_IFA Client review | 12 |  |  |  |  | A2122
AR 11/19 | A2124 | Instrumentations accessories BOQ_IFC | 2 |  |  |  |  | A2123
AR 11/19 | A2240 | MTO for Telephony and LAN_IFU | 3 |  |  |  |  | A2210
AR 11/19 | A2130 | Control System Architecture_IFR | 5 |  |  |  |  | A3605
AR 11/19 | A2131 | Control System Architecture_IFR Client review | 12 |  |  |  |  | A2130
AR 11/19 | A2132 | Control System Architecture_IFA | 4 |  |  |  |  | A2131
AR 11/19 | A2133 | Control System Architecture_IFA Client review | 12 |  |  |  |  | A2132
AR 11/19 | A2134 | Control System Architecture_IFC | 3 |  |  |  |  | A2133
AR 11/19 | A2140 | Instrumentation Block Diagram_IFR | 4 |  |  |  |  | A2130, A2900
AR 11/19 | A2141 | Instrumentation Block Diagram_IFR Client review | 12 |  |  |  |  | A2140
AR 11/19 | A2142 | Instrumentation Block Diagram_IFA | 3 |  |  |  |  | A2141
AR 11/19 | A2143 | Instrumentation Block Diagram_IFA Client review | 12 |  |  |  |  | A2142
AR 11/19 | A2144 | Instrumentation Block Diagram_IFC | 3 |  |  |  |  | A2143
AR 11/19 | A2150 | Instrumentation Loop Diagram_IFR | 10 |  |  |  |  | A2182
AR 11/19 | A2151 | Instrumentation Loop Diagram_IFR Client review | 12 |  |  |  |  | A2150
AR 11/19 | A2152 | Instrumentation Loop Diagram_IFA | 9 |  |  |  |  | A2151
AR 11/19 | A2153 | Instrumentation Loop Diagram_IFA Client review | 12 |  |  |  |  | A2152
AR 11/19 | A2154 | Instrumentation Loop Diagram_IFC | 7 |  |  |  |  | A2153
AR 11/19 | A2160 | Instrument layout drawing_IFR | 5 |  |  |  |  | A1550, A1325, A1313, A5050
AR 11/19 | A2161 | Instrument layout drawing_IFR Client review | 12 |  |  |  |  | A2160
AR 11/19 | A2162 | Instrument layout drawing_IFA | 4 |  |  |  |  | A2161
AR 11/19 | A2163 | Instrument layout drawing_IFA Client review | 12 |  |  |  |  | A2162
AR 11/19 | A2164 | Instrument layout drawing_IFC | 3 |  |  |  |  | A2163
AR 11/19 | A2170 | Instrument cable routing Sheet 1_IFR | 5 |  |  |  |  | A2160
AR 11/19 | A2171 | Instrument cable routing Sheet 1_IFR Client review | 12 |  |  |  |  | A2170
AR 11/19 | A2172 | Instrument cable routing Sheet 1_IFA | 3 |  |  |  |  | A2171
AR 11/19 | A2173 | Instrument cable routing Sheet 1_IFA Client review | 12 |  |  |  |  | A2172
AR 11/19 | A2174 | Instrument cable routing Sheet 1_IFC | 2 |  |  |  |  | A2173
AR 11/19 | A2176 | Instrument cable routing Sheet 2_IFR | 5 |  |  |  |  | A2160, A2170
AR 11/19 | A2177 | Instrument cable routing Sheet 2_IFR Client review | 12 |  |  |  |  | A2176
AR 11/19 | A2178 | Instrument cable routing Sheet 2_IFA | 3 |  |  |  |  | A2177
AR 11/19 | A2179 | Instrument cable routing Sheet 2_IFA Client review | 12 |  |  |  |  | A2178
AR 11/19 | A2180 | Instrument cable routing Sheet 2_IFC | 2 |  |  |  |  | A2179
AR 11/19 | A2182 | Junction Box Connection Diagrams_IFR | 3 |  |  |  |  | A2110
AR 11/19 | A2183 | Junction Box Connection Diagrams_IFR Client review | 12 |  |  |  |  | A2182
AR 11/19 | A2184 | Junction Box Connection Diagrams_IFA | 2 |  |  |  |  | A2183
AR 11/19 | A2185 | Junction Box Connection Diagrams_IFA Client review | 12 |  |  |  |  | A2184
AR 11/19 | A2186 | Junction Box Connection Diagrams_IFC | 2 |  |  |  |  | A2185
AR 11/19 | A2190 | F&G detectors location drawing_IFR | 3 |  |  |  |  | A1530, A3180, A3220, A3240, A3185
AR 11/19 | A2191 | F&G detectors location drawing_IFR Client review | 12 |  |  |  |  | A2190
AR 11/19 | A2192 | F&G detectors location drawing_IFA | 2 |  |  |  |  | A2191
AR 11/19 | A2193 | F&G detectors location drawing_IFA Client review | 12 |  |  |  |  | A2192
AR 11/19 | A2194 | F&G detectors location drawing_IFC | 2 |  |  |  |  | A2193
AR 11/19 | A2200 | Fire alarm riser diagram_IFR | 3 |  |  |  |  | A2190
AR 11/19 | A2201 | Fire alarm riser diagram_IFR Client review | 12 |  |  |  |  | A2200
AR 11/19 | A2202 | Fire alarm riser diagram_IFA | 2 |  |  |  |  | A2201
AR 11/19 | A2203 | Fire alarm riser diagram_IFA Client review | 12 |  |  |  |  | A2202
AR 11/19 | A2204 | Fire alarm riser diagram_IFC | 2 |  |  |  |  | A2203
AR 11/19 | A2210 | Telephony and LAN Implementation Plan_IFR | 3 |  |  |  |  | A3240, A1530, A3180, A3220, A3185
AR 11/19 | A2211 | Telephony and LAN Implementation Plan_IFR Client review | 12 |  |  |  |  | A2210
AR 11/19 | A2212 | Telephony and LAN Implementation Plan_IFA | 2 |  |  |  |  | A2211
AR 11/19 | A2213 | Telephony and LAN Implementation Plan_IFA Client review | 12 |  |  |  |  | A2212
AR 11/19 | A2214 | Telephony and LAN Implementation Plan_IFC | 2 |  |  |  |  | A2213
AR 11/19 | A2220 | Junction Box mounting and installation details_IFR | 6 |  |  |  |  | A2182
AR 11/19 | A2221 | Junction Box mounting and installation details_IFR Client review | 12 |  |  |  |  | A2220
AR 11/19 | A2222 | Junction Box mounting and installation details_IFA | 4 |  |  |  |  | A2221
AR 11/19 | A2223 | Junction Box mounting and installation details_IFA Client review | 12 |  |  |  |  | A2222
AR 11/19 | A2224 | Junction Box mounting and installation details_IFC | 3 |  |  |  |  | A2223
AR 11/19 | A2230 | Instrumentation Hookup drawing_IFR | 6 |  |  |  |  | A1910, A1920, A1930, A1940, A1950
AR 11/19 | A2231 | Instrumentation Hookup drawing_IFR Client review | 12 |  |  |  |  | A2230
AR 11/19 | A2232 | Instrumentation Hookup drawing_IFA | 4 |  |  |  |  | A2231
AR 11/19 | A2233 | Instrumentation Hookup drawing_IFA Client review | 12 |  |  |  |  | A2232
AR 11/19 | A2234 | Instrumentation Hookup drawing_IFC | 3 |  |  |  |  | A2233
AR 11/19 | A2960 | HSE Philosophy_IFR | 4 |  |  |  |  | A3640, A3982
AR 11/19 | A2961 | HSE Philosophy_IFR Client review | 12 |  |  |  |  | A2960
AR 11/19 | A2962 | HSE Philosophy_IFA | 3 |  |  |  |  | A2961
AR 11/19 | A2963 | HSE Philosophy_IFA Client review | 12 |  |  |  |  | A2962
AR 11/19 | A2964 | HSE Philosophy_IFC | 2 |  |  |  |  | A2963
AR 11/19 | A2970 | Fire Fighting Calculations Report_IFR | 5 |  |  |  |  | A2960, A3280, A3300, A3180, A3220, A3240, A3185
AR 11/19 | A2971 | Fire Fighting Calculations Report_IFR Client review | 12 |  |  |  |  | A2970
AR 11/19 | A2972 | Fire Fighting Calculations Report_IFA | 4 |  |  |  |  | A2971
AR 11/19 | A2973 | Fire Fighting Calculations Report_IFA Client review | 12 |  |  |  |  | A2972
AR 11/19 | A2974 | Fire Fighting Calculations Report_IFC | 2 |  |  |  |  | A2973
AR 11/19 | A3030 | P&ID's Fire water system_IFR | 5 |  |  |  |  | A3530, A3550, A1530, A3602
AR 11/19 | A3031 | P&ID's Fire water system_IFR Client review | 12 |  |  |  |  | A3030
AR 11/19 | A3032 | P&ID's Fire water system_IFA | 4 |  |  |  |  | A3031
AR 11/19 | A3033 | P&ID's Fire water system_IFA Client review | 12 |  |  |  |  | A3032
AR 11/19 | A3034 | P&ID's Fire water system_IFC | 2 |  |  |  |  | A3033
AR 11/19 | A3040 | Fire fighting Layouts_IFR | 8 |  |  |  |  | A3550, A3530, A2960, A3030, A2970
AR 11/19 | A3041 | Fire fighting Layouts_IFR Client review | 12 |  |  |  |  | A3040
AR 11/19 | A3042 | Fire fighting Layouts_IFA | 6 |  |  |  |  | A3041, A5046
AR 11/19 | A3043 | Fire fighting Layouts_IFA Client review | 12 |  |  |  |  | A3042
AR 11/19 | A3044 | Fire fighting Layouts_IFC | 5 |  |  |  |  | A3043
AR 11/19 | A3050 | Hazardous Area Classification Layout_IFR | 4 |  |  |  |  | A3020
AR 11/19 | A3051 | Hazardous Area Classification Layout_IFR Client review | 12 |  |  |  |  | A3050
AR 11/19 | A3052 | Hazardous Area Classification Layout_IFA | 3 |  |  |  |  | A3051
AR 11/19 | A3053 | Hazardous Area Classification Layout_IFA Cliet review | 12 |  |  |  |  | A3052
AR 11/19 | A3054 | Hazardous Area Classification Layout_IFC | 2 |  |  |  |  | A3053
AR 11/19 | A3010 | Safety equipment list_IFR | 3 |  |  |  |  | A3604, A2990
AR 11/19 | A3011 | Safety equipment list_IFR Client review | 12 |  |  |  |  | A3010
AR 11/19 | A3012 | Safety equipment list_IFA | 2 |  |  |  |  | A3011
AR 11/19 | A3013 | Safety equipment list_IFA Client review | 12 |  |  |  |  | A3012
AR 11/19 | A3014 | Safety equipment list_IFC | 2 |  |  |  |  | A3013
AR 11/19 | A3020 | Hazardous Area Classification Schedule_IFR | 4 |  |  |  |  | A3980, A1530, A3602
AR 11/19 | A3021 | Hazardous Area Classification Schedule_IFR Client review | 12 |  |  |  |  | A3020
AR 11/19 | A3022 | Hazardous Area Classification Schedule_IFA | 3 |  |  |  |  | A3021
AR 11/19 | A3023 | Hazardous Area Classification Schedule_IFA Client review | 12 |  |  |  |  | A3022
AR 11/19 | A3024 | Hazardous Area Classification Schedule_IFC | 2 |  |  |  |  | A3023
AR 11/19 | A2980 | Safety Equipment Specification_IFR | 4 |  |  |  |  | A3980, A1852
AR 11/19 | A2981 | Safety Equipment Specification_IFR Client review | 12 |  |  |  |  | A2980
AR 11/19 | A2982 | Safety Equipment Specification_IFA | 3 |  |  |  |  | A2981
AR 11/19 | A2983 | Safety Equipment Specification_IFA Client review | 12 |  |  |  |  | A2982
AR 11/19 | A2984 | Safety Equipment Specification_IFC | 2 |  |  |  |  | A2983
AR 11/19 | A2990 | Safety Equipment Datasheet_IFR | 5 |  |  |  |  | A2980
AR 11/19 | A2991 | Safety Equipment Datasheet_IFR Client review | 12 |  |  |  |  | A2990
AR 11/19 | A2992 | Safety Equipment Datasheet_IFA | 3 |  |  |  |  | A2991
AR 11/19 | A2993 | Safety Equipment Datasheet_IFA Client review | 12 |  |  |  |  | A2992
AR 11/19 | A2994 | Safety Equipment Datasheet_IFC | 2 |  |  |  |  | A2993
AR 11/19 | A3000 | Safety Equipment Requisition_IFU | 3 |  |  |  |  | A2982, A2992