## Planning
Référence | Activity ID | Activity Name | Original Duration | NBHIngenieursenior | NBHIngenieurjunior | NBHProjeteursenior | NBHProjeteurjunior | Predecessors (activity name)
AR 11/19 | A5042 | Permit Package approval | 0 |  |  |  |  | A3935
AR 11/19 | A5043 | SEC Permit Submission | 0 |  |  |  |  | A2700, A2710, A3840, A3830, A3760, A2760